## Instructions
Project Planner - MS Project-compatible Excel template
REQUIREMENTS
Excel version | Excel 2019 or Microsoft 365 (Windows or Mac), or Excel for the web. No macros needed.
HOW IT WORKS
1. Settings | Set project start and status date (both typed dates; Ctrl+; enters today), working week (Mon-Sun Yes/No), hours/day, Gantt scale and sprint calendar. Add holidays on 'Holidays'. Update the status date whenever you report progress.
2. Resources | List people/roles with Max Units and hourly rate. They appear in the Resource dropdown on Tasks and in sprint capacity.
3. Tasks | One row per task. Enter Level (1 = phase/summary, 2 = task, 3 = sub-task...), Task Name, Duration in working days (0 = milestone), and up to two predecessors by UID with link type (FS, SS, FF, SF) and lag in days (negative = lead). A row becomes a SUMMARY automatically when the rows beneath it have a higher level; its dates, work, cost and progress roll up. Optional Deadline: Deadline Check shows 'Late by Nd'. Hover over a column header for what it means.
4. Set the baseline | When the plan is agreed: on Tasks, select the 5 'BL Source' columns (all task rows), Copy, then select the first 'Baseline Start' cell and Paste Special > Values. Planned Start/Finish now stay frozen (like MS Project's Baseline) and the variance columns compare against it. To re-baseline, repeat; to clear it, delete the 5 Baseline columns' contents.
5. Track progress | Enter Actual Start, Actual Finish and % Complete. Forecast Start/Finish then use actuals and push every dependent task. Start / Finish / Duration / Work / Cost Var and Status flag slippage. Optionally enter Actual Cost (cost to date) on detail tasks; blank = Cost x Progress.
Critical path | Late Start / Late Finish come from a backward pass from the forecast project finish (and any deadline). Total Slack = how far a task can slip before it delays the project or a deadline; Free Slack = before it delays a successor. Critical = slack <= Settings > CriticalSlackDays on an unfinished task. A missed deadline gives negative slack to the task and the chain feeding it.
6. Gantt | Read-only view: dark outline = planned dates, green = done, blue = remaining on track, red = remaining on the critical path, orange = remaining but late vs plan, dark grey = summary, purple = milestone, red cell = deadline, red border = status date. Change GanttStart / GanttPeriod (1 = days, 7 = weeks) on Settings to scroll or zoom.
7. Sprints | Sprint calendar from Settings. Each task is tagged with the sprint its forecast start falls in. Work hours are prorated across sprints per resource, compared against capacity (Max Units x Hours/day x working days); over-allocations turn red. Optional agile columns: Story Points and Planned Sprint on Tasks (Planned Sprint wins over the automatic sprint), Points Capacity on Sprints; the table then shows committed and done points, velocity and the release burndown.
8. Dashboard | KPIs (including overall RAG, SPI, CPI, missed deadlines, link problems), status counts, upcoming milestones and sprint load vs capacity.
9. Status Report | For steering meetings: overall RAG and RAG by area (schedule, SPI, CPI, deadlines, critical path, plan quality), calculated from the thresholds on Settings (RAG...). Type a PM RAG to override one and say why in Comment. Earned value (BAC, PV, EV, AC, SPI, CPI, EAC, VAC, TCPI) and a commentary box for the period.
10. Schedule Report | Phase summary with RAG, all milestones, late tasks, tasks starting and due in the look-ahead window (Settings > LookaheadDays) and open critical tasks. Lists update with every edit; drag a list's bottom corner down to show more rows.
11. Resource Report | Per resource: work, done, remaining, cost, actual cost, late and critical tasks, peak week and weeks over capacity. Weekly hours and utilisation grids for 26 weeks from Settings > ResourceWeekStart (red = over capacity), and a team hours vs capacity chart.
12. Agile Report | Story points: scope, done, remaining, velocity (last 3 closed sprints) and the sprint it forecasts finishing in; the current sprint's backlog and daily burndown; release burndown and committed vs done charts.
Earned value | Set a baseline first: without one, Budget = current Cost and PV follows the current plan, so SPI and CPI only show progress against the latest plan. PV = budget of work planned before the status date; EV = Budget x Progress; AC = Actual Cost. SPI = EV/PV, CPI = EV/AC, EAC = AC + (BAC - EV)/CPI.
CELL COLOURS
Blue text | Input - type here.
Black text on grey | Formula - do not overwrite. Summary rows grey-out inputs that are ignored.
Dark blue header | Input column. Dark grey header = calculated. Light grey header = helper column (hidden, grouped).
RULES (same as MS Project)
ID and UID | ID = position of the task (renumbers when rows move, like MS Project). UID = permanent number that predecessors refer to, so links survive inserting, deleting and moving rows. A duplicate or missing UID turns red.
Inserting tasks | Tasks is an Excel Table: right-click a row > Insert > Table Rows Above (or type in the row under the table). Every formula fills in automatically. Set the new task's UID to Settings > NextFreeUID (also shown at the top of Tasks).
Outline levels | Each row's Level may be at most 1 higher than the row above. A '?' in WBS (red) means a level jump.
Predecessors | Enter the predecessor's UID. A predecessor must be a detail task listed ABOVE its successor (order tasks roughly by date). Links that break this, or point to an empty row or a missing UID, are ignored and explained in the Link Check column (red). Summary rows ignore Duration / Predecessors / Actuals - they roll up. The rule keeps the schedule and the critical path consistent and rules out circular references.
Mode | Auto = scheduled from predecessors, project start and 'Start No Earlier Than'. Manual = pinned to the date in 'Start No Earlier Than'.
Rescheduling | Settings > RescheduleAfterStatus = Yes moves incomplete work to after the status date (like MS Project 'Update Project'), so late tasks push successors.
Capacity | Tables grow when you add rows: Tasks starts with 200 rows, Resources 50, Sprints 26, Holidays 100. The Gantt and MSP_Tasks sheets show the first 200 tasks (the Gantt says so when there are more).
Speed | An edit recalculates in well under a second for typical plans (about 0.05 s for 200 tasks). Each change to the build is timed in CI; see docs/ARCHITECTURE.md in the repository. Keep the status date typed (not =TODAY()), which would recalculate everything after every edit.
MOVING TO MICROSOFT PROJECT
One-time setting | MS Project > File > Options > Trust Center > Trust Center Settings > Legacy Formats > 'Allow loading files with legacy or non-default file formats'.
Import | In MS Project: File > Open > choose this .xlsx > Import Wizard > New map > 'As a new project' > tick Tasks (and Resources) > Tasks source worksheet = MSP_Tasks, Resources = MSP_Resources. Column headers already use MS Project field names, so the wizard maps them automatically. Map 'Predecessors' (by ID) for a new project; 'Unique ID' and 'Unique ID Predecessors' are for merging into an existing one.
Tip: Start/Finish | For auto-scheduled tasks map Duration + Predecessors (+ Constraint Type/Date) and set Start/Finish to '(not mapped)' - importing Start/Finish makes MS Project add fixed 'Start No Earlier Than' constraints. Map Baseline Start/Finish to keep the plan, and Actual Start/Finish/% Complete for progress.
Rows | Blank MSP_Tasks rows import as blank tasks - delete them in MS Project, or filter the table to non-blank names and copy those rows to a new sheet before importing.
From MS Project to Excel | MS Project > File > Save As > Excel Workbook, then paste Name / Outline Level / Duration / Predecessors etc. into the Tasks input columns (split '3FS+2d' into UID, Type, Lag).
NAMES AND TABLES (Formulas > Name Manager)
Tables | Tasks, ResourceTable, SprintTable, HolidayTable, GanttView, MSPTasks, MSPResources, KPIs, StatusSummary, NextMilestones, OverallStatus, StatusRAG, EarnedValue, StatusNotes, PhaseSummary, MilestoneReport, LateTasks, StartingSoon, DueSoon, CriticalTasks, ResourceSummary, AgileKPIs, SprintBacklog, SprintBurndown and the List* dropdown tables. Inside a table, formulas read [@Column] (this row).
Settings | ProjectStart, StatusDate, StatusWorkday, WorkWeek, Holidays, HoursPerDay, DefaultUnits, RescheduleAfterStatus, GanttStart, GanttPeriod, Sprint1Start, SprintLength, SprintCount, SprintPrefix, SprintLastEnd, CriticalSlackDays, ProjectFinish, PlannedFinish, FinishVarianceDays, LookaheadDays, RAGAmberSlipDays, RAGRedSlipDays, RAGAmberIndex, RAGRedIndex, ResourceWeekStart, CurrentSprint, TotalPoints, NextFreeUID. Report values: ProjectRAG, evm_BAC, evm_PV, evm_EV, evm_AC, evm_SPI, evm_CPI, evm_EAC ...
Task columns | tsk_ID, tsk_UID, tsk_WBS, tsk_Name, tsk_Duration, tsk_PlanStart, tsk_FcFinish, tsk_Status, tsk_Resource, tsk_Work, tsk_Cost ... each is Tasks[Column], so it grows with the table. Other sheets read Tasks only through these names.
Resources / Sprints | res_Name, res_MaxUnits, res_Rate, ... spr_Name, spr_Start, spr_End, spr_WorkDays, spr_Capacity, spr_Work
Key formulas | Calculated start = WORKDAY.INTL(MAX(ProjectStart, [@Start No Earlier Than], predecessor drivers) - 1, 1, WorkWeek, Holidays). Predecessor driver (FS) = WORKDAY.INTL(OFFSET(Tasks[[#Headers],[_LeafCalcFinish]], [@_Pred1Pos], 0), 1 + Lag, WorkWeek, Holidays). Planned Start = Baseline Start if set, else calculated. Summary start = MIN(INDEX(Tasks[_LeafCalcStart], [@_Row]+1):INDEX(Tasks[_LeafCalcStart], [@_Row]+[@_Descendants])), where _Descendants = COUNTIF(Tasks[WBS], [@WBS] & ".*").

## Dashboard
Customer Portal Implementation - Dashboard
Project manager: Priya Sharma Status date: Sun 25-Oct-2026
| Key indicator | Value | Status | Count
| Planned start | 2026-09-07 | Complete | 9
| Planned finish | 2027-01-06 | In Progress | 0
| Forecast finish | 2027-01-06 | Behind | 2
| Finish variance (work days) | 0 | Late Start | 1
| Overall progress (duration-weighted) | 43.42% | Not Started | 11
| Planned progress by status date | 55.48%
| Detail tasks | 23
| Milestones | 5
| Total work (hrs) | 720
| Total cost | 58040
| Current sprint | Sprint 4
| Baseline | Not set (planned = calculated)
| Open critical tasks | 11
| Missed deadlines | 1
| Link problems (see Tasks > Link Check) | 0
| Overall status (see Status Report) | Red
| Schedule performance (SPI) | 0.78218
| Cost performance (CPI) | 0.9343
| Forecast cost at completion (EAC) | 62121.5752
| Story points done / total | 33 / 82
| Next milestones (forecast) | Forecast date
| Build complete | 2026-11-09
| Go-live | 2026-12-15
| Project closed | 2027-01-06
Formulas:
Value = IFERROR(INDEX(tsk_FcFinish,MATCH(SMALL(tsk_MilestoneKey,(ROW()-ROW(NextMilestones[[#Headers],[Next milestones (forecast)]]))),tsk_MilestoneKey,0)),"")

## Status Report
Customer Portal Implementation - Status Report
Status date Sun 25-Oct-2026 Project manager: Priya Sharma Forecast finish Wed 06-Jan-2027 (0 working days vs plan)
| Area | Measure | Value | Calculated | PM RAG | RAG | Comment
| Overall | Worst of the areas below | 2 red, 2 amber | Red |  | Red
| Area | Measure | Value | Calculated | PM RAG | RAG | Comment
| Schedule | Forecast finish vs plan (working days) | 0 | Green |  | Green
| Schedule performance | SPI = earned value / planned value | 0.78218 | Red |  | Red
| Cost performance | CPI = earned value / actual cost | 0.9343 | Amber |  | Amber
| Deadlines | Tasks forecast to miss their deadline | 1 | Red |  | Red
| Critical path | Critical tasks forecast to finish late | 5 | Amber |  | Amber
| Plan quality | Ignored links and outline errors (see Tasks) | 0 | Green |  | Green
EARNED VALUE at the status date
| Measure | Meaning | Value
| Budget at completion (BAC) | Baseline Cost once a baseline is set, otherwise Cost. | 58040
| Planned value (PV) | Budget of the work planned before the status date. | 36360
| Earned value (EV) | Budget of the work done (Budget x Progress). | 28440
| Actual cost (AC) | Actual Cost on Tasks; Cost x Progress where blank. | 30440
| Schedule variance (SV) | EV - PV. Negative = behind plan. | -7920
| Cost variance (CV) | EV - AC. Negative = over cost. | -2000
| Schedule performance index (SPI) | EV / PV. Below 1 = behind. | 0.78218
| Cost performance index (CPI) | EV / AC. Below 1 = over cost. | 0.9343
| Estimate at completion (EAC) | AC + (BAC - EV) / CPI: forecast cost at the current CPI. | 62121.5752
| Estimate to complete (ETC) | EAC - AC: forecast cost of the remaining work. | 31681.5752
| Variance at completion (VAC) | BAC - EAC. Negative = forecast overrun. | -4081.5752
| To-complete performance index (TCPI) | CPI the remaining work needs to finish on budget. | 1.0725
| % complete (earned) | EV / BAC. | 49%
| % complete (planned) | PV / BAC. | 62.65%
COMMENTARY for this period (type in the Notes column)
| Section | Notes
Summary
Achievements this period
Planned for next period
Issues and escalations
Decisions needed
Risks to watch
Note on E4: RAG from the thresholds on Settings (RAGAmberSlipDays, RAGRedSlipDays, RAGAmberIndex, RAGRedIndex).
Note on E7: RAG from the thresholds on Settings (RAGAmberSlipDays, RAGRedSlipDays, RAGAmberIndex, RAGRedIndex).
Note on F4: Optional override by the project manager: Green, Amber or Red.
Note on F7: Optional override by the project manager: Green, Amber or Red.
Note on G4: Reported RAG: the PM override if there is one, otherwise the calculated RAG.
Note on G7: Reported RAG: the PM override if there is one, otherwise the calculated RAG.
Note on H4: Why: especially when the PM RAG differs from the calculated one.
Note on H7: Why: especially when the PM RAG differs from the calculated one.

## Schedule Report
Customer Portal Implementation - Schedule Report
Status date Sun 25-Oct-2026 Forecast finish Wed 06-Jan-2027 (0 working days vs plan)
Phases (outline level 1): 5
| _Task | WBS | Phase | Planned Finish | Forecast Finish | Finish Var | Progress | Budget | PV | EV | AC | SPI | CPI | Open Critical | RAG
| 1 | 1 | Initiation | 2026-09-11 | 2026-09-14 | 1 | 100% | 3400 | 3400 | 3400 | 4160 | 1 | 0.81731 | 0 | Red
| 5 | 2 | Requirements & Design | 2026-10-01 | 2026-10-06 | 3 | 100% | 12480 | 12480 | 12480 | 13040 | 1 | 0.95706 | 0 | Amber
| 10 | 3 | Build | 2026-10-30 | 2026-11-09 | 6 | 45.13% | 26700 | 20480 | 12560 | 13240 | 0.61328 | 0.94864 | 5 | Red
| 20 | 4 | Test & Release | 2027-01-04 | 2027-01-04 | 0 | 0% | 13180 | 0 | 0 | 0 |  |  | 4 | Green
| 27 | 5 | Project Close | 2027-01-06 | 2027-01-06 | 0 | 0% | 2280 | 0 | 0 | 0 |  |  | 2 | Green
Milestones (in planned order): 5
| _Task | WBS | Milestone | Planned | Forecast | Finish Var | Deadline | Deadline Check | Status
| 4 | 1.3 | Kickoff complete | 2026-09-11 | 2026-09-14 | 1 |  |  | Complete
| 9 | 2.4 | Design sign-off | 2026-10-01 | 2026-10-06 | 3 |  |  | Complete
| 19 | 3.3 | Build complete | 2026-10-30 | 2026-11-09 | 6 | 2026-11-06 | Late by 1d | Not Started
| 25 | 4.5 | Go-live | 2026-12-15 | 2026-12-15 | 0 | 2026-12-18 | OK | Not Started
| 30 | 5.3 | Project closed | 2027-01-06 | 2027-01-06 | 0 |  |  | Not Started
Late tasks (most days late first): 7
| _Task | WBS | Task | Resource | Planned Finish | Forecast Finish | Finish Var | Status | Critical
| 13 | 3.1.2 | Core API endpoints | Jordan Lee | 2026-10-22 | 2026-10-30 | 6 | Behind | Yes
| 14 | 3.1.3 | Payment gateway integration | Jordan Lee | 2026-10-30 | 2026-11-09 | 6 | Late Start | Yes
| 17 | 3.2.2 | Feature screens | Sam Rivera | 2026-10-28 | 2026-11-05 | 6 | Behind | Yes
| 18 | 3.2.3 | Accessibility review | Casey Kim | 2026-10-29 | 2026-11-06 | 6 | Not Started | Yes
| 19 | 3.3 | Build complete |  | 2026-10-30 | 2026-11-09 | 6 | Not Started | Yes
| 21 | 4.1 | System integration testing | Taylor Morgan | 2026-11-11 | 2026-11-19 | 6 | Not Started
| 23 | 4.3 | Training & user guides | Casey Kim | 2026-11-10 | 2026-11-18 | 6 | Not Started
Starting by Fri 06-Nov (look-ahead 10 working days): 2
| _Task | WBS | Task | Resource | Forecast Start | Forecast Finish | Duration | Predecessors | Critical
| 14 | 3.1.3 | Payment gateway integration | Jordan Lee | 2026-11-02 | 2026-11-09 | 6 | 13 | Yes
| 18 | 3.2.3 | Accessibility review | Casey Kim | 2026-11-04 | 2026-11-06 | 3 | 17FF+1d | Yes
Due by Fri 06-Nov: 3
| _Task | WBS | Task | Resource | Forecast Finish | Progress | Deadline Check | Status | Critical
| 13 | 3.1.2 | Core API endpoints | Jordan Lee | 2026-10-30 | 50% |  | Behind | Yes
| 17 | 3.2.2 | Feature screens | Sam Rivera | 2026-11-05 | 25% |  | Behind | Yes
| 18 | 3.2.3 | Accessibility review | Casey Kim | 2026-11-06 | 0% |  | Not Started | Yes
Open critical tasks (by forecast start): 11
| _Task | WBS | Task | Resource | Forecast Start | Forecast Finish | Total Slack | Deadline Check | Status
| 13 | 3.1.2 | Core API endpoints | Jordan Lee | 2026-10-15 | 2026-10-30 | -1 |  | Behind
| 17 | 3.2.2 | Feature screens | Sam Rivera | 2026-10-19 | 2026-11-05 | 0 |  | Behind
| 14 | 3.1.3 | Payment gateway integration | Jordan Lee | 2026-11-02 | 2026-11-09 | -1 |  | Late Start
| 18 | 3.2.3 | Accessibility review | Casey Kim | 2026-11-04 | 2026-11-06 | 0 |  | Not Started
| 19 | 3.3 | Build complete |  | 2026-11-09 | 2026-11-09 | -1 | Late by 1d | Not Started
| 22 | 4.2 | User acceptance testing | Morgan Patel | 2026-12-07 | 2026-12-14 | 0 |  | Not Started
| 24 | 4.4 | Go-live readiness review | Priya Sharma | 2026-12-15 | 2026-12-15 | 0 |  | Not Started
| 25 | 4.5 | Go-live |  | 2026-12-15 | 2026-12-15 | 0 | OK | Not Started
| 26 | 4.6 | Hypercare support | Jordan Lee | 2026-12-16 | 2027-01-04 | 0 |  | Not Started
| 29 | 5.2 | Lessons learned | Priya Sharma | 2027-01-05 | 2027-01-06 | 0 |  | Not Started
| 30 | 5.3 | Project closed |  | 2027-01-06 | 2027-01-06 | 0 |  | Not Started
Formulas:
Planned Finish = IF(PhaseSummary[[#This Row],[_Task]]="","",IF(N(INDEX(tsk_PlanFinish,PhaseSummary[[#This Row],[_Task]]))=0,"",INDEX(tsk_PlanFinish,PhaseSummary[[#This Row],[_Task]])))
Planned Finish = IF(MilestoneReport[[#This Row],[_Task]]="","",IF(N(INDEX(tsk_PlanFinish,MilestoneReport[[#This Row],[_Task]]))=0,"",INDEX(tsk_PlanFinish,MilestoneReport[[#This Row],[_Task]])))
Forecast Finish = IF(PhaseSummary[[#This Row],[_Task]]="","",IF(N(INDEX(tsk_FcFinish,PhaseSummary[[#This Row],[_Task]]))=0,"",INDEX(tsk_FcFinish,PhaseSummary[[#This Row],[_Task]])))
Forecast Finish = IF(MilestoneReport[[#This Row],[_Task]]="","",IF(N(INDEX(tsk_FcFinish,MilestoneReport[[#This Row],[_Task]]))=0,"",INDEX(tsk_FcFinish,MilestoneReport[[#This Row],[_Task]])))
Progress = IF(MilestoneReport[[#This Row],[_Task]]="","",IF(N(INDEX(tsk_Deadline,MilestoneReport[[#This Row],[_Task]]))=0,"",INDEX(tsk_Deadline,MilestoneReport[[#This Row],[_Task]])))
Finish Var = IF(LateTasks[[#This Row],[_Task]]="","",IF(N(INDEX(tsk_FcFinish,LateTasks[[#This Row],[_Task]]))=0,"",INDEX(tsk_FcFinish,LateTasks[[#This Row],[_Task]])))
Finish Var = IF(StartingSoon[[#This Row],[_Task]]="","",IF(N(INDEX(tsk_FcFinish,StartingSoon[[#This Row],[_Task]]))=0,"",INDEX(tsk_FcFinish,StartingSoon[[#This Row],[_Task]])))
Note on B5: Row of the task in the Tasks table (helper, hidden).
Note on B18: Row of the task in the Tasks table (helper, hidden).
Note on B36: Row of the task in the Tasks table (helper, hidden).
Note on B54: Row of the task in the Tasks table (helper, hidden).
Note on B72: Row of the task in the Tasks table (helper, hidden).
Note on B90: Row of the task in the Tasks table (helper, hidden).
Note on M5: Earned value / planned value. Below 1 = behind.
Note on N5: Earned value / actual cost. Below 1 = over cost.
Note on O5: Unfinished critical tasks in the phase.
Note on P5: Worst of finish slip, SPI and CPI against the Settings thresholds.

## Resource Report
Customer Portal Implementation - Resource Report
Weeks from Mon 05-Oct-2026 (Settings > ResourceWeekStart). Hours are each task's work spread over its forecast working days; red = more than Max Units x HoursPerDay x working days in the week.
RESOURCES
| Resource | Max Units | Tasks | Work | Work Done | Remaining | Cost | Actual Cost | Late Tasks | Open Critical | Peak Week (h) | Peak Use | Weeks Over
| Priya Sharma | 50% | 4 | 56 | 24 | 32 | 5320 | 3040 | 0 | 2 | 16 | 80% | 0
| Morgan Patel | 100% | 3 | 128 | 80 | 48 | 8960 | 6160 | 0 | 1 | 40 | 100% | 0
| Alex Chen | 50% | 1 | 40 | 40 | 0 | 4400 | 4400 | 0 | 0 | 0 | 0% | 0
| Casey Kim | 100% | 3 | 80 | 48 | 32 | 6000 | 3600 | 2 | 1 | 13.7143 | 34.29% | 0
| Jordan Lee | 100% | 4 | 208 | 80 | 128 | 17680 | 7480 | 2 | 3 | 40 | 100% | 0
| Sam Rivera | 100% | 2 | 144 | 72 | 72 | 11520 | 5760 | 1 | 1 | 34.2857 | 85.71% | 0
| Taylor Morgan | 100% | 1 | 64 | 0 | 64 | 4160 | 0 | 1 | 0 | 32 | 80% | 0
Weekly hours by resource
| Resource | Max Units | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29
| Working days |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Priya Sharma | 50% | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Morgan Patel | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Alex Chen | 50% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Casey Kim | 100% | 13.7143 | 0 | 0 | 0 | 12 | 8 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Jordan Lee | 100% | 20 | 33.3333 | 33.3333 | 33.3333 | 40 | 8 | 0 | 0 | 0 | 0 | 12 | 12 | 12 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sam Rivera | 100% | 18 | 30 | 34.2857 | 34.2857 | 27.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Taylor Morgan | 100% | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Team hours |  | 51.7143 | 63.3333 | 67.619 | 67.619 | 79.4286 | 48 | 52 | 0 | 0 | 40 | 28 | 12 | 12 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Team capacity |  | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 144 | 144 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240
Weekly utilisation by resource (hours / capacity)
| Resource | Max Units | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29
| Working days |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Priya Sharma | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 0% | 0% | 0% | 40% | 0% | 0% | 80% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Morgan Patel | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Alex Chen | 50% | bar: 2026-10-05 to 2027-03-29
| Casey Kim | 100% | 34.29% | 0% | 0% | 0% | 30% | 20% | 30% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Jordan Lee | 100% | 50% | 83.33% | 83.33% | 83.33% | 100% | 20% | 0% | 0% | 0% | 0% | 30% | 50% | 50% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Sam Rivera | 100% | 45% | 75% | 85.71% | 85.71% | 68.57% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Taylor Morgan | 100% | 0% | 0% | 0% | 0% | 0% | 80% | 80% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Cumulative hours at each week boundary (helper for the weekly grids)
|  |  | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 32 | 32 | 32 | 32 | 40 | 40 | 40 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56
|  |  | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 120 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128
|  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
|  |  | 34.2857 | 48 | 48 | 48 | 48 | 60 | 68 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
|  |  | 0 | 20 | 53.3333 | 86.6667 | 120 | 160 | 168 | 168 | 168 | 168 | 168 | 180 | 192 | 204 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208 | 208
|  |  | 0 | 18 | 48 | 82.2857 | 116.5714 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64
Note on E5: Assigned hours.
Note on F5: Work x Progress.
Note on J5: Unfinished tasks forecast to finish after plan, or not started on time (Schedule Report).
Note on L5: Most hours in any week shown in the grid below.
Note on M5: Highest weekly utilisation in the grid.
Note on N5: Weeks in the grid above 100% of capacity.

## Agile Report
Customer Portal Implementation - Agile Report
Status date Sun 25-Oct-2026 Sprint length 14 days. Per-sprint numbers: Sprints sheet. Enter Story Points (and optionally Planned Sprint) on Tasks.
RELEASE
|  | Measure | Value
|  | Total story points (scope) | 82
|  | Done by the status date | 33
|  | Remaining | 49
|  | Velocity (average of the last 3 closed sprints) | 11
|  | Sprints needed at that velocity | 5
|  | Sprints closed | 3
|  | Forecast to finish in | Sprint 8
|  | Forecast finish (velocity) | 2026-12-27
|  | Forecast finish (schedule) | 2027-01-06
|  | Current sprint | Sprint 4
|  | Current sprint: committed points | 8
|  | Current sprint: done so far | 0
|  | Tasks without story points (not milestones) | 0
Current sprint backlog (Sprint 4): 1
| _Task | Task | Story Points | Resource | Forecast Finish | Progress | Status
| 17 | Feature screens | 8 | Sam Rivera | 2026-11-05 | 25% | Behind
CURRENT SPRINT BURNDOWN (story points of the tasks in the sprint)
|  | Day | Remaining | Ideal | _ChartDay | _ChartRemaining | _ChartIdeal
|  | 2026-10-19 | 8 | 7.2 | 19-Oct | 8 | 7.2
|  | 2026-10-20 | 8 | 6.4 | 20-Oct | 8 | 6.4
|  | 2026-10-21 | 8 | 5.6 | 21-Oct | 8 | 5.6
|  | 2026-10-22 | 8 | 4.8 | 22-Oct | 8 | 4.8
|  | 2026-10-23 | 8 | 4 | 23-Oct | 8 | 4
|  | 2026-10-24 | 8 | 4 | 24-Oct | 8 | 4
|  | 2026-10-25 | 8 | 4 | 25-Oct | 8 | 4
|  | 2026-10-26 |  | 3.2 | 26-Oct | #N/A | 3.2
|  | 2026-10-27 |  | 2.4 | 27-Oct | #N/A | 2.4
|  | 2026-10-28 |  | 1.6 | 28-Oct | #N/A | 1.6
|  | 2026-10-29 |  | 0.8 | 29-Oct | #N/A | 0.8
|  | 2026-10-30 |  | 0 | 30-Oct | #N/A | 0
|  | 2026-10-31 |  | 0 | 31-Oct | #N/A | 0
|  | 2026-11-01 |  | 0 | 01-Nov | #N/A | 0
[6 empty] | #N/A | #N/A
[6 empty] | #N/A | #N/A
[6 empty] | #N/A | #N/A
[6 empty] | #N/A | #N/A
[6 empty] | #N/A | #N/A
[6 empty] | #N/A | #N/A
[6 empty] | #N/A | #N/A
[6 empty] | #N/A | #N/A
[6 empty] | #N/A | #N/A
[6 empty] | #N/A | #N/A
[6 empty] | #N/A | #N/A
[6 empty] | #N/A | #N/A
[6 empty] | #N/A | #N/A
[6 empty] | #N/A | #N/A
[6 empty] | #N/A | #N/A
[6 empty] | #N/A | #N/A
[6 empty] | #N/A | #N/A
Formulas:
Forecast Finish = IF(SprintBacklog[[#This Row],[_Task]]="","",IF(N(INDEX(tsk_FcFinish,SprintBacklog[[#This Row],[_Task]]))=0,"",INDEX(tsk_FcFinish,SprintBacklog[[#This Row],[_Task]])))
Task = IF(OR(CurrentSprint="",ROW()-ROW(SprintBurndown[[#Headers],[Day]])>SprintLength),"",CurrentSprintStart+ROW()-ROW(SprintBurndown[[#Headers],[Day]])-1)
Resource = IF(SprintBurndown[[#This Row],[Day]]="","",agl_CurCommitted*MAX(0,1-NETWORKDAYS.INTL(CurrentSprintStart,SprintBurndown[[#This Row],[Day]],WorkWeek,Holidays)/MAX(1,NETWORKDAYS.INTL(CurrentSprintStart,CurrentSprintEnd,WorkWeek,Holidays))))
Note on B20: Row of the task in the Tasks table (helper, hidden).
Note on D43: Committed points not yet done at the end of the day (blank after the status date).
Note on E43: Straight line over the sprint's working days.

## Settings
Project Settings
Blue = edit me. Grey = calculated. Column D shows the defined name every formula uses for that setting.
| Setting | Value | Named range | Notes
| Project name | Customer Portal Implementation | ProjectName | Shown on every sheet title.
| Project manager | Priya Sharma | ProjectManager
| Project start date | 2026-09-07 | ProjectStartDate | Required. Tasks without predecessors start here (moved to the next working day if needed).
| Project start (in use) | 2026-09-07 | ProjectStart | Copy of the date above (dates show as 1900 until it is entered).
| Status date | 2026-10-25 | StatusDateInput | The date progress is reported as of. Type it, or press Ctrl+; for today. It is a typed date rather than TODAY() on purpose: TODAY() would make Excel recalculate the whole schedule after every edit.
| Status date (in use) | 2026-10-25 | StatusDate | The project start until a status date is entered. Drives Status, the red status-date line on the Gantt and rescheduling of late work.
| First working day on/after status date | 2026-10-26 | StatusWorkday
| Reschedule incomplete work after status date? | Yes | RescheduleAfterStatus | Yes = like MS Project 'move incomplete parts after status date': unstarted tasks can't start before the status date and in-progress tasks finish their remaining duration after it, pushing all successors.
| Working hours per day | 8 | HoursPerDay | Work (hrs) = Duration x Hours/day x Units.
| Default assignment units | 100% | DefaultUnits | Used when a task has a resource but Units is blank. 100% = full time.
| Monday is a working day | Yes | WorkMon | Working-week calendar (Yes/No). Feeds every WORKDAY / NETWORKDAYS formula.
| Tuesday is a working day | Yes | WorkTue
| Wednesday is a working day | Yes | WorkWed
| Thursday is a working day | Yes | WorkThu
| Friday is a working day | Yes | WorkFri
| Saturday is a working day | No | WorkSat
| Sunday is a working day | No | WorkSun
| Weekend mask (calculated) | 0000011 | WorkWeek | 7-character Mon..Sun string used by WORKDAY.INTL (1 = non-working).
| Gantt timeline start | 2026-09-07 | GanttStart | Defaults to the Monday of the project start week. Overwrite with any date to scroll the timeline.
| Gantt days per column | 1 | GanttPeriod | 1 = daily timeline, 7 = weekly timeline.
| Sprint 1 start date | 2026-09-07 | Sprint1Start | Defaults to the project start. Overwrite to align with your sprint calendar.
| Sprint length (calendar days) | 14 | SprintLength | 14 = two-week sprints.
| Number of sprints | 12 | SprintCount | Up to the number of rows in the Sprints table (26; add rows to the table for more). Tasks outside the sprint range are labelled 'Backlog'.
| Sprint name prefix | Sprint | SprintPrefix | Sprint names = prefix & number.
| Last sprint end (calculated) | 2027-02-21 | SprintLastEnd
| Sprint containing the status date (calculated) | Sprint 4 | CurrentSprint | Blank outside the sprint calendar. Agile Report shows its backlog and daily burndown.
| Current sprint start (calculated) | 2026-10-19 | CurrentSprintStart
| Current sprint end (calculated) | 2026-11-01 | CurrentSprintEnd
| Total story points (calculated) | 82 | TotalPoints | Story points on all detail tasks: the release scope for burndown and burn-up.
| Critical when total slack is at most (days) | 0 | CriticalSlackDays | 0 = only tasks with no slack (or negative slack from a missed deadline) are critical, like MS Project.
| Forecast project finish (calculated) | 2027-01-06 | ProjectFinish | The critical path's backward pass starts here.
| Planned project finish (calculated) | 2027-01-06 | PlannedFinish | Baseline finish once a baseline is set.
| Project finish variance (calculated, working days) | 0 | FinishVarianceDays | Forecast finish minus planned finish. Positive = late.
| Look-ahead window (working days) | 10 | LookaheadDays | Schedule Report lists tasks starting or due within this many working days of the status date.
| Look-ahead window ends (calculated) | 2026-11-06 | LookaheadEnd
| RAG: amber when the finish slips by (working days) | 3 | RAGAmberSlipDays | Status Report thresholds. A finish slip of at least this many working days is amber.
| RAG: red when the finish slips by (working days) | 10 | RAGRedSlipDays
| RAG: amber when SPI or CPI is below | 0.95 | RAGAmberIndex | SPI = earned value / planned value; CPI = earned value / actual cost. 1.00 = on plan.
| RAG: red when SPI or CPI is below | 0.85 | RAGRedIndex
| Resource Report first week | 2026-10-05 | ResourceWeekStart | Defaults to the Monday two weeks before the status date. Overwrite with any Monday to scroll the weekly grids.
| Next free task UID (calculated) | 201 | NextFreeUID | Give a newly inserted task row this UID (see Instructions > Inserting tasks).

## Tasks
Customer Portal Implementation - Task Entry
Type in BLUE columns only. Level = outline level (1 = phase, 2 = task, 3 = sub-task). Predecessors refer to the UID column. Planned = Baseline once set, otherwise calculated from Duration + Predecessors. Forecast also uses Actuals, so slips ripple to every successor. Insert rows inside the table: formulas fill in automatically.
Next free UID for a new row: 201
IDENTITY |  |  |  |  | SCHEDULING INPUTS | [9 empty] | PLAN / ACTUAL / FORECAST | [5 empty] | VARIANCE |  | CRITICAL PATH |  |  |  |  | CHECKS |  | PROGRESS |  |  | RESOURCES & SPRINT | [9 empty] | SET BASELINE: copy these 5 columns, then Paste Special > Values onto the 5 Baseline columns | [9 empty] | VARIANCE vs BASELINE |  |  | EARNED VALUE (at status date) |  |  |  | HELPER COLUMNS (hidden - click + above to show)
ID | UID | WBS | Level | Task Name | Mode | Duration | Pred1 UID | Pred1 Type | Pred1 Lag | Pred2 UID | Pred2 Type | Pred2 Lag | Start No Earlier Than | Deadline | Planned Start | Planned Finish | Actual Start | Actual Finish | Forecast Start | Forecast Finish | Start Var | Finish Var | Late Start | Late Finish | Total Slack | Free Slack | Critical | Deadline Check | Link Check | % Complete | Progress | Status | Resource | Units | Work | Cost | Actual Cost | Planned Sprint | Sprint | Story Points | Predecessors | Notes | BL Source Start | BL Source Finish | BL Source Duration | BL Source Work | BL Source Cost | Baseline Start | Baseline Finish | Baseline Duration | Baseline Work | Baseline Cost | Duration Var | Work Var | Cost Var | Budget | PV | EV | AC | _Level | _Row | _ParentRow | _NextLevel | _IsSummary | _Descendants | _IsLeaf | _Pred1Pos | _Pred2Pos | _LeafCalcStart | _LeafCalcFinish | _LeafFcstStart | _LeafFcstFinish | _LeafProgress | _LeafWork | _LeafCost | _Pred1FinishKey | _Pred2FinishKey | _Pred1SlackKey | _Pred2SlackKey | _LastSuccessorRow | _SuccessorFinishLimit | _LeafLateFinish | _LeafLateStart | _LeafTotalSlack | _LeafCritical | _CalcStart | _CalcFinish | _Pred1Problem | _Pred2Problem | _Pred1PlanDriver | _Pred2PlanDriver | _Pred1FcstDriver | _Pred2FcstDriver | _StartWorkday | _FinishWorkday | _WorkPerWorkday | _WorkBeforeStart | _WeightDur | _WeightDone | _Pred1IDText | _Pred2IDText | _Pred1UIDText | _Pred2UIDText | _UIDPredecessors | _MilestoneKey | _PlannedPct | _LeafBudget | _LeafPV | _LeafEV | _LeafAC | _Phase | _PhaseKey | _MilestoneOrder | _LateKey | _StartSoonKey | _DueSoonKey | _CriticalKey | _LeafWorkDone | _DoneDate | _LeafPoints | _CurrentSprintKey
1 | 1 | 1 | 1 | Initiation | Auto | [9 empty] | 2026-09-07 | 2026-09-11 |  |  | 2026-09-07 | 2026-09-14 | 0 | 1 | 2026-09-14 | 2026-09-18 | 4 | [5 empty] | 100% | Complete |  |  | 40 | 3400 | [5 empty] | Phase 1 - summary rows roll up dates, work, cost and progress automatically. | 2026-09-07 | 2026-09-14 | 6 | 40 | 3400 | [8 empty] | 3400 | 3400 | 3400 | 4160 | 1 | 1 | 0 | 2 | TRUE | 3 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE | 2026-09-07 | 2026-09-11 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 1 | [5 empty] | 0 |  | 0
2 | 2 | 1.1 | 2 | Project charter & scope statement | Auto | 3 | [8 empty] | 2026-09-07 | 2026-09-09 | 2026-09-07 | 2026-09-10 | 2026-09-07 | 2026-09-10 | 0 | 1 | 2026-09-14 | 2026-09-16 | 4 | 0 |  |  |  | 100% | 100% | Complete | Priya Sharma |  | 24 | 2280 | 3040 |  | Sprint 1 | 3 |  | Took 1 extra day for sponsor sign-off. | 2026-09-07 | 2026-09-10 | 3 | 24 | 2280 | [8 empty] | 2280 | 2280 | 2280 | 3040 | 2 | 2 | 6 | 2 | FALSE | 0 | 1 | 0 | 0 | 2026-09-07 | 2026-09-09 | 2026-09-07 | 2026-09-10 | 1 | 24 | 2280 |  |  |  |  | 3 | 2026-09-16 | 2026-09-16 | 2026-09-14 | 4 | FALSE | 2026-09-07 | 2026-09-09 |  |  | 0 | 0 | 0 | 0 | 1 | 4 | 6 | 0 | 3 | 3 | [6 empty] | 1 | 2280 | 2280 | 2280 | 3040 | 1 | [6 empty] | 24 | 2026-09-10 | 3
3 | 3 | 1.2 | 2 | Stakeholder kickoff workshop | Auto | 2 | 2 | FS | [6 empty] | 2026-09-10 | 2026-09-11 | 2026-09-11 | 2026-09-14 | 2026-09-11 | 2026-09-14 | 1 | 1 | 2026-09-17 | 2026-09-18 | 4 | 0 |  |  |  | 100% | 100% | Complete | Morgan Patel |  | 16 | 1120 |  |  | Sprint 1 | 2 | 2 |  | 2026-09-11 | 2026-09-14 | 2 | 16 | 1120 | [8 empty] | 1120 | 1120 | 1120 | 1120 | 2 | 3 | 6 | 2 | FALSE | 0 | 1 | 2 | 0 | 2026-09-10 | 2026-09-11 | 2026-09-11 | 2026-09-14 | 1 | 16 | 1120 | 2912184 |  | 100000 |  | 4 | 2026-09-18 | 2026-09-18 | 2026-09-17 | 4 | FALSE | 2026-09-10 | 2026-09-11 |  |  | 2026-09-10 | 0 | 2026-09-11 | 0 | 5 | 6 | 8 | 32 | 2 | 2 | 2 |  | 2 |  | 2 |  | 1 | 1120 | 1120 | 1120 | 1120 | 1 | [6 empty] | 16 | 2026-09-14 | 2
4 | 4 | 1.3 | 2 | Kickoff complete | Auto | 0 | 3 | FS | [6 empty] | 2026-09-11 | 2026-09-11 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 1 | 1 | 2026-09-18 | 2026-09-18 | 4 | 0 |  |  |  | 100% | 100% | Complete |  |  | 0 | 0 |  |  | Sprint 1 |  | 3 | Milestone (Duration 0). | 2026-09-14 | 2026-09-14 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 2 | 4 | 6 | 1 | FALSE | 0 | 1 | 3 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-14 | 2026-09-14 | 1 | 0 | 0 | 2912182 |  | 100000 |  | 6 | 2026-09-18 | 2026-09-18 | 2026-09-18 | 4 | FALSE | 2026-09-11 | 2026-09-11 |  |  | 2026-09-11 | 0 | 2026-09-14 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 3 |  | 3 |  | 3 |  | 1 | 0 | 0 | 0 | 0 | 1 |  | 2026-09-11 |  |  |  |  | 0 | 2026-09-14 | 0
5 | 5 | 2 | 1 | Requirements & Design | Auto | [9 empty] | 2026-09-14 | 2026-10-01 |  |  | 2026-09-15 | 2026-10-06 | 1 | 3 | 2026-09-21 | 2026-10-08 | 2 | [5 empty] | 100% | Complete |  |  | 152 | 12480 | [6 empty] | 2026-09-15 | 2026-10-06 | 16 | 152 | 12480 | [8 empty] | 12480 | 12480 | 12480 | 13040 | 1 | 5 | 0 | 2 | TRUE | 4 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE | 2026-09-14 | 2026-10-01 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 2 | 5 | [5 empty] | 0 |  | 0
6 | 6 | 2.1 | 2 | Requirements gathering | Auto | 8 | 4 | FS | [6 empty] | 2026-09-14 | 2026-09-23 | 2026-09-15 | 2026-09-25 | 2026-09-15 | 2026-09-25 | 1 | 2 | 2026-09-21 | 2026-09-30 | 3 | 0 |  |  |  | 100% | 100% | Complete | Morgan Patel |  | 64 | 4480 | 5040 |  | Sprint 1 | 8 | 4 |  | 2026-09-15 | 2026-09-25 | 8 | 64 | 4480 | [8 empty] | 4480 | 4480 | 4480 | 5040 | 2 | 6 | 10 | 2 | FALSE | 0 | 1 | 4 | 0 | 2026-09-14 | 2026-09-23 | 2026-09-15 | 2026-09-25 | 1 | 64 | 4480 | 2912182 |  | 100000 |  | 8 | 2026-09-30 | 2026-09-30 | 2026-09-21 | 3 | FALSE | 2026-09-14 | 2026-09-23 |  |  | 2026-09-14 | 0 | 2026-09-15 | 0 | 7 | 15 | 7.1111 | 42.6667 | 8 | 8 | 4 |  | 4 |  | 4 |  | 1 | 4480 | 4480 | 4480 | 5040 | 2 | [6 empty] | 64 | 2026-09-25 | 8
7 | 7 | 2.2 | 2 | Solution architecture | Auto | 5 | 6 | SS | 3 | [5 empty] | 2026-09-17 | 2026-09-23 | 2026-09-18 | 2026-09-25 | 2026-09-18 | 2026-09-25 | 1 | 2 | 2026-10-02 | 2026-10-08 | 9 | 7 |  |  |  | 100% | 100% | Complete | Alex Chen |  | 40 | 4400 |  |  | Sprint 1 | 5 | 6SS+3d | Start-to-Start + 3 day lag example. | 2026-09-18 | 2026-09-25 | 5 | 40 | 4400 | [8 empty] | 4400 | 4400 | 4400 | 4400 | 2 | 7 | 10 | 2 | FALSE | 0 | 1 | 6 | 0 | 2026-09-17 | 2026-09-23 | 2026-09-18 | 2026-09-25 | 1 | 40 | 4400 | 2912162 |  | 100000 |  | 9 | 2026-10-08 | 2026-10-08 | 2026-10-02 | 9 | FALSE | 2026-09-17 | 2026-09-23 |  |  | 2026-09-17 | 0 | 2026-09-18 | 0 | 10 | 15 | 6.6667 | 60 | 5 | 5 | 6SS+3d |  | 6SS+3d |  | 6SS+3d |  | 1 | 4400 | 4400 | 4400 | 4400 | 2 | [6 empty] | 40 | 2026-09-25 | 5
8 | 8 | 2.3 | 2 | UX wireframes & prototype | Auto | 6 | 6 | FS | [6 empty] | 2026-09-24 | 2026-10-01 | 2026-09-28 | 2026-10-06 | 2026-09-28 | 2026-10-06 | 2 | 3 | 2026-10-01 | 2026-10-08 | 2 | 0 |  |  |  | 100% | 100% | Complete | Casey Kim |  | 48 | 3600 |  |  | Sprint 2 | 5 | 6 |  | 2026-09-28 | 2026-10-06 | 6 | 48 | 3600 | [8 empty] | 3600 | 3600 | 3600 | 3600 | 2 | 8 | 10 | 2 | FALSE | 0 | 1 | 6 | 0 | 2026-09-24 | 2026-10-01 | 2026-09-28 | 2026-10-06 | 1 | 48 | 3600 | 2912170 |  | 100000 |  | 9 | 2026-10-08 | 2026-10-08 | 2026-10-01 | 2 | FALSE | 2026-09-24 | 2026-10-01 |  |  | 2026-09-24 | 0 | 2026-09-28 | 0 | 16 | 22 | 6.8571 | 102.8571 | 6 | 6 | 6 |  | 6 |  | 6 |  | 1 | 3600 | 3600 | 3600 | 3600 | 2 | [6 empty] | 48 | 2026-10-06 | 5
9 | 9 | 2.4 | 2 | Design sign-off | Auto | 0 | 7 | FS |  | 8 | FS |  |  |  | 2026-10-01 | 2026-10-01 | 2026-10-06 | 2026-10-06 | 2026-10-06 | 2026-10-06 | 3 | 3 | 2026-10-08 | 2026-10-08 | 2 | 0 |  |  |  | 100% | 100% | Complete |  |  | 0 | 0 |  |  | Sprint 3 |  | 7,8 | Two predecessors - waits for the later one. | 2026-10-06 | 2026-10-06 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 2 | 9 | 10 | 1 | FALSE | 0 | 1 | 7 | 8 | 2026-10-01 | 2026-10-01 | 2026-10-06 | 2026-10-06 | 1 | 0 | 0 | 2912162 | 2912162 | 99993 | 100000 | 16 | 2026-10-08 | 2026-10-08 | 2026-10-08 | 2 | FALSE | 2026-10-01 | 2026-10-01 |  |  | 2026-09-23 | 2026-10-01 | 2026-09-25 | 2026-10-06 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 7 | 8 | 7 | 8 | 7,8 |  | 1 | 0 | 0 | 0 | 0 | 2 |  | 2026-10-01 |  |  |  |  | 0 | 2026-10-06 | 0
10 | 10 | 3 | 1 | Build | Auto | [9 empty] | 2026-10-02 | 2026-10-30 |  |  | 2026-10-07 | 2026-11-09 | 3 | 6 | 2026-10-09 | 2026-11-06 | -1 |  | Yes |  |  |  | 45.13% | Behind |  |  | 324 | 26700 | [6 empty] | 2026-10-07 | 2026-11-09 | 24 | 324 | 26700 | [8 empty] | 26700 | 20480 | 12560 | 13240 | 1 | 10 | 0 | 2 | TRUE | 9 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE | 2026-10-02 | 2026-10-30 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 3 | 10 | [5 empty] | 0 |  | 0
11 | 11 | 3.1 | 2 | Backend | Auto | [9 empty] | 2026-10-02 | 2026-10-30 |  |  | 2026-10-07 | 2026-11-09 | 3 | 6 | 2026-10-09 | 2026-11-06 | -1 |  | Yes |  |  |  | 47.62% | Behind |  |  | 168 | 14280 | [5 empty] | Level-2 summary with sub-tasks. | 2026-10-07 | 2026-11-09 | 24 | 168 | 14280 | [8 empty] | 14280 | 10880 | 6800 | 7480 | 2 | 11 | 15 | 3 | TRUE | 3 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE | 2026-10-02 | 2026-10-30 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 3 | [6 empty] | 0 |  | 0
12 | 12 | 3.1.1 | 3 | Data model & database setup | Auto | 5 | 9 | FS | [6 empty] | 2026-10-02 | 2026-10-08 | 2026-10-07 | 2026-10-14 | 2026-10-07 | 2026-10-14 | 3 | 4 | 2026-10-09 | 2026-10-15 | 1 | 0 |  |  |  | 100% | 100% | Complete | Jordan Lee |  | 40 | 3400 |  |  | Sprint 3 | 5 | 9 |  | 2026-10-07 | 2026-10-14 | 5 | 40 | 3400 | [8 empty] | 3400 | 3400 | 3400 | 3400 | 3 | 12 | 16 | 3 | FALSE | 0 | 1 | 9 | 0 | 2026-10-02 | 2026-10-08 | 2026-10-07 | 2026-10-14 | 1 | 40 | 3400 | 2912162 |  | 100000 |  | 13 | 2026-10-15 | 2026-10-15 | 2026-10-09 | 1 | FALSE | 2026-10-02 | 2026-10-08 |  |  | 2026-10-02 | 0 | 2026-10-07 | 0 | 23 | 28 | 6.6667 | 146.6667 | 5 | 5 | 9 |  | 9 |  | 9 |  | 1 | 3400 | 3400 | 3400 | 3400 | 3 | [6 empty] | 40 | 2026-10-14 | 5
13 | 13 | 3.1.2 | 3 | Core API endpoints | Auto | 10 | 12 | FS | [6 empty] | 2026-10-09 | 2026-10-22 | 2026-10-15 |  | 2026-10-15 | 2026-10-30 | 4 | 6 | 2026-10-16 | 2026-10-29 | -1 | -1 | Yes |  |  | 50% | 50% | Behind | Jordan Lee |  | 80 | 6800 | 4080 |  | Sprint 3 | 8 | 12 | In progress - enter % Complete; forecast finish adjusts. | 2026-10-15 | 2026-10-30 | 10 | 80 | 6800 | [8 empty] | 6800 | 6800 | 3400 | 4080 | 3 | 13 | 16 | 3 | FALSE | 0 | 1 | 12 | 0 | 2026-10-09 | 2026-10-22 | 2026-10-15 | 2026-10-30 | 0.5 | 80 | 6800 | 2912155 |  | 100000 |  | 17 | 2026-10-29 | 2026-10-29 | 2026-10-16 | -1 | TRUE | 2026-10-09 | 2026-10-22 |  |  | 2026-10-09 | 0 | 2026-10-15 | 0 | 29 | 40 | 6.6667 | 186.6667 | 10 | 5 | 12 |  | 12 |  | 12 |  | 1 | 6800 | 6800 | 3400 | 4080 | 3 |  |  | 7 |  | 2026-10-30 | 2026-10-15 | 40 |  | 8
14 | 14 | 3.1.3 | 3 | Payment gateway integration | Auto | 6 | 13 | FS | [6 empty] | 2026-10-23 | 2026-10-30 |  |  | 2026-11-02 | 2026-11-09 | 6 | 6 | 2026-10-30 | 2026-11-06 | -1 | -1 | Yes |  |  |  | 0% | Late Start | Jordan Lee |  | 48 | 4080 |  |  | Sprint 5 | 5 | 13 |  | 2026-11-02 | 2026-11-09 | 6 | 48 | 4080 | [8 empty] | 4080 | 680 | 0 | 0 | 3 | 14 | 16 | 2 | FALSE | 0 | 1 | 13 | 0 | 2026-10-23 | 2026-10-30 | 2026-11-02 | 2026-11-09 | 0 | 48 | 4080 | 2912141 |  | 100000 |  | 19 | 2026-11-06 | 2026-11-06 | 2026-10-30 | -1 | TRUE | 2026-10-23 | 2026-10-30 |  |  | 2026-10-23 | 0 | 2026-11-02 | 0 | 41 | 46 | 8 | 320 | 6 | 0 | 13 |  | 13 |  | 13 |  | 0.16667 | 4080 | 680 | 0 | 0 | 3 |  |  | 7 | 2026-11-02 |  | 2026-11-02 | 0 |  | 5
15 | 15 | 3.2 | 2 | Frontend | Auto | [9 empty] | 2026-10-02 | 2026-10-29 |  |  | 2026-10-07 | 2026-11-06 | 3 | 6 | 2026-10-13 | 2026-11-06 | 0 |  | Yes |  |  |  | 42.86% | Behind |  |  | 156 | 12420 | [6 empty] | 2026-10-07 | 2026-11-06 | 23 | 156 | 12420 | [8 empty] | 12420 | 9600 | 5760 | 5760 | 2 | 15 | 15 | 3 | TRUE | 3 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE | 2026-10-02 | 2026-10-29 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 3 | [6 empty] | 0 |  | 0
16 | 16 | 3.2.1 | 3 | UI component library | Auto | 6 | 9 | FS | [6 empty] | 2026-10-02 | 2026-10-09 | 2026-10-07 | 2026-10-16 | 2026-10-07 | 2026-10-16 | 3 | 5 | 2026-10-13 | 2026-10-20 | 2 | 0 |  |  |  | 100% | 100% | Complete | Sam Rivera |  | 48 | 3840 |  |  | Sprint 3 | 5 | 9 |  | 2026-10-07 | 2026-10-16 | 6 | 48 | 3840 | [8 empty] | 3840 | 3840 | 3840 | 3840 | 3 | 16 | 20 | 3 | FALSE | 0 | 1 | 9 | 0 | 2026-10-02 | 2026-10-09 | 2026-10-07 | 2026-10-16 | 1 | 48 | 3840 | 2912158 |  | 100000 |  | 17 | 2026-10-20 | 2026-10-20 | 2026-10-13 | 2 | FALSE | 2026-10-02 | 2026-10-09 |  |  | 2026-10-02 | 0 | 2026-10-07 | 0 | 23 | 30 | 6 | 132 | 6 | 6 | 9 |  | 9 |  | 9 |  | 1 | 3840 | 3840 | 3840 | 3840 | 3 | [6 empty] | 48 | 2026-10-16 | 5
17 | 17 | 3.2.2 | 3 | Feature screens | Auto | 12 | 16 | FS |  | 13 | SS | 2 |  |  | 2026-10-13 | 2026-10-28 | 2026-10-19 |  | 2026-10-19 | 2026-11-05 | 4 | 6 | 2026-10-21 | 2026-11-05 | 0 | 0 | Yes |  |  | 25% | 25% | Behind | Sam Rivera |  | 96 | 7680 |  |  | Sprint 4 | 8 | 16,13SS+2d |  | 2026-10-19 | 2026-11-05 | 12 | 96 | 7680 | [8 empty] | 7680 | 5760 | 1920 | 1920 | 3 | 17 | 20 | 3 | FALSE | 0 | 1 | 16 | 13 | 2026-10-13 | 2026-10-28 | 2026-10-19 | 2026-11-05 | 0.25 | 96 | 7680 | 2912150 | 2912140 | 100000 | 100000 | 18 | 2026-11-05 | 2026-11-05 | 2026-10-21 | 0 | TRUE | 2026-10-13 | 2026-10-28 |  |  | 2026-10-12 | 2026-10-13 | 2026-10-19 | 2026-10-19 | 31 | 44 | 6.8571 | 205.7143 | 12 | 3 | 16 | 13SS+2d | 16 | 13SS+2d | 16,13SS+2d |  | 0.75 | 7680 | 5760 | 1920 | 1920 | 3 |  |  | 7 |  | 2026-11-05 | 2026-10-19 | 24 |  | 8 | 17
18 | 18 | 3.2.3 | 3 | Accessibility review | Auto | 3 | 17 | FF | 1 | [5 empty] | 2026-10-27 | 2026-10-29 |  |  | 2026-11-04 | 2026-11-06 | 6 | 6 | 2026-11-04 | 2026-11-06 | 0 | 0 | Yes |  |  |  | 0% | Not Started | Casey Kim | 50% | 12 | 900 |  |  | Sprint 5 | 3 | 17FF+1d | Finish-to-Finish + 1 day; 50% units. | 2026-11-04 | 2026-11-06 | 3 | 12 | 900 | [8 empty] | 900 | 0 | 0 | 0 | 3 | 18 | 20 | 2 | FALSE | 0 | 1 | 17 | 0 | 2026-10-27 | 2026-10-29 | 2026-11-04 | 2026-11-06 | 0 | 12 | 900 | 2912134 |  | 100000 |  | 19 | 2026-11-06 | 2026-11-06 | 2026-11-04 | 0 | TRUE | 2026-10-27 | 2026-10-29 |  |  | 2026-10-27 | 0 | 2026-11-04 | 0 | 43 | 45 | 4 | 168 | 3 | 0 | 17FF+1d |  | 17FF+1d |  | 17FF+1d |  | 0 | 900 | 0 | 0 | 0 | 3 |  |  | 7 | 2026-11-04 | 2026-11-06 | 2026-11-04 | 0 |  | 3
19 | 19 | 3.3 | 2 | Build complete | Auto | 0 | 14 | FS |  | 18 | FS |  |  | 2026-11-06 | 2026-10-30 | 2026-10-30 |  |  | 2026-11-09 | 2026-11-09 | 6 | 6 | 2026-11-06 | 2026-11-06 | -1 | -1 | Yes | Late by 1d |  |  | 0% | Not Started |  |  | 0 | 0 |  |  | Sprint 5 |  | 14,18 | Milestone with a deadline of 06-Nov (see Deadline Check). | 2026-11-09 | 2026-11-09 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 2 | 19 | 15 | 1 | FALSE | 0 | 1 | 14 | 18 | 2026-10-30 | 2026-10-30 | 2026-11-09 | 2026-11-09 | 0 | 0 | 0 | 2912133 | 2912133 | 100000 | 99999 | 21 | 2026-11-24 | 2026-11-06 | 2026-11-06 | -1 | TRUE | 2026-10-30 | 2026-10-30 |  |  | 2026-10-30 | 2026-10-29 | 2026-11-09 | 2026-11-06 | 0 | 0 | 0 | 0 | 0.1 | 0 | 14 | 18 | 14 | 18 | 14,18 | 2026-11-09 | 0 | 0 | 0 | 0 | 0 | 3 |  | 2026-10-30 | 7 |  |  | 2026-11-09 | 0 |  | 0
20 | 20 | 4 | 1 | Test & Release | Auto | [9 empty] | 2026-11-02 | 2027-01-04 |  |  | 2026-11-10 | 2027-01-04 | 6 | 0 | 2026-11-25 | 2027-01-04 | 0 |  | Yes |  |  |  | 0% | Not Started |  |  | 180 | 13180 | [6 empty] | 2026-11-10 | 2027-01-04 | 36 | 180 | 13180 | [8 empty] | 13180 | 0 | 0 | 0 | 1 | 20 | 0 | 2 | TRUE | 6 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE | 2026-11-02 | 2027-01-04 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 4 | 20 | [5 empty] | 0 |  | 0
21 | 21 | 4.1 | 2 | System integration testing | Auto | 8 | 19 | FS | [6 empty] | 2026-11-02 | 2026-11-11 |  |  | 2026-11-10 | 2026-11-19 | 6 | 6 | 2026-11-25 | 2026-12-04 | 11 | 0 |  |  |  |  | 0% | Not Started | Taylor Morgan |  | 64 | 4160 |  |  | Sprint 5 | 8 | 19 |  | 2026-11-10 | 2026-11-19 | 8 | 64 | 4160 | [8 empty] | 4160 | 0 | 0 | 0 | 2 | 21 | 25 | 2 | FALSE | 0 | 1 | 19 | 0 | 2026-11-02 | 2026-11-11 | 2026-11-10 | 2026-11-19 | 0 | 64 | 4160 | 2912115 |  | 100000 |  | 23 | 2026-12-04 | 2026-12-04 | 2026-11-25 | 11 | FALSE | 2026-11-02 | 2026-11-11 |  |  | 2026-11-02 | 0 | 2026-11-10 | 0 | 47 | 54 | 8 | 368 | 8 | 0 | 19 |  | 19 |  | 19 |  | 0 | 4160 | 0 | 0 | 0 | 4 |  |  | 7 |  |  |  | 0 |  | 8
22 | 22 | 4.2 | 2 | User acceptance testing | Auto | 6 | 21 | FS |  |  |  |  | 2026-12-07 |  | 2026-12-07 | 2026-12-14 |  |  | 2026-12-07 | 2026-12-14 | 0 | 0 | 2026-12-07 | 2026-12-14 | 0 | 0 | Yes |  |  |  | 0% | Not Started | Morgan Patel |  | 48 | 3360 |  |  | Sprint 7 | 5 | 21 | Start No Earlier Than 07-Dec (client availability). | 2026-12-07 | 2026-12-14 | 6 | 48 | 3360 | [8 empty] | 3360 | 0 | 0 | 0 | 2 | 22 | 25 | 2 | FALSE | 0 | 1 | 21 | 0 | 2026-12-07 | 2026-12-14 | 2026-12-07 | 2026-12-14 | 0 | 48 | 3360 | 2912105 |  | 99989 |  | 24 | 2026-12-14 | 2026-12-14 | 2026-12-07 | 0 | TRUE | 2026-12-07 | 2026-12-14 |  |  | 2026-11-12 | 0 | 2026-11-20 | 0 | 66 | 71 | 8 | 520 | 6 | 0 | 21 |  | 21 |  | 21 |  | 0 | 3360 | 0 | 0 | 0 | 4 | [5 empty] | 2026-12-07 | 0 |  | 5
23 | 23 | 4.3 | 2 | Training & user guides | Auto | 5 | 21 | SS | 2 | [5 empty] | 2026-11-04 | 2026-11-10 |  |  | 2026-11-12 | 2026-11-18 | 6 | 6 | 2026-12-08 | 2026-12-14 | 18 | 18 |  |  |  |  | 0% | Not Started | Casey Kim | 50% | 20 | 1500 |  |  | Sprint 5 | 3 | 21SS+2d |  | 2026-11-12 | 2026-11-18 | 5 | 20 | 1500 | [8 empty] | 1500 | 0 | 0 | 0 | 2 | 23 | 25 | 2 | FALSE | 0 | 1 | 21 | 0 | 2026-11-04 | 2026-11-10 | 2026-11-12 | 2026-11-18 | 0 | 20 | 1500 | 2912094 |  | 100000 |  | 24 | 2026-12-14 | 2026-12-14 | 2026-12-08 | 18 | FALSE | 2026-11-04 | 2026-11-10 |  |  | 2026-11-04 | 0 | 2026-11-12 | 0 | 49 | 53 | 4 | 192 | 5 | 0 | 21SS+2d |  | 21SS+2d |  | 21SS+2d |  | 0 | 1500 | 0 | 0 | 0 | 4 |  |  | 7 |  |  |  | 0 |  | 3
24 | 24 | 4.4 | 2 | Go-live readiness review | Auto | 1 | 22 | FS |  | 23 | FS |  |  |  | 2026-12-15 | 2026-12-15 |  |  | 2026-12-15 | 2026-12-15 | 0 | 0 | 2026-12-15 | 2026-12-15 | 0 | 0 | Yes |  |  |  | 0% | Not Started | Priya Sharma |  | 8 | 760 |  |  | Sprint 8 | 1 | 22,23 |  | 2026-12-15 | 2026-12-15 | 1 | 8 | 760 | [8 empty] | 760 | 0 | 0 | 0 | 2 | 24 | 25 | 2 | FALSE | 0 | 1 | 22 | 23 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 0 | 8 | 760 | 2912095 | 2912095 | 100000 | 99982 | 25 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 0 | TRUE | 2026-12-15 | 2026-12-15 |  |  | 2026-12-15 | 2026-11-11 | 2026-12-15 | 2026-11-19 | 72 | 72 | 8 | 568 | 1 | 0 | 22 | 23 | 22 | 23 | 22,23 |  | 0 | 760 | 0 | 0 | 0 | 4 | [5 empty] | 2026-12-15 | 0 |  | 1
25 | 25 | 4.5 | 2 | Go-live | Auto | 0 | 24 | FS | [5 empty] | 2026-12-18 | 2026-12-15 | 2026-12-15 |  |  | 2026-12-15 | 2026-12-15 | 0 | 0 | 2026-12-15 | 2026-12-15 | 0 | 0 | Yes | OK |  |  | 0% | Not Started |  |  | 0 | 0 |  |  | Sprint 8 |  | 24 | Milestone with a deadline of 18-Dec. | 2026-12-15 | 2026-12-15 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 2 | 25 | 25 | 2 | FALSE | 0 | 1 | 24 | 0 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 0 | 0 | 0 | 2912094 |  | 100000 |  | 26 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 0 | TRUE | 2026-12-15 | 2026-12-15 |  |  | 2026-12-15 | 0 | 2026-12-15 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 24 |  | 24 |  | 24 | 2026-12-15 | 0 | 0 | 0 | 0 | 0 | 4 |  | 2026-12-15 |  |  |  | 2026-12-15 | 0 |  | 0
26 | 26 | 4.6 | 2 | Hypercare support | Auto | 10 | 25 | FS | [6 empty] | 2026-12-16 | 2027-01-04 |  |  | 2026-12-16 | 2027-01-04 | 0 | 0 | 2026-12-16 | 2027-01-04 | 0 | 0 | Yes |  |  |  | 0% | Not Started | Jordan Lee | 50% | 40 | 3400 |  |  | Sprint 8 | 5 | 25 |  | 2026-12-16 | 2027-01-04 | 10 | 40 | 3400 | [8 empty] | 3400 | 0 | 0 | 0 | 2 | 26 | 25 | 1 | FALSE | 0 | 1 | 25 | 0 | 2026-12-16 | 2027-01-04 | 2026-12-16 | 2027-01-04 | 0 | 40 | 3400 | 2912094 |  | 100000 |  | 29 | 2027-01-04 | 2027-01-04 | 2026-12-16 | 0 | TRUE | 2026-12-16 | 2027-01-04 |  |  | 2026-12-16 | 0 | 2026-12-16 | 0 | 73 | 82 | 4 | 288 | 10 | 0 | 25 |  | 25 |  | 25 |  | 0 | 3400 | 0 | 0 | 0 | 4 | [5 empty] | 2026-12-16 | 0 |  | 5
27 | 27 | 5 | 1 | Project Close | Auto | [9 empty] | 2026-11-16 | 2027-01-06 |  |  | 2026-11-16 | 2027-01-06 | 0 | 0 | 2027-01-05 | 2027-01-06 | 0 |  | Yes |  |  |  | 0% | Not Started |  |  | 24 | 2280 | [6 empty] | 2026-11-16 | 2027-01-06 | 34 | 24 | 2280 | [8 empty] | 2280 | 0 | 0 | 0 | 1 | 27 | 0 | 2 | TRUE | 3 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE | 2026-11-16 | 2027-01-06 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 5 | 27 | [5 empty] | 0 |  | 0
28 | 28 | 5.1 | 2 | Steering committee update | Manual | 1 | [6 empty] | 2026-11-16 |  | 2026-11-16 | 2026-11-16 |  |  | 2026-11-16 | 2026-11-16 | 0 | 0 | 2027-01-06 | 2027-01-06 | 33 | 33 |  |  |  |  | 0% | Not Started | Priya Sharma |  | 8 | 760 |  |  | Sprint 6 | 1 |  | Manual mode example: fixed on the date in the Start No Earlier Than column. | 2026-11-16 | 2026-11-16 | 1 | 8 | 760 | [8 empty] | 760 | 0 | 0 | 0 | 2 | 28 | 32 | 2 | FALSE | 0 | 1 | 0 | 0 | 2026-11-16 | 2026-11-16 | 2026-11-16 | 2026-11-16 | 0 | 8 | 760 |  |  |  |  | 0 | 2958465 | 2027-01-06 | 2027-01-06 | 33 | FALSE | 2026-11-16 | 2026-11-16 |  |  | 0 | 0 | 0 | 0 | 51 | 51 | 8 | 400 | 1 | 0 | [6 empty] | 0 | 760 | 0 | 0 | 0 | 5 | [6 empty] | 0 |  | 1
29 | 29 | 5.2 | 2 | Lessons learned | Auto | 2 | 26 | FS | [6 empty] | 2027-01-05 | 2027-01-06 |  |  | 2027-01-05 | 2027-01-06 | 0 | 0 | 2027-01-05 | 2027-01-06 | 0 | 0 | Yes |  |  |  | 0% | Not Started | Priya Sharma |  | 16 | 1520 |  |  | Sprint 9 | 2 | 26 |  | 2027-01-05 | 2027-01-06 | 2 | 16 | 1520 | [8 empty] | 1520 | 0 | 0 | 0 | 2 | 29 | 32 | 2 | FALSE | 0 | 1 | 26 | 0 | 2027-01-05 | 2027-01-06 | 2027-01-05 | 2027-01-06 | 0 | 16 | 1520 | 2912074 |  | 100000 |  | 30 | 2027-01-06 | 2027-01-06 | 2027-01-05 | 0 | TRUE | 2027-01-05 | 2027-01-06 |  |  | 2027-01-05 | 0 | 2027-01-05 | 0 | 83 | 84 | 8 | 656 | 2 | 0 | 26 |  | 26 |  | 26 |  | 0 | 1520 | 0 | 0 | 0 | 5 | [5 empty] | 2027-01-05 | 0 |  | 2
30 | 30 | 5.3 | 2 | Project closed | Auto | 0 | 29 | FS | [6 empty] | 2027-01-06 | 2027-01-06 |  |  | 2027-01-06 | 2027-01-06 | 0 | 0 | 2027-01-06 | 2027-01-06 | 0 | 0 | Yes |  |  |  | 0% | Not Started |  |  | 0 | 0 |  |  | Sprint 9 |  | 29 | Milestone | 2027-01-06 | 2027-01-06 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 2 | 30 | 32 | 0 | FALSE | 0 | 1 | 29 | 0 | 2027-01-06 | 2027-01-06 | 2027-01-06 | 2027-01-06 | 0 | 0 | 0 | 2912072 |  | 100000 |  | 0 | 2958465 | 2027-01-06 | 2027-01-06 | 0 | TRUE | 2027-01-06 | 2027-01-06 |  |  | 2027-01-06 | 0 | 2027-01-06 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 29 |  | 29 |  | 29 | 2027-01-06 | 0 | 0 | 0 | 0 | 0 | 5 |  | 2027-01-06 |  |  |  | 2027-01-06 | 0 |  | 0
| 31 | [59 empty] | 31 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 32 | [59 empty] | 32 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 33 | [59 empty] | 33 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 34 | [59 empty] | 34 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 35 | [59 empty] | 35 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 36 | [59 empty] | 36 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 37 | [59 empty] | 37 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 38 | [59 empty] | 38 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 39 | [59 empty] | 39 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 40 | [59 empty] | 40 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 41 | [59 empty] | 41 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 42 | [59 empty] | 42 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 43 | [59 empty] | 43 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 44 | [59 empty] | 44 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 45 | [59 empty] | 45 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 46 | [59 empty] | 46 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 47 | [59 empty] | 47 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 48 | [59 empty] | 48 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 49 | [59 empty] | 49 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 50 | [59 empty] | 50 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 51 | [59 empty] | 51 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 52 | [59 empty] | 52 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 53 | [59 empty] | 53 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 54 | [59 empty] | 54 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 55 | [59 empty] | 55 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 56 | [59 empty] | 56 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 57 | [59 empty] | 57 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 58 | [59 empty] | 58 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 59 | [59 empty] | 59 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 60 | [59 empty] | 60 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 61 | [59 empty] | 61 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 62 | [59 empty] | 62 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 63 | [59 empty] | 63 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 64 | [59 empty] | 64 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 65 | [59 empty] | 65 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 66 | [59 empty] | 66 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 67 | [59 empty] | 67 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 68 | [59 empty] | 68 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 69 | [59 empty] | 69 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 70 | [59 empty] | 70 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 71 | [59 empty] | 71 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 72 | [59 empty] | 72 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 73 | [59 empty] | 73 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 74 | [59 empty] | 74 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 75 | [59 empty] | 75 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 76 | [59 empty] | 76 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 77 | [59 empty] | 77 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 78 | [59 empty] | 78 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 79 | [59 empty] | 79 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 80 | [59 empty] | 80 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 81 | [59 empty] | 81 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 82 | [59 empty] | 82 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 83 | [59 empty] | 83 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 84 | [59 empty] | 84 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 85 | [59 empty] | 85 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 86 | [59 empty] | 86 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 87 | [59 empty] | 87 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 88 | [59 empty] | 88 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 89 | [59 empty] | 89 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 90 | [59 empty] | 90 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 91 | [59 empty] | 91 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 92 | [59 empty] | 92 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 93 | [59 empty] | 93 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 94 | [59 empty] | 94 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 95 | [59 empty] | 95 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 96 | [59 empty] | 96 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 97 | [59 empty] | 97 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 98 | [59 empty] | 98 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 99 | [59 empty] | 99 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 100 | [59 empty] | 100 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 101 | [59 empty] | 101 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 102 | [59 empty] | 102 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 103 | [59 empty] | 103 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 104 | [59 empty] | 104 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 105 | [59 empty] | 105 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 106 | [59 empty] | 106 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 107 | [59 empty] | 107 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 108 | [59 empty] | 108 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 109 | [59 empty] | 109 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 110 | [59 empty] | 110 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 111 | [59 empty] | 111 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 112 | [59 empty] | 112 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 113 | [59 empty] | 113 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 114 | [59 empty] | 114 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 115 | [59 empty] | 115 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 116 | [59 empty] | 116 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 117 | [59 empty] | 117 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 118 | [59 empty] | 118 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 119 | [59 empty] | 119 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 120 | [59 empty] | 120 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 121 | [59 empty] | 121 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 122 | [59 empty] | 122 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 123 | [59 empty] | 123 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 124 | [59 empty] | 124 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 125 | [59 empty] | 125 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 126 | [59 empty] | 126 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 127 | [59 empty] | 127 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 128 | [59 empty] | 128 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 129 | [59 empty] | 129 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 130 | [59 empty] | 130 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 131 | [59 empty] | 131 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 132 | [59 empty] | 132 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 133 | [59 empty] | 133 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 134 | [59 empty] | 134 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 135 | [59 empty] | 135 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 136 | [59 empty] | 136 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 137 | [59 empty] | 137 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 138 | [59 empty] | 138 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 139 | [59 empty] | 139 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 140 | [59 empty] | 140 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 141 | [59 empty] | 141 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 142 | [59 empty] | 142 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 143 | [59 empty] | 143 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 144 | [59 empty] | 144 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 145 | [59 empty] | 145 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 146 | [59 empty] | 146 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 147 | [59 empty] | 147 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 148 | [59 empty] | 148 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 149 | [59 empty] | 149 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 150 | [59 empty] | 150 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 151 | [59 empty] | 151 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 152 | [59 empty] | 152 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 153 | [59 empty] | 153 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 154 | [59 empty] | 154 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 155 | [59 empty] | 155 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 156 | [59 empty] | 156 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 157 | [59 empty] | 157 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 158 | [59 empty] | 158 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 159 | [59 empty] | 159 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 160 | [59 empty] | 160 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 161 | [59 empty] | 161 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 162 | [59 empty] | 162 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 163 | [59 empty] | 163 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 164 | [59 empty] | 164 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 165 | [59 empty] | 165 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 166 | [59 empty] | 166 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 167 | [59 empty] | 167 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 168 | [59 empty] | 168 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 169 | [59 empty] | 169 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 170 | [59 empty] | 170 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 171 | [59 empty] | 171 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 172 | [59 empty] | 172 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 173 | [59 empty] | 173 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 174 | [59 empty] | 174 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 175 | [59 empty] | 175 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 176 | [59 empty] | 176 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 177 | [59 empty] | 177 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 178 | [59 empty] | 178 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 179 | [59 empty] | 179 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 180 | [59 empty] | 180 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 181 | [59 empty] | 181 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 182 | [59 empty] | 182 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 183 | [59 empty] | 183 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 184 | [59 empty] | 184 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 185 | [59 empty] | 185 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 186 | [59 empty] | 186 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 187 | [59 empty] | 187 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 188 | [59 empty] | 188 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 189 | [59 empty] | 189 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 190 | [59 empty] | 190 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 191 | [59 empty] | 191 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 192 | [59 empty] | 192 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 193 | [59 empty] | 193 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 194 | [59 empty] | 194 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 195 | [59 empty] | 195 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 196 | [59 empty] | 196 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 197 | [59 empty] | 197 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 198 | [59 empty] | 198 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 199 | [59 empty] | 199 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 200 | [59 empty] | 200 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | FALSE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
Formulas:
PLAN / ACTUAL / FORECAST = IF(Tasks[[#This Row],[Task Name]]="","",IF(N(Tasks[[#This Row],[Baseline Start]])>0,Tasks[[#This Row],[Baseline Start]],Tasks[[#This Row],[_CalcStart]]))
Note on A5: Position in the list; renumbers when rows move (like MS Project).
Note on B5: Permanent number that predecessors refer to. Each task needs a different one.
Note on C5: Outline number, generated from Level.
Note on D5: Outline level: 1 = phase, 2 = task, 3 = sub-task ... (at most 1 more than the row above).
Note on F5: Auto = scheduled from predecessors. Manual = pinned to Start No Earlier Than.
Note on G5: Working days. 0 = milestone.
Note on H5: UID of the predecessor.
Note on I5: FS, SS, FF or SF (blank = FS).
Note on J5: Lag in working days (negative = lead).
Note on K5: UID of a second predecessor.
Note on L5: FS, SS, FF or SF (blank = FS).
Note on M5: Lag in working days (negative = lead).
Note on N5: Auto tasks start no earlier than this. Manual tasks start exactly on it.
Note on O5: Optional deadline; Deadline Check flags a forecast finish after it.
Note on P5: Baseline Start if a baseline is set, otherwise calculated from durations and links.
Note on Q5: Baseline Finish if a baseline is set, otherwise calculated.
Note on T5: Current schedule: actuals where entered, otherwise recalculated from predecessors.
Note on U5: Current schedule finish.
Note on V5: Forecast Start minus Planned Start, in working days.
Note on W5: Forecast Finish minus Planned Finish, in working days.
Note on X5: Latest start that doesn't delay the project finish or a deadline (critical path backward pass).
Note on Y5: Latest finish that doesn't delay the project finish or a deadline.
Note on Z5: Total slack: working days this task can slip before it delays the project or a deadline.
Note on AA5: Free slack: working days it can slip before it delays any successor.
Note on AB5: Yes when Total Slack <= CriticalSlackDays (Settings) and the task isn't complete.
Note on AD5: Explains predecessor links that are ignored.
Note on AE5: Enter 0-100%. An Actual Finish counts as 100%.
Note on AF5: % Complete, rolled up to summaries (duration-weighted).
Note on AI5: Share of the resource's time (blank = DefaultUnits).
Note on AJ5: Hours = Duration x HoursPerDay x Units.
Note on AL5: Cost to date of a detail task. Blank = Cost x Progress (as MS Project calculates it). Summaries roll up in the AC column.
Note on AM5: Optional: the sprint this task is planned in (dropdown). Blank = the sprint containing its forecast start.
Note on AN5: Planned Sprint if entered, otherwise the sprint containing the forecast start.
Note on AO5: Story points (optional estimate for agile reporting). Detail tasks only.
Note on AP5: Predecessors in MS Project notation, by ID.
Note on AR5: Copy the 5 BL Source columns, then Paste Special > Values onto the 5 Baseline columns.
Note on AW5: Frozen plan. Filled by pasting values from the BL Source columns.
Note on BB5: Duration minus Baseline Duration (working days).
Note on BC5: Work minus Baseline Work (hours).
Note on BD5: Cost minus Baseline Cost.
Note on BE5: Budget at completion: Baseline Cost once a baseline is set, otherwise Cost.
Note on BF5: Planned value: the budget of the work planned before the status date.
Note on BG5: Earned value: Budget x Progress.
Note on BH5: Actual cost to date: Actual Cost, or Cost x Progress when it is blank.

## Gantt
Customer Portal Implementation - Gantt Chart | [21 empty] | Planned (outline) | [11 empty] | Done (% complete) | [11 empty] | Remaining - on track | [11 empty] | Remaining - late vs plan | [11 empty] | Remaining - critical
Status date: Sun 25-Oct-2026 ¦ Forecast finish: 06-Jan-2027 ¦ Planned finish: 06-Jan-2027 | [21 empty] | Summary (forecast) | [11 empty] | Milestone (forecast) | [11 empty] | Deadline | [11 empty] | Status date | [11 empty] | Non-working day
Timeline: conditional formatting only (no formulas), so it costs no recalculation. | [20 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W
[21 empty] | Sep 26 | [23 empty] | Oct 26 | [30 empty] | Nov 26 | [29 empty] | Dec 26 | [30 empty] | Jan 27 | [30 empty] | Feb 27
ID | WBS | Task | Dur | Planned Start | Planned Finish | Forecast Start | Forecast Finish | % | Resource | Status | _Row | _IsSummary | _IsMilestone | _DoneFrom | _DoneTo | _RemFrom | _RemTo | _Late | _Deadline | _Critical | time axis 2026-09-07 to 2027-02-03
1 | 1 | Initiation | 6 | 2026-09-07 | 2026-09-11 | 2026-09-07 | 2026-09-14 | 100% |  | Complete | 1 | TRUE | FALSE | 0 | 0 | 0 | 0 | TRUE | 0 | FALSE
2 | 1.1 | Project charter & scope statement | 3 | 2026-09-07 | 2026-09-09 | 2026-09-07 | 2026-09-10 | 100% | Priya Sharma | Complete | 2 | FALSE | FALSE | 2026-09-07 | 2026-09-10 | 0 | 0 | TRUE | 0 | FALSE
3 | 1.2 | Stakeholder kickoff workshop | 2 | 2026-09-10 | 2026-09-11 | 2026-09-11 | 2026-09-14 | 100% | Morgan Patel | Complete | 3 | FALSE | FALSE | 2026-09-11 | 2026-09-14 | 0 | 0 | TRUE | 0 | FALSE
4 | 1.3 | Kickoff complete | 0 | 2026-09-11 | 2026-09-11 | 2026-09-14 | 2026-09-14 | 100% |  | Complete | 4 | FALSE | TRUE | 0 | 0 | 0 | 0 | TRUE | 0 | FALSE
5 | 2 | Requirements & Design | 16 | 2026-09-14 | 2026-10-01 | 2026-09-15 | 2026-10-06 | 100% |  | Complete | 5 | TRUE | FALSE | 0 | 0 | 0 | 0 | TRUE | 0 | FALSE
6 | 2.1 | Requirements gathering | 8 | 2026-09-14 | 2026-09-23 | 2026-09-15 | 2026-09-25 | 100% | Morgan Patel | Complete | 6 | FALSE | FALSE | 2026-09-15 | 2026-09-25 | 0 | 0 | TRUE | 0 | FALSE
7 | 2.2 | Solution architecture | 5 | 2026-09-17 | 2026-09-23 | 2026-09-18 | 2026-09-25 | 100% | Alex Chen | Complete | 7 | FALSE | FALSE | 2026-09-18 | 2026-09-25 | 0 | 0 | TRUE | 0 | FALSE
8 | 2.3 | UX wireframes & prototype | 6 | 2026-09-24 | 2026-10-01 | 2026-09-28 | 2026-10-06 | 100% | Casey Kim | Complete | 8 | FALSE | FALSE | 2026-09-28 | 2026-10-06 | 0 | 0 | TRUE | 0 | FALSE
9 | 2.4 | Design sign-off | 0 | 2026-10-01 | 2026-10-01 | 2026-10-06 | 2026-10-06 | 100% |  | Complete | 9 | FALSE | TRUE | 0 | 0 | 0 | 0 | TRUE | 0 | FALSE
10 | 3 | Build | 24 | 2026-10-02 | 2026-10-30 | 2026-10-07 | 2026-11-09 | 45.13% |  | Behind | 10 | TRUE | FALSE | 0 | 0 | 0 | 0 | TRUE | 0 | TRUE
11 | 3.1 | Backend | 24 | 2026-10-02 | 2026-10-30 | 2026-10-07 | 2026-11-09 | 47.62% |  | Behind | 11 | TRUE | FALSE | 0 | 0 | 0 | 0 | TRUE | 0 | TRUE
12 | 3.1.1 | Data model & database setup | 5 | 2026-10-02 | 2026-10-08 | 2026-10-07 | 2026-10-14 | 100% | Jordan Lee | Complete | 12 | FALSE | FALSE | 2026-10-07 | 2026-10-14 | 0 | 0 | TRUE | 0 | FALSE
13 | 3.1.2 | Core API endpoints | 10 | 2026-10-09 | 2026-10-22 | 2026-10-15 | 2026-10-30 | 50% | Jordan Lee | Behind | 13 | FALSE | FALSE | 2026-10-15 | 2026-10-22 | 2026-10-23 | 2026-10-30 | TRUE | 0 | TRUE
14 | 3.1.3 | Payment gateway integration | 6 | 2026-10-23 | 2026-10-30 | 2026-11-02 | 2026-11-09 | 0% | Jordan Lee | Late Start | 14 | FALSE | FALSE | 0 | 0 | 2026-11-02 | 2026-11-09 | TRUE | 0 | TRUE
15 | 3.2 | Frontend | 23 | 2026-10-02 | 2026-10-29 | 2026-10-07 | 2026-11-06 | 42.86% |  | Behind | 15 | TRUE | FALSE | 0 | 0 | 0 | 0 | TRUE | 0 | TRUE
16 | 3.2.1 | UI component library | 6 | 2026-10-02 | 2026-10-09 | 2026-10-07 | 2026-10-16 | 100% | Sam Rivera | Complete | 16 | FALSE | FALSE | 2026-10-07 | 2026-10-16 | 0 | 0 | TRUE | 0 | FALSE
17 | 3.2.2 | Feature screens | 12 | 2026-10-13 | 2026-10-28 | 2026-10-19 | 2026-11-05 | 25% | Sam Rivera | Behind | 17 | FALSE | FALSE | 2026-10-19 | 2026-10-23 | 2026-10-24 | 2026-11-05 | TRUE | 0 | TRUE
18 | 3.2.3 | Accessibility review | 3 | 2026-10-27 | 2026-10-29 | 2026-11-04 | 2026-11-06 | 0% | Casey Kim | Not Started | 18 | FALSE | FALSE | 0 | 0 | 2026-11-04 | 2026-11-06 | TRUE | 0 | TRUE
19 | 3.3 | Build complete | 0 | 2026-10-30 | 2026-10-30 | 2026-11-09 | 2026-11-09 | 0% |  | Not Started | 19 | FALSE | TRUE | 0 | 0 | 0 | 0 | TRUE | 2026-11-06 | TRUE
20 | 4 | Test & Release | 36 | 2026-11-02 | 2027-01-04 | 2026-11-10 | 2027-01-04 | 0% |  | Not Started | 20 | TRUE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | TRUE
21 | 4.1 | System integration testing | 8 | 2026-11-02 | 2026-11-11 | 2026-11-10 | 2026-11-19 | 0% | Taylor Morgan | Not Started | 21 | FALSE | FALSE | 0 | 0 | 2026-11-10 | 2026-11-19 | TRUE | 0 | FALSE
22 | 4.2 | User acceptance testing | 6 | 2026-12-07 | 2026-12-14 | 2026-12-07 | 2026-12-14 | 0% | Morgan Patel | Not Started | 22 | FALSE | FALSE | 0 | 0 | 2026-12-07 | 2026-12-14 | FALSE | 0 | TRUE
23 | 4.3 | Training & user guides | 5 | 2026-11-04 | 2026-11-10 | 2026-11-12 | 2026-11-18 | 0% | Casey Kim | Not Started | 23 | FALSE | FALSE | 0 | 0 | 2026-11-12 | 2026-11-18 | TRUE | 0 | FALSE
24 | 4.4 | Go-live readiness review | 1 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 0% | Priya Sharma | Not Started | 24 | FALSE | FALSE | 0 | 0 | 2026-12-15 | 2026-12-15 | FALSE | 0 | TRUE
25 | 4.5 | Go-live | 0 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 0% |  | Not Started | 25 | FALSE | TRUE | 0 | 0 | 0 | 0 | FALSE | 2026-12-18 | TRUE
26 | 4.6 | Hypercare support | 10 | 2026-12-16 | 2027-01-04 | 2026-12-16 | 2027-01-04 | 0% | Jordan Lee | Not Started | 26 | FALSE | FALSE | 0 | 0 | 2026-12-16 | 2027-01-04 | FALSE | 0 | TRUE
27 | 5 | Project Close | 34 | 2026-11-16 | 2027-01-06 | 2026-11-16 | 2027-01-06 | 0% |  | Not Started | 27 | TRUE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | TRUE
28 | 5.1 | Steering committee update | 1 | 2026-11-16 | 2026-11-16 | 2026-11-16 | 2026-11-16 | 0% | Priya Sharma | Not Started | 28 | FALSE | FALSE | 0 | 0 | 2026-11-16 | 2026-11-16 | FALSE | 0 | FALSE
29 | 5.2 | Lessons learned | 2 | 2027-01-05 | 2027-01-06 | 2027-01-05 | 2027-01-06 | 0% | Priya Sharma | Not Started | 29 | FALSE | FALSE | 0 | 0 | 2027-01-05 | 2027-01-06 | FALSE | 0 | TRUE
30 | 5.3 | Project closed | 0 | 2027-01-06 | 2027-01-06 | 2027-01-06 | 2027-01-06 | 0% |  | Not Started | 30 | FALSE | TRUE | 0 | 0 | 0 | 0 | FALSE | 0 | TRUE
[11 empty] | 31 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 32 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 33 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 34 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 35 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 36 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 37 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 38 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 39 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 40 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 41 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 42 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 43 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 44 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 45 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 46 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 47 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 48 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 49 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 50 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 51 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 52 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 53 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 54 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 55 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 56 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 57 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 58 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 59 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 60 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 61 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 62 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 63 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 64 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 65 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 66 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 67 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 68 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 69 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 70 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 71 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 72 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 73 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 74 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 75 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 76 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 77 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 78 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 79 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 80 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 81 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 82 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 83 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 84 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 85 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 86 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 87 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 88 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 89 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 90 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 91 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 92 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 93 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 94 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 95 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 96 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 97 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 98 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 99 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 100 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 101 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 102 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 103 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 104 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 105 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 106 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 107 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 108 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 109 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 110 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 111 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 112 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 113 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 114 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 115 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 116 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 117 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 118 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 119 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 120 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 121 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 122 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 123 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 124 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 125 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 126 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 127 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 128 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 129 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 130 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 131 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 132 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 133 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 134 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 135 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 136 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 137 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 138 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 139 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 140 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 141 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 142 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 143 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 144 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 145 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 146 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 147 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 148 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 149 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 150 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 151 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 152 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 153 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 154 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 155 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 156 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 157 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 158 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 159 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 160 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 161 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 162 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 163 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 164 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 165 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 166 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 167 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 168 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 169 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 170 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 171 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 172 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 173 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 174 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 175 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 176 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 177 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 178 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 179 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 180 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 181 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 182 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 183 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 184 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 185 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 186 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 187 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 188 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 189 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 190 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 191 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 192 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 193 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 194 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 195 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 196 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 197 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 198 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 199 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[11 empty] | 200 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE

## Resources
Resource Sheet
Like MS Project's Resource Sheet. Names here feed the Resource dropdown on Tasks. Add rows to the table for more people.
| Resource Name | Initials | Group | Type | Max Units | Std Rate | Email | Tasks | Work | Cost | Actual Cost | Notes
| Priya Sharma | PS | Project Manager | Work | 50% | 95 | priya@example.com | 4 | 56 | 5320 | 3040
| Morgan Patel | MP | Business Analyst | Work | 100% | 70 | morgan@example.com | 3 | 128 | 8960 | 6160
| Alex Chen | AC | Solution Architect | Work | 50% | 110 | alex@example.com | 1 | 40 | 4400 | 4400
| Casey Kim | CK | UX Designer | Work | 100% | 75 | casey@example.com | 3 | 80 | 6000 | 3600
| Jordan Lee | JL | Backend Developer | Work | 100% | 85 | jordan@example.com | 4 | 208 | 17680 | 7480
| Sam Rivera | SR | Frontend Developer | Work | 100% | 80 | sam@example.com | 2 | 144 | 11520 | 5760
| Taylor Morgan | TM | QA Engineer | Work | 100% | 65 | taylor@example.com | 1 | 64 | 4160 | 0
Note on E5: Work, Material or Cost (MS Project resource types).
Note on F5: Availability: 100% = full time.
Note on G5: Standard rate per hour.
Note on I5: Detail tasks assigned to this resource.
Note on J5: Assigned work (hours).
Note on K5: Assigned cost.
Note on L5: Cost to date: Actual Cost entered on Tasks, or Cost x Progress where blank.

## Sprints
Customer Portal Implementation - Sprint & Capacity Planning
Sprint calendar from Settings (Sprint1Start, SprintLength, SprintCount); add rows to the table for more sprints. Each task's work is spread evenly over its forecast working days, then summed per sprint.
No | Sprint | Start | End | Working Days | Goal | Tasks Starting | Planned Work | Capacity | Utilisation | Status | Points Capacity | Committed Points | Done Points | Velocity | Remaining Points | Forecast Remaining | Ideal Remaining | _ChartRemaining
1 | Sprint 1 | 2026-09-07 | 2026-09-20 | 10 | Charter & kickoff | 5 | 75.1111 | 480 | 15.65% | Closed |  | 18 | 5 | 5 | 77 | 77 | 75.1667 | 77
2 | Sprint 2 | 2026-09-21 | 2026-10-04 | 10 | Requirements | 1 | 103.1746 | 480 | 21.49% | Closed |  | 5 | 13 | 9 | 64 | 64 | 68.3333 | 64
3 | Sprint 3 | 2026-10-05 | 2026-10-18 | 10 | Design & architecture | 4 | 115.0476 | 480 | 23.97% | Closed |  | 18 | 15 | 11 | 49 | 49 | 61.5 | 49
4 | Sprint 4 | 2026-10-19 | 2026-11-01 | 10 | Foundations: DB + components | 1 | 135.2381 | 480 | 28.17% | Active |  | 8 | 0 |  | 49 | 41 | 54.6667 | 49
5 | Sprint 5 | 2026-11-02 | 2026-11-15 | 10 | Core APIs + screens | 5 | 127.4286 | 480 | 26.55% | Future |  | 19 |  |  |  | 25 | 47.8333 | #N/A
6 | Sprint 6 | 2026-11-16 | 2026-11-29 | 10 | Payments + screens | 1 | 52 | 480 | 10.83% | Future |  | 1 |  |  |  | 13 | 41 | #N/A
7 | Sprint 7 | 2026-11-30 | 2026-12-13 | 10 | Feature complete | 1 | 40 | 480 | 8.333% | Future |  | 5 |  |  |  | 13 | 34.1667 | #N/A
8 | Sprint 8 | 2026-12-14 | 2026-12-27 | 8 | System testing | 3 | 40 | 384 | 10.42% | Future |  | 6 |  |  |  | 7 | 27.3333 | #N/A
9 | Sprint 9 | 2026-12-28 | 2027-01-10 | 8 | UAT | 2 | 32 | 384 | 8.333% | Future |  | 2 |  |  |  | 0 | 20.5 | #N/A
10 | Sprint 10 | 2027-01-11 | 2027-01-24 | 10 | Release & hypercare | 0 | 0 | 480 | 0% | Future |  | 0 |  |  |  | 0 | 13.6667 | #N/A
11 | Sprint 11 | 2027-01-25 | 2027-02-07 | 10 | Hypercare | 0 | 0 | 480 | 0% | Future |  | 0 |  |  |  | 0 | 6.8333 | #N/A
12 | Sprint 12 | 2027-02-08 | 2027-02-21 | 10 | Close-out | 0 | 0 | 480 | 0% | Future |  | 0 |  |  |  | 0 | 0 | #N/A
13 |  | 2027-02-22 | 2027-03-07 | 10 | [13 empty] | #N/A
14 |  | 2027-03-08 | 2027-03-21 | 10 | [13 empty] | #N/A
15 |  | 2027-03-22 | 2027-04-04 | 10 | [13 empty] | #N/A
16 |  | 2027-04-05 | 2027-04-18 | 10 | [13 empty] | #N/A
17 |  | 2027-04-19 | 2027-05-02 | 10 | [13 empty] | #N/A
18 |  | 2027-05-03 | 2027-05-16 | 10 | [13 empty] | #N/A
19 |  | 2027-05-17 | 2027-05-30 | 10 | [13 empty] | #N/A
20 |  | 2027-05-31 | 2027-06-13 | 10 | [13 empty] | #N/A
21 |  | 2027-06-14 | 2027-06-27 | 10 | [13 empty] | #N/A
22 |  | 2027-06-28 | 2027-07-11 | 10 | [13 empty] | #N/A
23 |  | 2027-07-12 | 2027-07-25 | 10 | [13 empty] | #N/A
24 |  | 2027-07-26 | 2027-08-08 | 10 | [13 empty] | #N/A
25 |  | 2027-08-09 | 2027-08-22 | 10 | [13 empty] | #N/A
26 |  | 2027-08-23 | 2027-09-05 | 10 | [13 empty] | #N/A
Resource load by sprint (hours) - red = over capacity (Max Units x HoursPerDay x working days)
| Resource | Max Units | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | Sprint 12
| Sprint start |  | 2026-09-07 | 2026-09-21 | 2026-10-05 | 2026-10-19 | 2026-11-02 | 2026-11-16 | 2026-11-30 | 2026-12-14 | 2026-12-28 | 2027-01-11 | 2027-01-25 | 2027-02-08
| Priya Sharma | 50% | 24 | 0 | 0 | 0 | 0 | 8 | 0 | 8 | 16 | 0 | 0 | 0
| Morgan Patel | 100% | 44.4444 | 35.5556 | 0 | 0 | 0 | 0 | 40 | 8 | 0 | 0 | 0 | 0
| Alex Chen | 50% | 6.6667 | 33.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Casey Kim | 100% | 0 | 34.2857 | 13.7143 | 0 | 20 | 12 | 0 | 0 | 0 | 0 | 0 | 0
| Jordan Lee | 100% | 0 | 0 | 53.3333 | 66.6667 | 48 | 0 | 0 | 24 | 16 | 0 | 0 | 0
| Sam Rivera | 100% | 0 | 0 | 48 | 68.5714 | 27.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Taylor Morgan | 100% | 0 | 0 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0
Resource utilisation by sprint (%)
| Resource | Max Units | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | Sprint 12
| Sprint start |  | 2026-09-07 | 2026-09-21 | 2026-10-05 | 2026-10-19 | 2026-11-02 | 2026-11-16 | 2026-11-30 | 2026-12-14 | 2026-12-28 | 2027-01-11 | 2027-01-25 | 2027-02-08
| Priya Sharma | 50% | 60% | 0% | 0% | 0% | 0% | 20% | 0% | 25% | 50% | 0% | 0% | 0%
| Morgan Patel | 100% | 55.56% | 44.44% | 0% | 0% | 0% | 0% | 50% | 12.5% | 0% | 0% | 0% | 0%
| Alex Chen | 50% | 16.67% | 83.33% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Casey Kim | 100% | 0% | 42.86% | 17.14% | 0% | 25% | 15% | 0% | 0% | 0% | 0% | 0% | 0%
| Jordan Lee | 100% | 0% | 0% | 66.67% | 83.33% | 60% | 0% | 0% | 37.5% | 25% | 0% | 0% | 0%
| Sam Rivera | 100% | 0% | 0% | 60% | 85.71% | 34.29% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Taylor Morgan | 100% | 0% | 0% | 0% | 0% | 40% | 40% | 0% | 0% | 0% | 0% | 0% | 0%
Formulas:
Start = Sprint1Start+(SprintTable[[#This Row],[No]]-1)*SprintLength
End = SprintTable[[#This Row],[Start]]+SprintLength-1
Working Days = NETWORKDAYS.INTL(SprintTable[[#This Row],[Start]],SprintTable[[#This Row],[End]],WorkWeek,Holidays)
Note on H5: Hours of task work falling in the sprint.
Note on I5: Sum of Work resources' Max Units x HoursPerDay x working days.
Note on L5: Optional: story points the team can take on in the sprint. Committed Points turn red above it.
Note on M5: Story points of the tasks in this sprint (Tasks > Sprint).
Note on N5: Story points of tasks finished during the sprint (by Actual Finish).
Note on O5: Average Done Points of this and the two previous sprints (closed sprints only).
Note on P5: Release burndown: story points not yet done at the sprint end (or the status date).
Note on Q5: Points still open at the sprint end if tasks finish on their forecast dates.
Note on R5: Straight line from the total scope to zero at the last sprint.

## Holidays
Holidays & Non-Working Days
Every date in this table is skipped by all scheduling formulas (named range: Holidays). Add rows to the table as needed.
| Date | Description
| 2026-12-24 | Christmas Eve (example - replace with your calendar)
| 2026-12-25 | Christmas Day (example)
| 2026-12-31 | New Year's Eve (example)
| 2027-01-01 | New Year's Day (example)

## MSP_Tasks
ID | Unique ID | Name | Outline Level | Task Mode | Duration | Start | Finish | Predecessors | Unique ID Predecessors | Resource Names | % Complete | Actual Start | Actual Finish | Baseline Start | Baseline Finish | Baseline Duration | Baseline Work | Baseline Cost | Actual Cost | Constraint Type | Constraint Date | Deadline | Text1 | Number1 | Notes
1 | 1 | Initiation | 1 | Auto Scheduled |  | 2026-09-07 | 2026-09-14 | [6 empty] | 2026-09-07 | 2026-09-11 | [9 empty] | Phase 1 - summary rows roll up dates, work, cost and progress automatically.
2 | 2 | Project charter & scope statement | 2 | Auto Scheduled | 3d | 2026-09-07 | 2026-09-10 |  |  | Priya Sharma | 100 | 2026-09-07 | 2026-09-10 | 2026-09-07 | 2026-09-09 |  |  |  | 3040 | As Soon As Possible |  |  | Sprint 1 | 3 | Took 1 extra day for sponsor sign-off.
3 | 3 | Stakeholder kickoff workshop | 2 | Auto Scheduled | 2d | 2026-09-11 | 2026-09-14 | 2 | 2 | Morgan Patel | 100 | 2026-09-11 | 2026-09-14 | 2026-09-10 | 2026-09-11 |  |  |  |  | As Soon As Possible |  |  | Sprint 1 | 2
4 | 4 | Kickoff complete | 2 | Auto Scheduled | 0d | 2026-09-14 | 2026-09-14 | 3 | 3 |  | 100 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 |  |  |  |  | As Soon As Possible |  |  | Sprint 1 |  | Milestone (Duration 0).
5 | 5 | Requirements & Design | 1 | Auto Scheduled |  | 2026-09-15 | 2026-10-06 | [6 empty] | 2026-09-14 | 2026-10-01
6 | 6 | Requirements gathering | 2 | Auto Scheduled | 8d | 2026-09-15 | 2026-09-25 | 4 | 4 | Morgan Patel | 100 | 2026-09-15 | 2026-09-25 | 2026-09-14 | 2026-09-23 |  |  |  | 5040 | As Soon As Possible |  |  | Sprint 1 | 8
7 | 7 | Solution architecture | 2 | Auto Scheduled | 5d | 2026-09-18 | 2026-09-25 | 6SS+3d | 6SS+3d | Alex Chen | 100 | 2026-09-18 | 2026-09-25 | 2026-09-17 | 2026-09-23 |  |  |  |  | As Soon As Possible |  |  | Sprint 1 | 5 | Start-to-Start + 3 day lag example.
8 | 8 | UX wireframes & prototype | 2 | Auto Scheduled | 6d | 2026-09-28 | 2026-10-06 | 6 | 6 | Casey Kim | 100 | 2026-09-28 | 2026-10-06 | 2026-09-24 | 2026-10-01 |  |  |  |  | As Soon As Possible |  |  | Sprint 2 | 5
9 | 9 | Design sign-off | 2 | Auto Scheduled | 0d | 2026-10-06 | 2026-10-06 | 7,8 | 7,8 |  | 100 | 2026-10-06 | 2026-10-06 | 2026-10-01 | 2026-10-01 |  |  |  |  | As Soon As Possible |  |  | Sprint 3 |  | Two predecessors - waits for the later one.
10 | 10 | Build | 1 | Auto Scheduled |  | 2026-10-07 | 2026-11-09 | [6 empty] | 2026-10-02 | 2026-10-30
11 | 11 | Backend | 2 | Auto Scheduled |  | 2026-10-07 | 2026-11-09 | [6 empty] | 2026-10-02 | 2026-10-30 | [9 empty] | Level-2 summary with sub-tasks.
12 | 12 | Data model & database setup | 3 | Auto Scheduled | 5d | 2026-10-07 | 2026-10-14 | 9 | 9 | Jordan Lee | 100 | 2026-10-07 | 2026-10-14 | 2026-10-02 | 2026-10-08 |  |  |  |  | As Soon As Possible |  |  | Sprint 3 | 5
13 | 13 | Core API endpoints | 3 | Auto Scheduled | 10d | 2026-10-15 | 2026-10-30 | 12 | 12 | Jordan Lee | 50 | 2026-10-15 |  | 2026-10-09 | 2026-10-22 |  |  |  | 4080 | As Soon As Possible |  |  | Sprint 3 | 8 | In progress - enter % Complete; forecast finish adjusts.
14 | 14 | Payment gateway integration | 3 | Auto Scheduled | 6d | 2026-11-02 | 2026-11-09 | 13 | 13 | Jordan Lee | 0 |  |  | 2026-10-23 | 2026-10-30 |  |  |  |  | As Soon As Possible |  |  | Sprint 5 | 5
15 | 15 | Frontend | 2 | Auto Scheduled |  | 2026-10-07 | 2026-11-06 | [6 empty] | 2026-10-02 | 2026-10-29
16 | 16 | UI component library | 3 | Auto Scheduled | 6d | 2026-10-07 | 2026-10-16 | 9 | 9 | Sam Rivera | 100 | 2026-10-07 | 2026-10-16 | 2026-10-02 | 2026-10-09 |  |  |  |  | As Soon As Possible |  |  | Sprint 3 | 5
17 | 17 | Feature screens | 3 | Auto Scheduled | 12d | 2026-10-19 | 2026-11-05 | 16,13SS+2d | 16,13SS+2d | Sam Rivera | 25 | 2026-10-19 |  | 2026-10-13 | 2026-10-28 |  |  |  |  | As Soon As Possible |  |  | Sprint 4 | 8
18 | 18 | Accessibility review | 3 | Auto Scheduled | 3d | 2026-11-04 | 2026-11-06 | 17FF+1d | 17FF+1d | Casey Kim[50%] | 0 |  |  | 2026-10-27 | 2026-10-29 |  |  |  |  | As Soon As Possible |  |  | Sprint 5 | 3 | Finish-to-Finish + 1 day; 50% units.
19 | 19 | Build complete | 2 | Auto Scheduled | 0d | 2026-11-09 | 2026-11-09 | 14,18 | 14,18 |  | 0 |  |  | 2026-10-30 | 2026-10-30 |  |  |  |  | As Soon As Possible |  | 2026-11-06 | Sprint 5 |  | Milestone with a deadline of 06-Nov (see Deadline Check).
20 | 20 | Test & Release | 1 | Auto Scheduled |  | 2026-11-10 | 2027-01-04 | [6 empty] | 2026-11-02 | 2027-01-04
21 | 21 | System integration testing | 2 | Auto Scheduled | 8d | 2026-11-10 | 2026-11-19 | 19 | 19 | Taylor Morgan | 0 |  |  | 2026-11-02 | 2026-11-11 |  |  |  |  | As Soon As Possible |  |  | Sprint 5 | 8
22 | 22 | User acceptance testing | 2 | Auto Scheduled | 6d | 2026-12-07 | 2026-12-14 | 21 | 21 | Morgan Patel | 0 |  |  | 2026-12-07 | 2026-12-14 |  |  |  |  | Start No Earlier Than | 2026-12-07 |  | Sprint 7 | 5 | Start No Earlier Than 07-Dec (client availability).
23 | 23 | Training & user guides | 2 | Auto Scheduled | 5d | 2026-11-12 | 2026-11-18 | 21SS+2d | 21SS+2d | Casey Kim[50%] | 0 |  |  | 2026-11-04 | 2026-11-10 |  |  |  |  | As Soon As Possible |  |  | Sprint 5 | 3
24 | 24 | Go-live readiness review | 2 | Auto Scheduled | 1d | 2026-12-15 | 2026-12-15 | 22,23 | 22,23 | Priya Sharma | 0 |  |  | 2026-12-15 | 2026-12-15 |  |  |  |  | As Soon As Possible |  |  | Sprint 8 | 1
25 | 25 | Go-live | 2 | Auto Scheduled | 0d | 2026-12-15 | 2026-12-15 | 24 | 24 |  | 0 |  |  | 2026-12-15 | 2026-12-15 |  |  |  |  | As Soon As Possible |  | 2026-12-18 | Sprint 8 |  | Milestone with a deadline of 18-Dec.
26 | 26 | Hypercare support | 2 | Auto Scheduled | 10d | 2026-12-16 | 2027-01-04 | 25 | 25 | Jordan Lee[50%] | 0 |  |  | 2026-12-16 | 2027-01-04 |  |  |  |  | As Soon As Possible |  |  | Sprint 8 | 5
27 | 27 | Project Close | 1 | Auto Scheduled |  | 2026-11-16 | 2027-01-06 | [6 empty] | 2026-11-16 | 2027-01-06
28 | 28 | Steering committee update | 2 | Manually Scheduled | 1d | 2026-11-16 | 2026-11-16 |  |  | Priya Sharma | 0 |  |  | 2026-11-16 | 2026-11-16 |  |  |  |  | As Soon As Possible |  |  | Sprint 6 | 1 | Manual mode example: fixed on the date in the Start No Earlier Than column.
29 | 29 | Lessons learned | 2 | Auto Scheduled | 2d | 2027-01-05 | 2027-01-06 | 26 | 26 | Priya Sharma | 0 |  |  | 2027-01-05 | 2027-01-06 |  |  |  |  | As Soon As Possible |  |  | Sprint 9 | 2
30 | 30 | Project closed | 2 | Auto Scheduled | 0d | 2027-01-06 | 2027-01-06 | 29 | 29 |  | 0 |  |  | 2027-01-06 | 2027-01-06 |  |  |  |  | As Soon As Possible |  |  | Sprint 9 |  | Milestone
Formulas:
Start = IF(IFERROR(INDEX(tsk_Name,(ROW()-ROW(MSPTasks[[#Headers],[ID]])))="",TRUE()),"",INDEX(tsk_FcStart,(ROW()-ROW(MSPTasks[[#Headers],[ID]]))))
Finish = IF(IFERROR(INDEX(tsk_Name,(ROW()-ROW(MSPTasks[[#Headers],[ID]])))="",TRUE()),"",INDEX(tsk_FcFinish,(ROW()-ROW(MSPTasks[[#Headers],[ID]]))))
Baseline Start = IF(IFERROR(INDEX(tsk_Name,(ROW()-ROW(MSPTasks[[#Headers],[ID]])))="",TRUE()),"",INDEX(tsk_PlanStart,(ROW()-ROW(MSPTasks[[#Headers],[ID]]))))
Baseline Finish = IF(IFERROR(INDEX(tsk_Name,(ROW()-ROW(MSPTasks[[#Headers],[ID]])))="",TRUE()),"",INDEX(tsk_PlanFinish,(ROW()-ROW(MSPTasks[[#Headers],[ID]]))))
Actual Start = IF(IFERROR(INDEX(tsk_Name,(ROW()-ROW(MSPTasks[[#Headers],[ID]])))="",TRUE()),"",IF(N(INDEX(tsk_ActStart,(ROW()-ROW(MSPTasks[[#Headers],[ID]]))))=0,"",INDEX(tsk_ActStart,(ROW()-ROW(MSPTasks[[#Headers],[ID]])))))
Actual Finish = IF(IFERROR(INDEX(tsk_Name,(ROW()-ROW(MSPTasks[[#Headers],[ID]])))="",TRUE()),"",IF(N(INDEX(tsk_ActFinish,(ROW()-ROW(MSPTasks[[#Headers],[ID]]))))=0,"",INDEX(tsk_ActFinish,(ROW()-ROW(MSPTasks[[#Headers],[ID]])))))
Deadline = IF(IFERROR(INDEX(tsk_Name,(ROW()-ROW(MSPTasks[[#Headers],[ID]])))="",TRUE()),"",IF(N(INDEX(tsk_Deadline,(ROW()-ROW(MSPTasks[[#Headers],[ID]]))))=0,"",INDEX(tsk_Deadline,(ROW()-ROW(MSPTasks[[#Headers],[ID]])))))
Note on X1: Sprint, in MS Project's custom field Text1 (rename it Sprint in MS Project).
Note on Y1: Story points, in MS Project's custom field Number1.

## MSP_Resources
Name | Initials | Group | Type | Max Units | Standard Rate | Email Address
Priya Sharma | PS | Project Manager | Work | 50% | 95/h | priya@example.com
Morgan Patel | MP | Business Analyst | Work | 100% | 70/h | morgan@example.com
Alex Chen | AC | Solution Architect | Work | 50% | 110/h | alex@example.com
Casey Kim | CK | UX Designer | Work | 100% | 75/h | casey@example.com
Jordan Lee | JL | Backend Developer | Work | 100% | 85/h | jordan@example.com
Sam Rivera | SR | Frontend Developer | Work | 100% | 80/h | sam@example.com
Taylor Morgan | TM | QA Engineer | Work | 100% | 65/h | taylor@example.com

## Lists
Link Type | Task Mode | Yes / No | Resource Type | Gantt Days per Column | RAG
FS | Auto | Yes | Work | 1 | Green
SS | Manual | No | Material | 7 | Amber
FF |  |  | Cost |  | Red
SF
Dropdown sources. Add a value by typing it in the row under a list: the table and its named range grow.