## Start
Project Planner - start here
Blue = type here. Grey = calculated. Every sheet works in Excel alone: desktop, web and iPhone.
YOUR PROJECT
Project name | Customer Portal Implementation
Project manager | Priya Sharma
Project start date | 2026-09-07
Working week | Mon-Fri
Working hours per day | 8
Project type | Software / Agile
QUICK START
1. Your project | Fill in the blue cells above: name, manager, start date, working week, hours per day and the project type (it sets the stages, sprint length and RAG thresholds). Everything else has a sensible default on Settings. Go to Settings.
2. People | List the people (or roles) with their Allocation %. Leave: type 1 (or 0.5) under each day off in the LEAVE BY DAY grid under the people (or type the days in a month column). Go to Resources.
3. Tasks | One row per task: Level (1 = phase, 2 = task ...), Task Name and Duration (3, 3d or 2w). Pick what must come first in Pred1 (a dropdown of the tasks above) and who does it in Res1; + opens links and people 2-4. Dates, the critical path, the Gantt and the reports follow. Go to Tasks.
4. Check | Fix anything in the Issues column (red), then look at the Gantt timeline to the right of the table (the link at the top of Tasks) and the Roadmap. Go to Tasks.
5. Baseline | When the plan is agreed, freeze it: on Tasks open the BASELINE section (+), copy the 4 'BL Source' columns and Paste Special > Values onto the 4 Baseline columns. Go to Tasks.
EVERY WEEK
Status sheet | Type the status date at the top of Status and follow its steps (progress on Tasks, the Log, the RAG, the commentary). Then the Check sheet, and the snapshot row on TakeSnapshot. A report in about ten minutes. Go to Status.
REFERENCE
REQUIREMENTS
Excel version | Excel 2019 or Microsoft 365 (Windows or Mac), or Excel for the web. No macros needed.
HOW IT WORKS
1. Settings | Project start (a typed date; Ctrl+; enters today), working week and hours/day are at the top of this sheet; the status date is at the top of the Status sheet. Settings holds the rest (Gantt scale, sprint calendar, RAG thresholds ...). Holidays are listed on Settings, below the settings. Update the status date whenever you report progress.
2. Resources | List people/roles with their Allocation % (share of them on this project), optional Start / End dates on the project and Focus % (share of sprint time on delivery; 0% = an advisory role). Day rates are on the Cost sheet. Type their names (or initials) in the Resources column on Tasks: several people are comma-separated, with an optional share of their time, e.g. 'Alex Chen, JL[50%]'.
3. Tasks | One row per task. Enter Level (1 = phase/summary, 2 = task, 3 = sub-task...), Task Name, Duration in working days (0 = milestone), and Predecessors: the UIDs of up to four tasks that must come first, comma-separated, each with an optional link type (FS, SS, FF, SF) and lag in days (negative = lead), e.g. '12, 14SS+2d'. A row becomes a SUMMARY automatically when the rows beneath it have a higher level; its dates, work, cost and progress roll up. Optional Deadline: Deadline Check shows 'Late by Nd'. Hover over a column header for what it means.
4. Set the baseline | When the plan is agreed: on Tasks, select the 4 'BL Source' columns (all task rows), Copy, then select the first 'Baseline Start' cell and Paste Special > Values. Planned Start/Finish now stay frozen (like MS Project's Baseline) and the variance columns compare against it. To re-baseline, repeat; to clear it, delete the 4 Baseline columns' contents.
5. Track progress | Pick each task's Stage (Not Started, Design, In Development, Test Ready, In Testing, Complete; each stage's % is on Settings > Stages, editable) and enter Actual Start once it starts and Actual Finish when it's done; Issues asks for the dates the Stage calls for. % Complete (DETAIL section) overrides the stage's % when typed. Start / Finish (the current schedule) then use actuals and push every dependent task. Start / Finish / Duration / Work Var and Status flag slippage; cost to date is worked out on the Cost sheet (work done x day rates).
Critical path | Late Start / Late Finish come from a backward pass from the forecast project finish (and any deadline). Total Slack = how far a task can slip before it delays the project or a deadline; Free Slack = before it delays a successor. Critical = slack <= Settings > CriticalSlackDays on an unfinished task. A missed deadline gives negative slack to the task and the chain feeding it.
6. Gantt | The timeline is on the Tasks sheet, to the right of the table, on the same rows (the link 'Gantt timeline >>' at the top jumps there; ID and Task stay frozen on the left). It is conditional formatting only. Timeline: black outline = planned dates (the baseline once set; a task added after the baseline has no outline), pale blue-grey = planned days no work is on now, green = done, blue = remaining on track, red = remaining past the planned finish (slip), orange = remaining on the critical path, dark grey = summary, purple = milestone, red cell = deadline, red line = status date. Change GanttStart / GanttPeriod (1 = days, 7 = weeks, 30 = months, 91 = quarters) on Settings to scroll or zoom. Collapse the outline with the 1 2 3 buttons at the top left (rows are grouped by Level), or set Settings > OutlineShowLevel and filter Show = Yes (DETAIL section).
6b. Roadmap | One landscape page for sponsors. Each phase (Level 1) with its owner (Tasks > Owner, WORK section), progress (duration-weighted) and how many of its tasks are done, a RAG from its finish slip, its next milestone and a link to its row; then the milestones. Drawn by month (blue = forecast, green = done, amber = late vs plan, outline = planned, purple = milestone, red = deadline missed). Settings > RoadmapStart scrolls the 18 months shown.
8. Status | The weekly page, printable on one page: the status date and this week's steps, overall RAG and RAG by area (schedule, SPI, deadlines, critical path, RAID, plan quality) calculated from the thresholds on Settings (RAG...); pick a PM RAG to override one and say why in Comment. Then key figures (SPI here is duration-weighted: progress / progress planned by now), tasks by status, next milestones, the top open RAID items, the first five late tasks, tasks due and starting in the look-ahead window (Settings > LookaheadDays) and open critical tasks (filter Tasks by Status or Critical for the full lists), change control, the commentary for the period and the snapshot row for History.
Protected sheets | Start, Status, Roadmap, Resource Report, Agile, Log, Cost, Check and TakeSnapshot are protected without a password: their blue cells take typing, the formulas can't be typed over. Tasks, Resources, Settings and History stay open because rows are added there (Excel can't add table rows on a protected sheet), but their formula cells are locked: Review > Protect Sheet (no password) protects them too, and Unprotect Sheet lifts it before adding rows.
Leave | On Resources. Easiest: the LEAVE BY DAY grid under the people: pick the person and the month, then type 1 (all day) or 0.5 (half a day) under each day off; its Days column builds the text the reports read. Or type the days in the person's month column: '16, 17(0.5)' under Nov-26. Both count (don't enter a day in both). Weekends and holidays are ignored. Leave lowers capacity, it doesn't move task dates.
CELL COLOURS
Blue text | Input - type here.
Black text on grey | Formula - do not overwrite. Summary rows grey-out inputs that are ignored.
Dark blue header | Input column. Dark grey header = calculated. Light grey header = helper column (hidden, grouped).
Duration | Working days: 3, 3d or 2w (a week = 5 working days); 0 = a milestone. Anything else (e.g. '2days') is refused when typed and flagged in Issues when pasted.
Printing | Status, Roadmap, Resource Report and Check are set to print on one page wide, with the template version and page number in the footer.
Limits | See README > Limits: the predecessor rule (above its successor), 4 links and 4 people per task, the fixed grid sizes, and what needs a rebuild.
RACI | Tasks > RACI (+): Accountable (one person, from Resources), Consulted and Informed (names, comma-separated). Responsible is the task's Resources. Resources counts each person's tasks in each role.
Dependencies | On the Log, a Dependency row with an Expected date and a Task UID shows the task's start and the gap in working days (negative = it arrives too late). Status lists the five latest against their task; Check counts the late ones.
Sandbox | Try a what-if without touching the plan: type a Sandbox Duration on the tasks (Tasks > ESTIMATES and SANDBOX), then Settings > Sandbox = Yes. Every date and report follows; Status and Check say the sandbox is on. Set No to go back; the Sandbox Durations stay for next time.
Three-point estimates | Optimistic and Pessimistic beside a task's Duration give its Expected duration ((O + 4 x Duration + P) / 6). Status shows the finish with a 50% (P50) and 80% (P80) chance, from the critical tasks' estimates.
Summary | Status > SUMMARY writes the status in one paragraph (RAG, finish, progress, late tasks, next milestone, top risk, late dependencies): copy it into the commentary and add the why.
RULES (same as MS Project)
ID and UID | ID = position of the task (renumbers when rows move). UID = permanent number that predecessors refer to: pre-filled for every row, and a typed UID must be a whole number no other task uses (the cell refuses a duplicate). Settings counts duplicate and missing UIDs; the Check sheet lists them.
Inserting tasks | Tasks is an Excel Table: right-click a row > Insert > Table Rows Above (or type in the row under the table). Every formula fills in automatically. Set the new task's UID to Settings > NextFreeUID (also shown at the top of Tasks).
Outline levels | Each row's Level may be at most 1 higher than the row above. A '?' in WBS (red) means a level jump.
Predecessors | Pick each predecessor in Pred1-4 (a dropdown of the detail tasks, 'UID Name'; typing a UID works too), with an optional Type (FS, SS, FF, SF) and Lag in working days. While Pred1-4 are blank the typed Predecessors text is used ('12, 14SS+2d'), which is where pasted and imported plans land. A predecessor must be a detail task listed ABOVE its successor; anything else is ignored and explained in Link Check and Issues.
Mode | Auto = scheduled from predecessors, project start and the constraint. Manual = pinned to the Constraint Date.
Constraints | Pick an MS Project constraint and enter its Constraint Date (a date alone = Start No Earlier Than). Start / Finish No Earlier Than push the task later; Start / Finish No Later Than and Must Start / Finish On win over predecessors (as in MS Project), so a conflict shows as negative slack. As Late As Possible moves the task later by its free slack: it finishes just in time for its successors and moves nothing else (its planned dates move by the same days).
Rescheduling | Settings > RescheduleAfterStatus = Yes moves incomplete work to after the status date (like MS Project 'Update Project'), so late tasks push successors.
Pasting rows | Paste rows under the last task (or into the table) as values: formulas fill in. Pasting skips the cells' checks, so Issues also flags a Duration or date that came in as text (e.g. '2d', or a date in another format) and suggests a name ('Did you mean Alex Chen?') for a person who isn't on Resources.
Capacity | Tables grow when you add rows: Tasks starts with 200 rows, Resources 50, SprintTable 26, Log 150, Holidays 100. The Gantt timeline has 150 columns; the per-resource grids on the Resource Report show the first 25 resources and the Resource Report 26 weeks. To change these sizes, rebuild with scripts/build_planner.py --tasks / --resources / --grid-resources / --sprints / --gantt-columns / --weeks (see README).
Speed | An edit recalculates in well under a second for typical plans (about 0.05 s for 200 tasks). Each change to the build is timed in CI; see docs/ARCHITECTURE.md in the repository. Keep the status date typed (not =TODAY()), which would recalculate everything after every edit.
Views not updating? | Formulas > Calculation Options must be Automatic. Excel takes the mode from the first workbook opened in a session, so another workbook in Manual mode makes this one manual too: switch back to Automatic, or press F9 to recalculate.
MOVING TO MICROSOFT PROJECT
Best: MS Project XML | Save this workbook, then convert it with the browser page docs/export.html in the repository (nothing to install; works on a phone; the file stays on your device) or python scripts/export_mspdi.py. In MS Project: File > Open > the .xml > 'Open as a new project'. It carries the calendar and holidays, links by UID with lags, constraints, deadlines, actuals, the baseline, resources, assignments, Sprint (Text1) and Story Points (Number1), so MS Project schedules the plan the same way.
From MS Project | MS Project > File > Save As > XML, then choose the .xml on docs/export.html (or run python scripts/import_mspdi.py): you get a new planner workbook with the project's tasks, links, calendar, holidays, resources, assignments, baseline and leave. Anything the planner can't hold is listed and noted on the task.
Upgrading | To move a plan made with an older version of this template into the latest one, choose the old workbook on docs/export.html with 'Move to the latest template' (or run python scripts/upgrade_planner.py old.xlsx new.xlsx). Everything you typed is carried over.
NAMES AND TABLES (Formulas > Name Manager)
Tables | Tasks, ResourceTable, SprintTable, HolidayTable, KPIs, StatusSummary, NextMilestones, OverallStatus, StatusRAG, StatusNotes, RoadmapPhases, RoadmapMilestones, LateTasks, StartingSoon, DueSoon, CriticalTasks, ResourceSummary, AgileKPIs, SprintBacklog, SprintBurndown, Log, TopRAID, ChangeControl, SnapshotNow, StatusHistory and the List* dropdown tables. Inside a table, formulas read [@Column] (this row).
Settings | ProjectStart, StatusDate, StatusWorkday, WorkWeek, Holidays, HoursPerDay, DefaultUnits, RescheduleAfterStatus, GanttStart, GanttPeriod, OutlineShowLevel, RoadmapStart, Sprint1Start, SprintLength, SprintCount, SprintPrefix, SprintLastEnd, CriticalSlackDays, ProjectFinish, PlannedFinish, FinishVarianceDays, LookaheadDays, RAGAmberSlipDays, RAGRedSlipDays, RAGAmberIndex, RAGRedIndex, ResourceWeekStart, CurrentSprint, TotalPoints, RAIDHighScore, RAIDMediumScore, FocusFactor, NextFreeUID. Report values: ProjectRAG, sch_Progress, sch_Planned, sch_SPI; on the Cost sheet evm_BAC, evm_EV, evm_CPI, evm_EAC ...
Task columns | tsk_ID, tsk_UID, tsk_WBS, tsk_Name, tsk_Duration, tsk_PlanStart, tsk_FcFinish, tsk_Status, tsk_Resource, tsk_Work, tsk_Stage ... each is Tasks[Column], so it grows with the table. Other sheets read Tasks only through these names.
Key formulas | Calculated start = WORKDAY.INTL(MIN(MAX(ProjectStart, [@_ConstraintLow], predecessor drivers), [@_ConstraintHigh]) - 1, 1, WorkWeek, Holidays). Predecessor driver (FS) = WORKDAY.INTL(OFFSET(Tasks[[#Headers],[_LeafCalcFinish]], [@_Pred1Pos], 0), 1 + Lag, WorkWeek, Holidays). Planned Start = Baseline Start if set, else calculated. Summary start = MIN(INDEX(Tasks[_LeafCalcStart], [@_Row]+1):INDEX(Tasks[_LeafCalcStart], [@_Row]+[@_Descendants])), where _Descendants = COUNTIF(Tasks[WBS], [@WBS] & ".*").
Project Planner template 1.2 - Excel 2019 or Microsoft 365, desktop, web and iPhone. No macros.

## Status
Customer Portal Implementation - Status
Project manager: Priya Sharma Forecast finish Thu 29-Oct-2026 (+4 working days vs plan)
| THIS WEEK | Every reporting date, top to bottom
| 1. Status date | 2026-10-25 | Type the reporting date (Ctrl+; = today)
| 2. Progress | On Tasks: the Stage, Actual Start and Actual Finish for the tasks that moved. Go to Tasks.
| 4. RAG | Review the RAG below; where you disagree, pick a PM RAG and say why in Comment.
| 5. Commentary | Write this period's notes in the COMMENTARY table below.
| Area | Measure | Value | Calculated | PM RAG | RAG | Comment
| Overall | Worst of the areas below | 0 red, 3 amber | Amber |  | Amber
| Area | Measure | Value | Calculated | PM RAG | RAG | Comment
| Schedule | Forecast finish vs plan (working days) | 4 | Amber |  | Amber
| Schedule performance | SPI = progress / progress planned by now (duration-weighted) | 0.9051 | Amber |  | Amber
| Deadlines | Tasks forecast to miss their deadline | 0 | Green |  | Green
| Critical path | Critical tasks forecast to finish late | 3 | Amber |  | Amber
| Plan quality | Ignored links and outline errors (see Tasks) | 0 | Green |  | Green
SUMMARY (automatic: copy it into the commentary below and add the why)
Overall AMBER. Forecast finish 29-Oct-2026, 4 working days later than planned. Progress 91% against 100% planned. 3 tasks late. Next milestone: Go-live on 29-Oct.
KEY FIGURES
| Measure | Source | Value | Status | Count
| Planned start | Tasks | 2026-09-07 | Complete | 6
| Planned finish | Tasks (the baseline once it is set) | 2026-10-23 | In Progress | 0
| Forecast finish | Tasks | 2026-10-29 | Behind | 1
| Overall progress (duration-weighted) | Tasks | 90.51% | Late Start | 2
| Planned progress by status date | Tasks | 100% | Not Started | 0
| Schedule performance (SPI) | Progress / planned progress | 0.9051
| Detail tasks | Tasks | 9
| Milestones | Tasks | 3
| Total work (hrs) | Tasks | 340
| Baseline | Tasks > BASELINE | Set on 12 tasks
| Open critical tasks | Tasks | 3
| Tasks with issues (see Tasks > Issues) | Tasks > Issues | 1
| Finish P50 (three-point estimates) | Tasks > ESTIMATES | 2026-10-27
| Finish P80 (three-point estimates) | Tasks > ESTIMATES | 2026-10-28
| Next milestones (forecast) | Forecast date
| Go-live | 2026-10-29
LATE TASKS (most days late first): 3
_Task | Task | Resources | Finish | Finish Var | Status | Critical
10 | System integration testing | Taylor Morgan, Sam Rivera[50%] | 2026-10-28 | 4 | Behind | Yes
11 | Go-live readiness review | Priya Sharma | 2026-10-29 | 4 | Late Start | Yes
12 | Go-live |  | 2026-10-29 | 4 | Late Start | Yes
DUE BY FRI 06-NOV: 3
_Task | Task | Resources | Finish | Progress | Deadline Check | Critical
10 | System integration testing | Taylor Morgan, Sam Rivera[50%] | 2026-10-28 | 85% |  | Yes
11 | Go-live readiness review | Priya Sharma | 2026-10-29 | 0% |  | Yes
12 | Go-live |  | 2026-10-29 | 0% | OK | Yes
STARTING BY FRI 06-NOV (look-ahead 10 working days): 2
_Task | Task | Resources | Start | Duration | Predecessors | Critical
11 | Go-live readiness review | Priya Sharma | 2026-10-29 | 1 | 10 | Yes
12 | Go-live |  | 2026-10-29 | 0 | 11 | Yes
OPEN CRITICAL TASKS (by start): 3
_Task | Task | Resources | Start | Total Slack | Deadline Check | Finish
10 | System integration testing | Taylor Morgan, Sam Rivera[50%] | 2026-10-07 | 0 |  | 2026-10-28
11 | Go-live readiness review | Priya Sharma | 2026-10-29 | 0 |  | 2026-10-29
12 | Go-live |  | 2026-10-29 | 0 | OK | 2026-10-29
COMMENTARY for this period (type in the Notes column)
| Section | Notes
Summary
Achievements this period
Planned for next period
Issues and escalations
Decisions needed
Risks to watch
Formulas:
Value = IF(LateTasks[[#This Row],[_Task]]="","",IF(N(INDEX(tsk_FcFinish,LateTasks[[#This Row],[_Task]]))=0,"",INDEX(tsk_FcFinish,LateTasks[[#This Row],[_Task]])))
Value = IF(DueSoon[[#This Row],[_Task]]="","",IF(N(INDEX(tsk_FcFinish,DueSoon[[#This Row],[_Task]]))=0,"",INDEX(tsk_FcFinish,DueSoon[[#This Row],[_Task]])))
Measure = IFERROR(INDEX(tsk_FcFinish,MATCH(SMALL(tsk_MilestoneKey,(ROW()-ROW(NextMilestones[[#Headers],[Next milestones (forecast)]]))),tsk_MilestoneKey,0)),"")
RAG = IF(CriticalTasks[[#This Row],[_Task]]="","",IF(N(INDEX(tsk_FcFinish,CriticalTasks[[#This Row],[_Task]]))=0,"",INDEX(tsk_FcFinish,CriticalTasks[[#This Row],[_Task]])))
Note on A52: Row of the task in the Tasks table (helper, hidden).
Note on A60: Row of the task in the Tasks table (helper, hidden).
Note on A68: Row of the task in the Tasks table (helper, hidden).
Note on A76: Row of the task in the Tasks table (helper, hidden).
Note on E13: RAG from the thresholds on Settings (RAGAmberSlipDays, RAGRedSlipDays, RAGAmberIndex, RAGRedIndex).
Note on E16: RAG from the thresholds on Settings (RAGAmberSlipDays, RAGRedSlipDays, RAGAmberIndex, RAGRedIndex).
Note on F13: Optional override by the project manager: Green, Amber or Red.
Note on F16: Optional override by the project manager: Green, Amber or Red.
Note on G13: Reported RAG: the PM override if there is one, otherwise the calculated RAG.
Note on G16: Reported RAG: the PM override if there is one, otherwise the calculated RAG.
Note on H13: Why: especially when the PM RAG differs from the calculated one.
Note on H16: Why: especially when the PM RAG differs from the calculated one.

## Roadmap
Customer Portal Implementation - Roadmap
Status date 25-Oct-2026 Forecast finish 29-Oct-2026 (+4 working days vs plan)
[16 empty] | 2026 |  |  |  | 2027 | [11 empty] | 2028
[16 empty] | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2028-01-01 | 2028-02-01
Phases: 3
| _Task | WBS | Phase | Owner | Planned Start | Planned Finish | Start | Finish | Progress | Finish Var | Tasks Done | RAG | Next Milestone | Link | _Milestone
| 1 | 1 | Initiation | Priya Sharma | 2026-09-07 | 2026-09-11 | 2026-09-07 | 2026-09-14 | 100% | 1 | 2 of 2 done | Green |  | Go to phase
| 5 | 2 | Requirements & Design | Morgan Patel | 2026-09-14 | 2026-10-01 | 2026-09-15 | 2026-10-06 | 100% | 3 | 2 of 2 done | Amber |  | Go to phase
| 9 | 3 | Test & Release | Taylor Morgan | 2026-10-02 | 2026-10-23 | 2026-10-07 | 2026-10-29 | 79.19% | 4 | 0 of 2 done | Amber | Go-live (29-Oct) | Go to phase | 12
Milestones (in planned order): 3
| _Task | WBS | Milestone | Planned | Deadline | Forecast | Deadline Check | Status | Finish Var
| 4 | 1.3 | Kickoff complete | 2026-09-11 |  | 2026-09-14 |  | Complete | 1
| 8 | 2.3 | Design sign-off | 2026-10-01 |  | 2026-10-06 |  | Complete | 3
| 12 | 3.3 | Go-live | 2026-10-23 | 2026-12-18 | 2026-10-29 | OK | Late Start | 4
|  |  | Forecast |  | Done |  | Late vs plan |  | Planned (outline)
|  |  | Milestone |  | Deadline missed |  | Status date month
Months: Settings > RoadmapStart. Lists: drag a table's corner down for more rows. The timeline is conditional formatting only.
Formulas:
Planned Start = IF(RoadmapPhases[[#This Row],[_Task]]="","",IF(N(INDEX(tsk_PlanStart,RoadmapPhases[[#This Row],[_Task]]))=0,"",INDEX(tsk_PlanStart,RoadmapPhases[[#This Row],[_Task]])))
Planned Start = IF(RoadmapMilestones[[#This Row],[_Task]]="","",IF(N(INDEX(tsk_Deadline,RoadmapMilestones[[#This Row],[_Task]]))=0,"",INDEX(tsk_Deadline,RoadmapMilestones[[#This Row],[_Task]])))
Planned Finish = IF(RoadmapPhases[[#This Row],[_Task]]="","",IF(N(INDEX(tsk_PlanFinish,RoadmapPhases[[#This Row],[_Task]]))=0,"",INDEX(tsk_PlanFinish,RoadmapPhases[[#This Row],[_Task]])))
Planned Finish = IF(RoadmapMilestones[[#This Row],[_Task]]="","",IF(N(INDEX(tsk_FcFinish,RoadmapMilestones[[#This Row],[_Task]]))=0,"",INDEX(tsk_FcFinish,RoadmapMilestones[[#This Row],[_Task]])))
Start = IF(RoadmapPhases[[#This Row],[_Task]]="","",IF(N(INDEX(tsk_FcStart,RoadmapPhases[[#This Row],[_Task]]))=0,"",INDEX(tsk_FcStart,RoadmapPhases[[#This Row],[_Task]])))
Finish = IF(RoadmapPhases[[#This Row],[_Task]]="","",IF(N(INDEX(tsk_FcFinish,RoadmapPhases[[#This Row],[_Task]]))=0,"",INDEX(tsk_FcFinish,RoadmapPhases[[#This Row],[_Task]])))
Owner = IF(RoadmapMilestones[[#This Row],[_Task]]="","",IF(N(INDEX(tsk_PlanFinish,RoadmapMilestones[[#This Row],[_Task]]))=0,"",INDEX(tsk_PlanFinish,RoadmapMilestones[[#This Row],[_Task]])))
Note on B7: Row of the task in the Tasks table (helper, hidden).
Note on B20: Row of the task in the Tasks table (helper, hidden).
Note on L7: Detail tasks complete out of the phase's tasks (milestones left out). Progress weighs them by duration.
Note on M7: From the phase's finish slip against its planned finish (Settings > RAG slip thresholds).
Note on N7: The phase's earliest milestone not yet done, with its forecast date.
Note on O7: Jumps to the phase's row on Tasks.
Note on P7: Row on Tasks of the phase's next milestone (smallest open milestone key in the phase).

## Settings
Project Settings
Blue = edit me. Grey = calculated. Column D shows the defined name every formula uses for that setting. The settings every plan needs are on the Start sheet.
| Setting | Value | Named range | Notes | Dropdown lists (+) | Link Type | Task Mode | Working Week | Constraint | Yes / No | Resource Type | Gantt Days per Column | RAG | Log Type | RAID Status | Decision Status | Change Status | Project Type | Sprint Length | Amber Slip | Red Slip | Stage 1 | Stage 2 | Stage 3 | Stage 4 | Stage 5 | Stage 6 | % 1 | % 2 | % 3 | % 4 | % 5 | % 6
| Project start (in use) | 2026-09-07 | ProjectStart | Copy of the date above (dates show as 1900 until it is entered). |  | FS | Auto | Mon-Fri | As Soon As Possible | Yes | Work | 1 | Green | Risk | Open | Proposed | Submitted | Software / Agile | 14 | 3 | 10 | Not Started | Design | In Development | Test Ready | In Testing | Complete | 0% | 15% | 40% | 70% | 85% | 100%
| Status date (in use) | 2026-10-25 | StatusDate | The project start until a status date is entered. Drives Status, the red status-date line on the Gantt and rescheduling of late work. |  | SS | Manual | Sun-Thu | As Late As Possible | No | Material | 7 | Amber | Assumption | In Progress | Approved | Under Review | Construction | 28 | 5 | 15 | Not Started | Mobilised | Under Way | Inspection | Snagging | Complete | 0% | 10% | 50% | 85% | 95% | 100%
| First working day on/after status date | 2026-10-26 | StatusWorkday |  |  | FF |  | Mon-Sat | Must Start On |  | Cost | 30 | Red | Issue | Closed | Rejected | Approved | IT infrastructure | 14 | 2 | 5 | Not Started | Design | Build | Testing | Cutover | Complete | 0% | 15% | 50% | 80% | 95% | 100%
| Reschedule incomplete work after status date? | Yes | RescheduleAfterStatus | Yes = like MS Project 'move incomplete parts after status date': unstarted tasks can't start before the status date and in-progress tasks finish their remaining duration after it, pushing all successors. |  | SF |  | Custom | Must Finish On |  |  | 91 |  | Dependency |  | Superseded | Rejected
| Default assignment units | 100% | DefaultUnits | Used when a task has a resource but Units is blank. 100% = full time. |  |  |  |  | Start No Earlier Than |  |  |  |  | Decision |  |  | Implemented
| Monday is a working day | Yes | WorkMon | Used when Working week (Start sheet) is Custom: Yes / No for each day. |  |  |  |  | Start No Later Than |  |  |  |  | Change
| Tuesday is a working day | Yes | WorkTue | [5 empty] | Finish No Earlier Than
| Wednesday is a working day | Yes | WorkWed | [5 empty] | Finish No Later Than
| Thursday is a working day | Yes | WorkThu
| Friday is a working day | Yes | WorkFri |  |  | Dropdown sources. Add a value by typing it in the row under a list: the table and its named range grow.
| Saturday is a working day | No | WorkSat
| Sunday is a working day | No | WorkSun
| Weekend mask (calculated) | 0000011 | WorkWeek | 7-character Mon..Sun string used by WORKDAY.INTL (1 = non-working).
| Show the Gantt and Resource Report from | 2026-10-11 | ViewFrom | Defaults to two weeks before the status date (the project start until then). Overwrite with any date to scroll both views at once; GanttStart and ResourceWeekStart below follow it unless you overwrite them.
| Gantt timeline start | 2026-10-05 | GanttStart | Defaults to the Monday of the View from week. Overwrite with any date to scroll the timeline alone.
| Gantt days per column | 1 | GanttPeriod | 1 = daily timeline, 7 = weekly, 30 = monthly (calendar months), 91 = quarterly (calendar quarters).
| Show tasks down to outline level | 9 | OutlineShowLevel | Tasks > Show (DETAIL section) is Yes for rows at this level or above: filter Show = Yes to see only phases (1), phases and tasks (2) ... Reapply the filter (Data > Reapply) after changing it.
| Live resource grids | Yes | LiveGrids | No = the Resource Report's weekly and sprint grids per person (and Tasks > Over-allocated) stop calculating, for fast bulk entry on a big plan; Status says so while they are off. Set Yes afterwards.
| Roadmap first month | 2026-09-01 | RoadmapStart | The Roadmap sheet's first month. Overwrite with the first of any month to scroll it.
| Sprint focus (share of time on delivery) | 80% | FocusFactor | Of each person's available days in a sprint, the share that is delivery (1 person-day = 1 story point); the rest is ceremonies and overhead. A Focus % on Resources overrides it per person (0% = advisory).
| Most people on one task (calculated) | 2 | MaxPeople | Per-resource totals skip the person slots no task uses, so a plan with one person per task stays fast.
| Critical when total slack is at most (days) | 0 | CriticalSlackDays | 0 = only tasks with no slack (or negative slack from a missed deadline) are critical, like MS Project.
| Forecast project finish (calculated) | 2026-10-29 | ProjectFinish | The critical path's backward pass starts here (the detail tasks' early finish).
| Planned project finish (calculated) | 2026-10-23 | PlannedFinish | Baseline finish once a baseline is set.
| Baseline set (calculated) | 1 | BaselineSet | TRUE once any task has a Baseline Start: the Gantt then outlines only the tasks that have one.
| Project finish variance (calculated, working days) | 4 | FinishVarianceDays | Forecast finish minus planned finish. Positive = late.
| Look-ahead window (working days) | 10 | LookaheadDays | Status lists tasks starting or due within this many working days of the status date.
| Look-ahead window ends (calculated) | 2026-11-06 | LookaheadEnd
| RAG: amber when the finish slips by (working days) | 3 | RAGAmberSlipDays | Status sheet thresholds. A finish slip of at least this many working days is amber.
| RAG: red when the finish slips by (working days) | 10 | RAGRedSlipDays | Both slip thresholds default from the Project type (Start); type a number to set your own.
| RAG: amber when SPI or CPI is below | 0.95 | RAGAmberIndex | SPI = earned value / planned value; CPI = earned value / actual cost. 1.00 = on plan.
| RAG: red when SPI or CPI is below | 0.85 | RAGRedIndex
| RAID: high rating from score | 15 | RAIDHighScore | Score = probability x impact (1-25). At or above this a risk or issue is rated High.
| RAID: medium rating from score | 8 | RAIDMediumScore
| Resource Report first week | 2026-10-05 | ResourceWeekStart | Defaults to the Monday of the View from week. Overwrite with any Monday to scroll the weekly grids alone.
| Next free task UID (calculated) | 214 | NextFreeUID | Give a newly inserted task row this UID (see Start > Inserting tasks).
| Re-baseline every task (BL Source) | No | TakeBaseline | No = the BL Source columns keep each task's pasted baseline and give the current dates only to tasks without one: copy BL Source and Paste Values onto Baseline to baseline new tasks. Yes = BL Source is the current schedule for every task: the same copy and paste re-baselines the whole plan. Set it back to No afterwards.
| Tasks sharing a UID (calculated) | 0 | DuplicateUIDs | Should be 0. Each such task says so in Tasks > Issues; give one of them Settings > NextFreeUID.
| Named tasks without a UID (calculated) | 0 | MissingUIDs | Should be 0: links can't point at a task without a UID.
| Sandbox: use the Sandbox Durations (what-if) | No | Sandbox | Yes = every task with a Sandbox Duration (Tasks > ESTIMATES and SANDBOX) uses it instead of its Duration, and the whole plan, Status and the reports show the what-if. Status and Check say so. Set No to go back.
| Finish P50, from the estimates (calculated) | 2026-10-27 | PertP50 | Forecast finish moved by the critical tasks' Expected - Duration: a 50% chance of finishing by then.
| Finish P80, from the estimates (calculated) | 2026-10-28 | PertP80 | Adds 0.84 standard deviations (the critical tasks' variances added up): an 80% chance of finishing by then.
STAGES: pick one per task on Tasks > Stage; its % Complete counts as the task's progress (a typed % Complete overrides it).
| Stage | % Complete
| Not Started | 0%
| Design | 15%
| In Development | 40%
| Test Ready | 70%
| In Testing | 85%
| Complete | 100%
HOLIDAYS: every date here is skipped by all scheduling formulas (named range: Holidays). Add rows to the table as needed.
| Date | Description
| 2026-12-24 | Christmas Eve (example - replace with your calendar)
| 2026-12-25 | Christmas Day (example)
| 2026-12-31 | New Year's Eve (example)
| 2027-01-01 | New Year's Day (example)

## Tasks
Customer Portal Implementation - Task Entry | [215 empty] | Planned (outline) | [10 empty] | Done (% complete) | [10 empty] | Remaining - on track | [10 empty] | Slip: past the planned finish | [10 empty] | Remaining - critical | [10 empty] | Planned, no work now
Type in BLUE columns only. Level = outline level (1 = phase, 2 = task, 3 = sub-task). Predecessors refer to the UID column. Fix anything in Issues (red). More columns (scheduling, detail, work, agile, baseline): click + above a section. The Gantt timeline is to the right of the table. Insert rows inside the table, or paste rows under the last task: formulas fill in automatically. | [215 empty] | Summary (forecast) | [10 empty] | Milestone (forecast) | [10 empty] | Deadline | [10 empty] | Status date | [10 empty] | Non-working day
Next free UID for a new row: 214 | [25 empty] | Gantt timeline >> | [188 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W
PLAN: type or pick in the blue columns |  |  |  |  | PREDECESSORS: pick |  | + links 2-4, text | [10 empty] | RESOURCES: pick | + people 2-4, text | [7 empty] | PROGRESS | [7 empty] | SCHEDULING |  |  |  | DETAIL | [16 empty] | WORK |  |  |  | AGILE |  | BASELINE | [9 empty] | RACI |  |  | ESTIMATES (PERT) and SANDBOX |  |  |  | HELPER COLUMNS (hidden) | [135 empty] | M: Oct 26; Deadline S: Nov 26; Non-working day T: Dec 26; Non-working day F: Jan 27; Non-working day M: Feb 27; Non-working day M: Mar 27
ID | UID | Level | Task Name | Duration | Pred1 | Type1 | Lag1 | Pred2 | Type2 | Lag2 | Pred3 | Type3 | Lag3 | Pred4 | Type4 | Lag4 | Predecessors | Res1 | Units1 | Res2 | Units2 | Res3 | Units3 | Res4 | Units4 | Resources | Stage | Actual Start | Actual Finish | Start | Finish | Sprint | Notes | Issues | Deadline | Mode | Constraint | Constraint Date | Finish Var | Status | Critical | Planned Start | Planned Finish | Start Var | Late Start | Late Finish | Total Slack | Free Slack | Deadline Check | Link Check | % Complete | Progress | Predecessors by ID | WBS | Show | Work | Owner | Resource Names | Over-allocated | Story Points | Planned Sprint | Duration Var | Work Var | BL Source Start | BL Source Finish | BL Source Duration | BL Source Work | Baseline Start | Baseline Finish | Baseline Duration | Baseline Work | Accountable | Consulted | Informed | Expected | Optimistic | Pessimistic | Sandbox Duration | _Level | _Row | _ParentRow | _NextLevel | _IsSummary | _Descendants | _IsLeaf | _Pred1Pos | _Pred2Pos | _Pred3Pos | _Pred4Pos | _ConstraintCode | _ConstraintStart | _ConstraintLow | _ConstraintHigh | _LeafCalcStart | _LeafCalcFinish | _LeafFcstStart | _LeafFcstFinish | _Pred1Text | _Pred1UID | _Pred1Type | _Pred1Lag | _Pred2Text | _Pred2UID | _Pred2Type | _Pred2Lag | _Pred3Text | _Pred3UID | _Pred3Type | _Pred3Lag | _Pred4Text | _Pred4UID | _Pred4Type | _Pred4Lag | _Res1Text | _Res2Text | _Res3Text | _Res4Text | _Res1Row | _Res2Row | _Res3Row | _Res4Row | _Resource1 | _Units1 | _People | _Res2 | _Res2Units | _Res2Work | _Res2WorkPerWD | _Res2WorkBefore | _Res2WorkDone | _Res3 | _Res3Units | _Res3Work | _Res3WorkPerWD | _Res3WorkBefore | _Res3WorkDone | _Res4 | _Res4Units | _Res4Work | _Res4WorkPerWD | _Res4WorkBefore | _Res4WorkDone | _Pct | _LeafProgress | _LeafWork | _LeafTotalWork | _Pred1FinishKey | _Pred2FinishKey | _Pred3FinishKey | _Pred4FinishKey | _Pred1SlackKey | _Pred2SlackKey | _Pred3SlackKey | _Pred4SlackKey | _LastSuccessorRow | _SuccessorFinishLimit | _LeafLateFinish | _LeafLateStart | _LeafTotalSlack | _LeafCritical | _AlapShift | _ShownCalcStart | _ShownCalcFinish | _ShownFcstStart | _ShownFcstFinish | _CalcStart | _CalcFinish | _Pred1Problem | _Pred2Problem | _Pred3Problem | _Pred4Problem | _Pred1PlanDriver | _Pred2PlanDriver | _Pred3PlanDriver | _Pred4PlanDriver | _Pred1FcstDriver | _Pred2FcstDriver | _Pred3FcstDriver | _Pred4FcstDriver | _StartWorkday | _FinishWorkday | _WorkPerWorkday | _WorkBeforeStart | _WeightDur | _WeightDone | _WeightPlanned | _UIDPredecessors | _MilestoneKey | _PlannedPct | _Phase | _PhaseKey | _MilestoneOrder | _LateKey | _StartSoonKey | _DueSoonKey | _CriticalKey | _LeafWorkDone | _DoneDate | _LeafPoints | _CurrentSprintKey | _IsMilestone | _DoneFrom | _DoneTo | _RemFrom | _RemTo | _ShowPlan | _Days | _Predecessors | _Resources | _PickKey | _PickList | _SpanDays | _PertVariance | _PertShift | time axis 2026-10-05 to 2027-03-03
1 | 1 | 1 | Initiation | [26 empty] | 2026-09-07 | 2026-09-14 |  | Phase 1 - summary rows roll up dates, work, cost and progress automatically. |  |  | Auto |  |  | 1 | Complete |  | 2026-09-07 | 2026-09-11 | 0 | 2026-09-11 | 2026-09-17 | 3 |  |  |  |  | 100% |  | 1 | Yes | 40 | Priya Sharma |  |  |  |  | 1 | 0 | 2026-09-07 | 2026-09-11 | 5 | 40 | 2026-09-07 | 2026-09-11 | 5 | 40 | [7 empty] | 1 | 1 | 0 | 2 | TRUE | 3 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 |  |  |  |  | 2026-09-07 | 2026-09-11 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 1 | 1 | [5 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | TRUE |  |  |  |  | 2 Project charter & scope statement | 6 | 0 | 0
2 | 2 | 2 | Project charter & scope statement | 3 | [13 empty] | Priya Sharma | [8 empty] | Complete | 2026-09-07 | 2026-09-10 | 2026-09-07 | 2026-09-10 |  | Took 1 extra day for sponsor sign-off. |  |  | Auto |  |  | 1 | Complete |  | 2026-09-07 | 2026-09-09 | 0 | 2026-09-11 | 2026-09-15 | 3 | 0 |  |  |  | 100% |  | 1.1 | Yes | 24 |  | Priya Sharma |  |  |  | 0 | 0 | 2026-09-07 | 2026-09-09 | 3 | 24 | 2026-09-07 | 2026-09-09 | 3 | 24 | Priya Sharma | Morgan Patel | Steering committee |  |  |  |  | 2 | 2 | 6 | 2 | FALSE | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2958465 | 2026-09-07 | 2026-09-09 | 2026-09-07 | 2026-09-10 | [16 empty] | Priya Sharma |  |  |  | 1 | 0 | 0 | 0 | Priya Sharma |  | 1 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 100% | 1 | 24 | 24 | [8 empty] | 3 | 2026-09-15 | 2026-09-15 | 2026-09-11 | 3 | FALSE | 0 | 2026-09-07 | 2026-09-09 | 2026-09-07 | 2026-09-10 | 2026-09-07 | 2026-09-09 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 6 | 0 | 3 | 3 | 3 |  |  | 1 | 1 | [6 empty] | 24 | 2026-09-10 | 0 |  | FALSE | 2026-09-07 | 2026-09-10 | 0 | 0 | TRUE | 3 |  | Priya Sharma | 2 | 3 Stakeholder kickoff workshop | 3 | 0 | 0
3 | 3 | 2 | Stakeholder kickoff workshop | 2 | 2 | [12 empty] | Morgan Patel | [8 empty] | Complete | 2026-09-11 | 2026-09-14 | 2026-09-11 | 2026-09-14 |  |  |  |  | Auto |  |  | 1 | Complete |  | 2026-09-10 | 2026-09-11 | 1 | 2026-09-16 | 2026-09-17 | 3 | 0 |  |  |  | 100% | 2 | 1.2 | Yes | 16 |  | Morgan Patel |  |  |  | 0 | 0 | 2026-09-10 | 2026-09-11 | 2 | 16 | 2026-09-10 | 2026-09-11 | 2 | 16 | [7 empty] | 2 | 3 | 6 | 2 | FALSE | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2958465 | 2026-09-10 | 2026-09-11 | 2026-09-11 | 2026-09-14 | 2 | 2 | FS | 0 | [12 empty] | Morgan Patel |  |  |  | 2 | 0 | 0 | 0 | Morgan Patel |  | 1 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 100% | 1 | 16 | 16 | 2912185 |  |  |  | 100000 |  |  |  | 4 | 2026-09-17 | 2026-09-17 | 2026-09-16 | 3 | FALSE | 0 | 2026-09-10 | 2026-09-11 | 2026-09-11 | 2026-09-14 | 2026-09-10 | 2026-09-11 |  |  |  |  | 2026-09-10 | 0 | 0 | 0 | 2026-09-11 | 0 | 0 | 0 | 5 | 6 | 8 | 32 | 2 | 2 | 2 | 2 |  | 1 | 1 | [6 empty] | 16 | 2026-09-14 | 0 |  | FALSE | 2026-09-11 | 2026-09-14 | 0 | 0 | TRUE | 2 | 2 | Morgan Patel | 3 | 4 Kickoff complete | 2 | 0 | 0
4 | 4 | 2 | Kickoff complete | 0 | 3 | [21 empty] | Complete | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 |  | Milestone (Duration 0). |  |  | Auto |  |  | 1 | Complete |  | 2026-09-11 | 2026-09-11 | 1 | 2026-09-17 | 2026-09-17 | 3 | 0 |  |  |  | 100% | 3 | 1.3 | Yes | 0 | [5 empty] | 0 | 0 | 2026-09-11 | 2026-09-11 | 0 | 0 | 2026-09-11 | 2026-09-11 | 0 | 0 | [7 empty] | 2 | 4 | 6 | 1 | FALSE | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2958465 | 2026-09-11 | 2026-09-11 | 2026-09-14 | 2026-09-14 | 3 | 3 | FS | 0 | [16 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 100% | 1 | 0 | 0 | 2912183 |  |  |  | 100000 |  |  |  | 6 | 2026-09-17 | 2026-09-17 | 2026-09-17 | 3 | FALSE | 0 | 2026-09-11 | 2026-09-11 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 |  |  |  |  | 2026-09-11 | 0 | 0 | 0 | 2026-09-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 3 |  | 1 | 1 |  | 2026-09-11 |  |  |  |  | 0 | 2026-09-14 | 0 |  | TRUE | 0 | 0 | 0 | 0 | TRUE | 0 | 3 |  | 4 | 6 Requirements gathering | 0 | 0 | 0
5 | 5 | 1 | Requirements & Design | [26 empty] | 2026-09-15 | 2026-10-06 |  |  |  |  | Auto |  |  | 3 | Complete |  | 2026-09-14 | 2026-10-01 | 1 | 2026-09-18 | 2026-10-07 | 1 |  |  |  |  | 100% |  | 2 | Yes | 112 | Morgan Patel |  |  |  |  | 2 | 0 | 2026-09-14 | 2026-10-01 | 14 | 112 | 2026-09-14 | 2026-10-01 | 14 | 112 | [7 empty] | 1 | 5 | 0 | 2 | TRUE | 3 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 |  |  |  |  | 2026-09-14 | 2026-10-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 2 | 5 | [5 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | TRUE |  |  |  |  | 8 UX wireframes & prototype | 16 | 0 | 0
6 | 6 | 2 | Requirements gathering | 8 | 4 | [12 empty] | Morgan Patel | [8 empty] | Complete | 2026-09-15 | 2026-09-25 | 2026-09-15 | 2026-09-25 |  |  |  |  | Auto |  |  | 2 | Complete |  | 2026-09-14 | 2026-09-23 | 1 | 2026-09-18 | 2026-09-29 | 2 | 0 |  |  |  | 100% | 4 | 2.1 | Yes | 64 |  | Morgan Patel |  |  |  | 0 | 0 | 2026-09-14 | 2026-09-23 | 8 | 64 | 2026-09-14 | 2026-09-23 | 8 | 64 | [7 empty] | 2 | 6 | 10 | 2 | FALSE | 0 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2958465 | 2026-09-14 | 2026-09-23 | 2026-09-15 | 2026-09-25 | 4 | 4 | FS | 0 | [12 empty] | Morgan Patel |  |  |  | 2 | 0 | 0 | 0 | Morgan Patel |  | 1 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 100% | 1 | 64 | 64 | 2912183 |  |  |  | 100000 |  |  |  | 7 | 2026-09-29 | 2026-09-29 | 2026-09-18 | 2 | FALSE | 0 | 2026-09-14 | 2026-09-23 | 2026-09-15 | 2026-09-25 | 2026-09-14 | 2026-09-23 |  |  |  |  | 2026-09-14 | 0 | 0 | 0 | 2026-09-15 | 0 | 0 | 0 | 7 | 15 | 7.1111 | 42.6667 | 8 | 8 | 8 | 4 |  | 1 | 2 | [6 empty] | 64 | 2026-09-25 | 0 |  | FALSE | 2026-09-15 | 2026-09-25 | 0 | 0 | TRUE | 8 | 4 | Morgan Patel | 6 | 9 Design sign-off | 8 | 0 | 0
7 | 8 | 2 | UX wireframes & prototype | 6 | 6 | [12 empty] | Casey Kim | [8 empty] | Complete | 2026-09-28 | 2026-10-06 | 2026-09-28 | 2026-10-06 |  |  |  |  | Auto |  |  | 3 | Complete |  | 2026-09-24 | 2026-10-01 | 2 | 2026-09-30 | 2026-10-07 | 1 | 0 |  |  |  | 100% | 6 | 2.2 | Yes | 48 |  | Casey Kim |  |  |  | 0 | 0 | 2026-09-24 | 2026-10-01 | 6 | 48 | 2026-09-24 | 2026-10-01 | 6 | 48 | [7 empty] | 2 | 7 | 10 | 2 | FALSE | 0 | 1 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 2958465 | 2026-09-24 | 2026-10-01 | 2026-09-28 | 2026-10-06 | 6 | 6 | FS | 0 | [12 empty] | Casey Kim |  |  |  | 4 | 0 | 0 | 0 | Casey Kim |  | 1 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 100% | 1 | 48 | 48 | 2912171 |  |  |  | 100000 |  |  |  | 8 | 2026-10-07 | 2026-10-07 | 2026-09-30 | 1 | FALSE | 0 | 2026-09-24 | 2026-10-01 | 2026-09-28 | 2026-10-06 | 2026-09-24 | 2026-10-01 |  |  |  |  | 2026-09-24 | 0 | 0 | 0 | 2026-09-28 | 0 | 0 | 0 | 16 | 22 | 6.8571 | 102.8571 | 6 | 6 | 6 | 6 |  | 1 | 2 | [6 empty] | 48 | 2026-10-06 | 0 |  | FALSE | 2026-09-28 | 2026-10-06 | 0 | 0 | TRUE | 6 | 6 | Casey Kim | 7 | 21 System integration testing | 6 | 0 | 0
8 | 9 | 2 | Design sign-off | 0 | 8 | [21 empty] | Complete | 2026-10-06 | 2026-10-06 | 2026-10-06 | 2026-10-06 |  | Two predecessors - waits for the later one. |  |  | Auto |  |  | 3 | Complete |  | 2026-10-01 | 2026-10-01 | 3 | 2026-10-07 | 2026-10-07 | 1 | 0 |  |  |  | 100% | 7 | 2.3 | Yes | 0 | [5 empty] | 0 | 0 | 2026-10-01 | 2026-10-01 | 0 | 0 | 2026-10-01 | 2026-10-01 | 0 | 0 | [7 empty] | 2 | 8 | 10 | 1 | FALSE | 0 | 1 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 2958465 | 2026-10-01 | 2026-10-01 | 2026-10-06 | 2026-10-06 | 8 | 8 | FS | 0 | [16 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 100% | 1 | 0 | 0 | 2912163 |  |  |  | 100000 |  |  |  | 10 | 2026-10-07 | 2026-10-07 | 2026-10-07 | 1 | FALSE | 0 | 2026-10-01 | 2026-10-01 | 2026-10-06 | 2026-10-06 | 2026-10-01 | 2026-10-01 |  |  |  |  | 2026-10-01 | 0 | 0 | 0 | 2026-10-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 8 |  | 1 | 2 |  | 2026-10-01 |  |  |  |  | 0 | 2026-10-06 | 0 |  | TRUE | 0 | 0 | 0 | 0 | TRUE | 0 | 8 |  | 8 | 24 Go-live readiness review | 0 | 0 | 0
9 | 20 | 1 | Test & Release | [26 empty] | 2026-10-07 | 2026-10-29 |  |  |  |  | Auto |  |  | 4 | Behind | Yes | 2026-10-02 | 2026-10-23 | 3 | 2026-10-08 | 2026-10-29 | 0 |  |  |  |  | 79.19% |  | 3 | Yes | 188 | Taylor Morgan |  |  |  |  | 1 | 60 | 2026-10-02 | 2026-10-23 | 16 | 128 | 2026-10-02 | 2026-10-23 | 16 | 128 | [7 empty] | 1 | 9 | 0 | 2 | TRUE | 3 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 |  |  |  |  | 2026-10-02 | 2026-10-23 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 3 | 9 | [5 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | TRUE |  |  |  |  | 25 Go-live | 17 | 0 | 0
10 | 21 | 2 | System integration testing | 15 | 9 | [12 empty] | Taylor Morgan |  | Sam Rivera | 50% | [5 empty] | In Testing | 2026-10-07 |  | 2026-10-07 | 2026-10-28 |  | Started a few days late; on track. | Optimistic should be at most the Duration and Pessimistic at least it. |  | Auto |  |  | 4 | Behind | Yes | 2026-10-02 | 2026-10-22 | 3 | 2026-10-08 | 2026-10-28 | 0 | 0 |  |  |  | 85% | 8 | 3.1 | Yes | 180 |  | Taylor Morgan, Sam Rivera[50%] |  |  |  | 0 | 60 | 2026-10-02 | 2026-10-22 | 15 | 120 | 2026-10-02 | 2026-10-22 | 15 | 120 | Taylor Morgan | Jordan Lee, Sam Rivera | Morgan Patel | 13.2 | 6 | 13 |  | 2 | 10 | 14 | 2 | FALSE | 0 | 1 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 2958465 | 2026-10-02 | 2026-10-22 | 2026-10-07 | 2026-10-28 | 9 | 9 | FS | 0 | [12 empty] | Taylor Morgan | Sam Rivera[50%] |  |  | 7 | 6 | 0 | 0 | Taylor Morgan |  | 2 | Sam Rivera | 0.5 | 60 | 3.75 | 82.5 | 51 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 85% | 0.85 | 120 | 180 | 2912163 |  |  |  | 100000 |  |  |  | 11 | 2026-10-28 | 2026-10-28 | 2026-10-08 | 0 | TRUE | 0 | 2026-10-02 | 2026-10-22 | 2026-10-07 | 2026-10-28 | 2026-10-02 | 2026-10-22 |  |  |  |  | 2026-10-02 | 0 | 0 | 0 | 2026-10-07 | 0 | 0 | 0 | 23 | 38 | 7.5 | 165 | 15 | 12.75 | 15 | 9 |  | 1 | 3 |  |  | 5 |  | 2026-10-28 | 2026-10-07 | 102 |  | 0 |  | FALSE | 2026-10-07 | 2026-10-25 | 2026-10-26 | 2026-10-28 | TRUE | 15 | 9 | Taylor Morgan, Sam Rivera[50%] | 10 |  | 15 | 1.3611 | -1.8
11 | 24 | 2 | Go-live readiness review | 1 | 21 | [12 empty] | Priya Sharma | [11 empty] | 2026-10-29 | 2026-10-29 |  | Three predecessors. |  |  | Auto |  |  | 4 | Late Start | Yes | 2026-10-23 | 2026-10-23 | 4 | 2026-10-29 | 2026-10-29 | 0 | 0 |  |  |  | 0% | 10 | 3.2 | Yes | 8 |  | Priya Sharma |  |  |  | 0 | 0 | 2026-10-23 | 2026-10-23 | 1 | 8 | 2026-10-23 | 2026-10-23 | 1 | 8 | [7 empty] | 2 | 11 | 14 | 2 | FALSE | 0 | 1 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 2958465 | 2026-10-23 | 2026-10-23 | 2026-10-29 | 2026-10-29 | 21 | 21 | FS | 0 | [12 empty] | Priya Sharma |  |  |  | 1 | 0 | 0 | 0 | Priya Sharma |  | 1 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 2912142 |  |  |  | 100000 |  |  |  | 12 | 2026-10-29 | 2026-10-29 | 2026-10-29 | 0 | TRUE | 0 | 2026-10-23 | 2026-10-23 | 2026-10-29 | 2026-10-29 | 2026-10-23 | 2026-10-23 |  |  |  |  | 2026-10-23 | 0 | 0 | 0 | 2026-10-29 | 0 | 0 | 0 | 39 | 39 | 8 | 304 | 1 | 0 | 1 | 21 |  | 1 | 3 |  |  | 5 | 2026-10-29 | 2026-10-29 | 2026-10-29 | 0 |  | 0 |  | FALSE | 0 | 0 | 2026-10-29 | 2026-10-29 | TRUE | 1 | 21 | Priya Sharma | 11 |  | 1 | 0 | 0
12 | 25 | 2 | Go-live | 0 | 24 | [24 empty] | 2026-10-29 | 2026-10-29 |  | Milestone with a deadline of 18-Dec. |  | 2026-12-18 | Auto |  |  | 4 | Late Start | Yes | 2026-10-23 | 2026-10-23 | 4 | 2026-10-29 | 2026-10-29 | 0 | 0 | OK |  |  | 0% | 11 | 3.3 | Yes | 0 | [5 empty] | 0 | 0 | 2026-10-23 | 2026-10-23 | 0 | 0 | 2026-10-23 | 2026-10-23 | 0 | 0 | Priya Sharma | Steering committee | All staff |  |  |  |  | 2 | 12 | 14 | 0 | FALSE | 0 | 1 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 2958465 | 2026-10-23 | 2026-10-23 | 2026-10-29 | 2026-10-29 | 24 | 24 | FS | 0 | [16 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2912141 |  |  |  | 100000 |  |  |  | 0 | 2958465 | 2026-10-29 | 2026-10-29 | 0 | TRUE | 0 | 2026-10-23 | 2026-10-23 | 2026-10-29 | 2026-10-29 | 2026-10-23 | 2026-10-23 |  |  |  |  | 2026-10-23 | 0 | 0 | 0 | 2026-10-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0.1 | 24 | 2026-10-29 | 1 | 3 |  | 2026-10-23 | 5 | 2026-10-29 | 2026-10-29 | 2026-10-29 | 0 |  | 0 |  | TRUE | 0 | 0 | 0 | 0 | TRUE | 0 | 24 |  | 12 |  | 0 | 0 | 0
| 26 | [78 empty] | 13 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 27 | [78 empty] | 14 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 28 | [78 empty] | 15 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 29 | [78 empty] | 16 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 30 | [78 empty] | 17 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 31 | [78 empty] | 18 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 32 | [78 empty] | 19 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 33 | [78 empty] | 20 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 34 | [78 empty] | 21 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 35 | [78 empty] | 22 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 36 | [78 empty] | 23 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 37 | [78 empty] | 24 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 38 | [78 empty] | 25 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 39 | [78 empty] | 26 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 40 | [78 empty] | 27 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 41 | [78 empty] | 28 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 42 | [78 empty] | 29 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 43 | [78 empty] | 30 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 44 | [78 empty] | 31 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 45 | [78 empty] | 32 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 46 | [78 empty] | 33 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 47 | [78 empty] | 34 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 48 | [78 empty] | 35 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 49 | [78 empty] | 36 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 50 | [78 empty] | 37 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 51 | [78 empty] | 38 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 52 | [78 empty] | 39 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 53 | [78 empty] | 40 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 54 | [78 empty] | 41 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 55 | [78 empty] | 42 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 56 | [78 empty] | 43 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 57 | [78 empty] | 44 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 58 | [78 empty] | 45 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 59 | [78 empty] | 46 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 60 | [78 empty] | 47 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 61 | [78 empty] | 48 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 62 | [78 empty] | 49 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 63 | [78 empty] | 50 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 64 | [78 empty] | 51 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 65 | [78 empty] | 52 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 66 | [78 empty] | 53 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 67 | [78 empty] | 54 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 68 | [78 empty] | 55 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 69 | [78 empty] | 56 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 70 | [78 empty] | 57 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 71 | [78 empty] | 58 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 72 | [78 empty] | 59 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 73 | [78 empty] | 60 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 74 | [78 empty] | 61 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 75 | [78 empty] | 62 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 76 | [78 empty] | 63 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 77 | [78 empty] | 64 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 78 | [78 empty] | 65 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 79 | [78 empty] | 66 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 80 | [78 empty] | 67 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 81 | [78 empty] | 68 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 82 | [78 empty] | 69 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 83 | [78 empty] | 70 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 84 | [78 empty] | 71 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 85 | [78 empty] | 72 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 86 | [78 empty] | 73 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 87 | [78 empty] | 74 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 88 | [78 empty] | 75 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 89 | [78 empty] | 76 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 90 | [78 empty] | 77 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 91 | [78 empty] | 78 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 92 | [78 empty] | 79 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 93 | [78 empty] | 80 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 94 | [78 empty] | 81 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 95 | [78 empty] | 82 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 96 | [78 empty] | 83 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 97 | [78 empty] | 84 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 98 | [78 empty] | 85 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 99 | [78 empty] | 86 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 100 | [78 empty] | 87 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 101 | [78 empty] | 88 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 102 | [78 empty] | 89 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 103 | [78 empty] | 90 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 104 | [78 empty] | 91 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 105 | [78 empty] | 92 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 106 | [78 empty] | 93 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 107 | [78 empty] | 94 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 108 | [78 empty] | 95 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 109 | [78 empty] | 96 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 110 | [78 empty] | 97 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 111 | [78 empty] | 98 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 112 | [78 empty] | 99 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 113 | [78 empty] | 100 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 114 | [78 empty] | 101 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 115 | [78 empty] | 102 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 116 | [78 empty] | 103 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 117 | [78 empty] | 104 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 118 | [78 empty] | 105 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 119 | [78 empty] | 106 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 120 | [78 empty] | 107 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 121 | [78 empty] | 108 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 122 | [78 empty] | 109 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 123 | [78 empty] | 110 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 124 | [78 empty] | 111 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 125 | [78 empty] | 112 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 126 | [78 empty] | 113 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 127 | [78 empty] | 114 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 128 | [78 empty] | 115 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 129 | [78 empty] | 116 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 130 | [78 empty] | 117 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 131 | [78 empty] | 118 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 132 | [78 empty] | 119 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 133 | [78 empty] | 120 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 134 | [78 empty] | 121 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 135 | [78 empty] | 122 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 136 | [78 empty] | 123 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 137 | [78 empty] | 124 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 138 | [78 empty] | 125 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 139 | [78 empty] | 126 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 140 | [78 empty] | 127 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 141 | [78 empty] | 128 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 142 | [78 empty] | 129 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 143 | [78 empty] | 130 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 144 | [78 empty] | 131 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 145 | [78 empty] | 132 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 146 | [78 empty] | 133 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 147 | [78 empty] | 134 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 148 | [78 empty] | 135 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 149 | [78 empty] | 136 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 150 | [78 empty] | 137 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 151 | [78 empty] | 138 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 152 | [78 empty] | 139 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 153 | [78 empty] | 140 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 154 | [78 empty] | 141 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 155 | [78 empty] | 142 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 156 | [78 empty] | 143 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 157 | [78 empty] | 144 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 158 | [78 empty] | 145 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 159 | [78 empty] | 146 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 160 | [78 empty] | 147 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 161 | [78 empty] | 148 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 162 | [78 empty] | 149 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 163 | [78 empty] | 150 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 164 | [78 empty] | 151 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 165 | [78 empty] | 152 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 166 | [78 empty] | 153 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 167 | [78 empty] | 154 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 168 | [78 empty] | 155 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 169 | [78 empty] | 156 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 170 | [78 empty] | 157 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 171 | [78 empty] | 158 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 172 | [78 empty] | 159 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 173 | [78 empty] | 160 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 174 | [78 empty] | 161 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 175 | [78 empty] | 162 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 176 | [78 empty] | 163 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 177 | [78 empty] | 164 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 178 | [78 empty] | 165 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 179 | [78 empty] | 166 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 180 | [78 empty] | 167 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 181 | [78 empty] | 168 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 182 | [78 empty] | 169 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 183 | [78 empty] | 170 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 184 | [78 empty] | 171 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 185 | [78 empty] | 172 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 186 | [78 empty] | 173 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 187 | [78 empty] | 174 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 188 | [78 empty] | 175 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 189 | [78 empty] | 176 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 190 | [78 empty] | 177 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 191 | [78 empty] | 178 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 192 | [78 empty] | 179 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 193 | [78 empty] | 180 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 194 | [78 empty] | 181 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 195 | [78 empty] | 182 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 196 | [78 empty] | 183 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 197 | [78 empty] | 184 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 198 | [78 empty] | 185 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 199 | [78 empty] | 186 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 200 | [78 empty] | 187 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 201 | [78 empty] | 188 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 202 | [78 empty] | 189 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 203 | [78 empty] | 190 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 204 | [78 empty] | 191 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 205 | [78 empty] | 192 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 206 | [78 empty] | 193 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 207 | [78 empty] | 194 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 208 | [78 empty] | 195 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 209 | [78 empty] | 196 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 210 | [78 empty] | 197 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 211 | [78 empty] | 198 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 212 | [78 empty] | 199 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
| 213 | [78 empty] | 200 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 | [24 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 |  | 0 |  | FALSE | 0 | 0 | 0 | 0 | FALSE | [6 empty] | 0 | 0
Note on A5: Position in the list; renumbers when rows move (like MS Project).
Note on B5: Permanent number that predecessors refer to. Each task needs a different one.
Note on C5: Outline level: 1 = phase, 2 = task, 3 = sub-task ... (at most 1 more than the row above).
Note on E5: Working days. 0 = milestone.
Note on F5: Predecessor 1: pick a task (its UID and name) or type its UID. It must be a detail task above this one.
Note on G5: Link type: FS (blank: finish to start), SS, FF or SF.
Note on H5: Lag in working days (negative = lead). Blank = 0.
Note on I5: Predecessor 2: pick a task (its UID and name) or type its UID. It must be a detail task above this one.
Note on J5: Link type: FS (blank: finish to start), SS, FF or SF.
Note on K5: Lag in working days (negative = lead). Blank = 0.
Note on L5: Predecessor 3: pick a task (its UID and name) or type its UID. It must be a detail task above this one.
Note on M5: Link type: FS (blank: finish to start), SS, FF or SF.
Note on N5: Lag in working days (negative = lead). Blank = 0.
Note on O5: Predecessor 4: pick a task (its UID and name) or type its UID. It must be a detail task above this one.
Note on P5: Link type: FS (blank: finish to start), SS, FF or SF.
Note on Q5: Lag in working days (negative = lead). Blank = 0.
Note on R5: Tasks that must come first, by UID, comma-separated: 12 = after 12 finishes; 12SS+2d = 2 days after 12 starts; FS, SS, FF, SF; lag in working days (- = lead). Up to 4; each must be a detail task above this one.
Note on S5: Person 1 on the task: pick a name from Resources.
Note on T5: Share of their time on this task (blank = Settings > DefaultUnits).
Note on U5: Person 2 on the task: pick a name from Resources.
Note on V5: Share of their time on this task (blank = Settings > DefaultUnits).
Note on W5: Person 3 on the task: pick a name from Resources.
Note on X5: Share of their time on this task (blank = Settings > DefaultUnits).
Note on Y5: Person 4 on the task: pick a name from Resources.
Note on Z5: Share of their time on this task (blank = Settings > DefaultUnits).
Note on AA5: Who does it: names or initials from Resources, comma-separated, with an optional share of their time, e.g. Alex Chen, JL[50%] (blank = DefaultUnits). Up to 4 people.
Note on AB5: Where the task is: Not Started, Design, In Development, Test Ready, In Testing, Complete. Each stage's % Complete is on Settings > Stages.
Note on AE5: Current schedule: actuals where entered, otherwise recalculated from predecessors.
Note on AF5: Current schedule finish.
Note on AG5: Planned Sprint if entered, otherwise the sprint containing the forecast start.
Note on AI5: Everything wrong on this row, in words: links, UID, outline level, resource, over-allocation, missed deadline. Blank = fine.
Note on AJ5: Optional deadline; Deadline Check flags a forecast finish after it.
Note on AK5: Auto = scheduled from predecessors and the constraint. Manual = starts on the Constraint Date (finish constraints: finishes on it).
Note on AL5: MS Project constraint (dropdown). Blank = Start No Earlier Than when a Constraint Date is entered, otherwise As Soon As Possible. Constraint dates win over links.
Note on AM5: Date for the Constraint. Manual tasks are pinned to it.
Note on AN5: Finish minus Planned Finish, in working days.
Note on AP5: Yes when Total Slack <= CriticalSlackDays (Settings) and the task isn't complete.
Note on AQ5: Baseline Start if a baseline is set, otherwise calculated from durations and links.
Note on AR5: Baseline Finish if a baseline is set, otherwise calculated.
Note on AS5: Start minus Planned Start, in working days.
Note on AT5: Latest start that doesn't delay the project finish or a deadline (critical path backward pass).
Note on AU5: Latest finish that doesn't delay the project finish or a deadline.
Note on AV5: Total slack: working days this task can slip before it delays the project or a deadline.
Note on AW5: Free slack: working days it can slip before it delays any successor.
Note on AY5: Explains predecessor links and constraints that are ignored.
Note on AZ5: Optional: overrides the Stage's % (0-100%). Blank = the Stage's %. An Actual Finish counts as 100%.
Note on BA5: The Stage's % (or the % Complete override), rolled up to summaries (duration-weighted).
Note on BB5: Predecessors in MS Project notation, by ID.
Note on BC5: Outline number, generated from Level.
Note on BD5: Yes when Level <= Settings > OutlineShowLevel: filter on Yes to collapse the outline to that level (or use the 1 2 3 outline buttons at the top left).
Note on BE5: Hours = Duration x HoursPerDay x Units, for each person on the task.
Note on BF5: Who answers for this phase: shown on the Roadmap. Phase (Level 1) rows.
Note on BG5: Everyone on the task, by full name with units: the Resources cell, checked (MS Project's Resource Names).
Note on BH5: Yes when this task's resource is over 100% of capacity (after leave) in a week the task runs: see Resource Report. Only weeks shown there count.
Note on BI5: Story points (optional estimate for agile reporting). Detail tasks only.
Note on BJ5: Optional: the sprint this task is planned in (dropdown). Blank = the sprint containing its forecast start.
Note on BK5: Duration minus Baseline Duration (working days).
Note on BL5: Work minus Baseline Work (hours).
Note on BM5: Copy the 4 BL Source columns, then Paste Special > Values onto the 4 Baseline columns.
Note on BQ5: Frozen plan. Filled by pasting values from the BL Source columns.
Note on BU5: RACI: who is accountable (one person, from Resources). Responsible = the Resources on the task.
Note on BV5: RACI: who is consulted (names, comma-separated; anyone, not only Resources).
Note on BW5: RACI: who is kept informed (names, comma-separated).
Note on BX5: Three-point estimate: (Optimistic + 4 x Duration + Pessimistic) / 6. Blank until both are typed. Settings > PertP50 / PertP80 add them up.
Note on BY5: Optimistic: the fewest working days it could take (at most the Duration).
Note on BZ5: Pessimistic: the most working days it could take (at least the Duration).
Note on CA5: What-if duration (3, 3d or 2w): used instead of Duration while Settings > Sandbox = Yes. Status says when the sandbox is on.

## Resources
Resource Sheet
One row per person: who they are, their availability and rate, then their leave by month, e.g. "16, 17(0.5)" under Nov-26 = all of 16 November and half of the 17th. Leave lowers capacity (Resource Report, Agile) but doesn't move tasks. Add rows for more people; add a month by inserting a column among the months (right-click a month > Insert > Table Columns to the Left) and typing its name, e.g. "Jan-29".
| Resource Name | Initials | Group | Type | Allocation % | Start | End | Focus % | Email | Tasks | Work | Notes | Accountable For | Consulted On | Informed Of | _Focus | Jan-26 | Feb-26 | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27 | Apr-27 | May-27 | Jun-27 | Jul-27 | Aug-27 | Sep-27 | Oct-27 | Nov-27 | Dec-27 | Jan-28 | Feb-28 | Mar-28 | Apr-28 | May-28 | Jun-28 | Jul-28 | Aug-28 | Sep-28 | Oct-28 | Nov-28 | Dec-28
| Priya Sharma | PS | Project Manager | Work | 50% |  |  | 0% | priya@example.com | 2 | 32 |  | 2 | 0 | 0 | 0%
| Morgan Patel | MP | Business Analyst | Work | 100% |  |  |  | morgan@example.com | 2 | 80 |  | 0 | 1 | 1 | 80% | [11 empty] | 28, 29, 30
| Alex Chen | AC | Solution Architect | Work | 50% |  |  | 0% | alex@example.com | 0 | 0 |  | 0 | 0 | 0 | 0%
| Casey Kim | CK | UX Designer | Work | 100% |  |  |  | casey@example.com | 1 | 48 |  | 0 | 0 | 0 | 80%
| Jordan Lee | JL | Backend Developer | Work | 100% |  |  |  | jordan@example.com | 0 | 0 |  | 0 | 1 | 0 | 80%
| Sam Rivera | SR | Frontend Developer | Work | 100% |  |  |  | sam@example.com | 1 | 60 |  | 0 | 1 | 0 | 80% | [10 empty] | 2(0.5)
| Taylor Morgan | TM | QA Engineer | Work | 100% |  |  |  | taylor@example.com | 1 | 120 |  | 1 | 0 | 0 | 80%
80%
80%
80%
80%
80%
80%
80%
80%
80%
80%
80%
80%
80%
80%
80%
80%
80%
80%
80%
80%
80%
80%
80%
80%
80%
80%
80%
80%
80%
80%
80%
80%
80%
80%
80%
80%
80%
80%
80%
80%
80%
80%
80%
LEAVE BY DAY: one row per person and month; type 1 (all day) or 0.5 (half a day) under each day off. It adds to the month columns above.
| Resource | Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | Days | _Key
| Casey Kim | Nov-26 | [15 empty] | 1 | 0.5 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 16, 17(0.5), 18, 19, 20, 23, 24, 25, 26, 27 | Casey Kim¦Nov-26
| Jordan Lee | Oct-26 | [29 empty] | 1 |  | 30 | Jordan Lee¦Oct-26
| Jordan Lee | Dec-26 | [20 empty] | 1 | 1 | 0.5 | [8 empty] | 21, 22, 23(0.5) | Jordan Lee¦Dec-26
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
¦
Note on B60: Pick the person (Resources).
Note on C60: Pick the month: one of the month columns above, e.g. Nov-26.
Note on E5: Work, Material or Cost (MS Project resource types).
Note on F5: How much of this person is on this project: 100% = full time, 70% = 7 of every 10 days.
Note on G5: Optional: first day on the project (blank = from the start).
Note on H5: Optional: last day on the project (blank = to the end).
Note on I5: Share of their sprint time that is delivery (story points); the rest is ceremonies and overhead. Blank = Settings > FocusFactor. 0% = an advisory role: allocated, but no points.
Note on K5: Detail tasks this resource is on (Tasks > Resources).
Note on L5: Assigned work (hours).
Note on N5: Tasks with this person as Accountable (RACI).
Note on O5: Tasks that name this person in Consulted (RACI).
Note on P5: Tasks that name this person in Informed (RACI).
Note on Q5: Focus % in use (the setting when blank).
Note on R5: Days off in Jan-26: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on S5: Days off in Feb-26: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on T5: Days off in Mar-26: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on U5: Days off in Apr-26: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on V5: Days off in May-26: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on W5: Days off in Jun-26: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on X5: Days off in Jul-26: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on Y5: Days off in Aug-26: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on Z5: Days off in Sep-26: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on AA5: Days off in Oct-26: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on AB5: Days off in Nov-26: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on AC5: Days off in Dec-26: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on AD5: Days off in Jan-27: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on AE5: Days off in Feb-27: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on AF5: Days off in Mar-27: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on AG5: Days off in Apr-27: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on AH5: Days off in May-27: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on AI5: Days off in Jun-27: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on AI60: The days off as the month cells write them: what the reports read.
Note on AJ5: Days off in Jul-27: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on AJ60: Person¦month: the look-up key (helper).
Note on AK5: Days off in Aug-27: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on AL5: Days off in Sep-27: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on AM5: Days off in Oct-27: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on AN5: Days off in Nov-27: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on AO5: Days off in Dec-27: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on AP5: Days off in Jan-28: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on AQ5: Days off in Feb-28: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on AR5: Days off in Mar-28: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on AS5: Days off in Apr-28: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on AT5: Days off in May-28: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on AU5: Days off in Jun-28: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on AV5: Days off in Jul-28: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on AW5: Days off in Aug-28: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on AX5: Days off in Sep-28: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on AY5: Days off in Oct-28: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on AZ5: Days off in Nov-28: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on BA5: Days off in Dec-28: "16, 17(0.5)" = 16th all day, 17th half a day.