## Instructions
Project Planner - MS Project-compatible Excel template
REQUIREMENTS
Excel version | Excel 2019 or Microsoft 365 (Windows or Mac), or Excel for the web. No macros needed.
HOW IT WORKS
1. Settings | Set project start and status date (both typed dates; Ctrl+; enters today), working week (Mon-Sun Yes/No), hours/day, Gantt scale and sprint calendar. Add holidays on 'Holidays'. Update the status date whenever you report progress.
2. Resources | List people/roles with Max Units and hourly rate. They appear in the Resource dropdown on Tasks and in sprint capacity. More than one person on a task: put the first on Tasks (Resource, Units) and add a row on the Assignments sheet (Task UID, Resource, Units) for each of the others.
3. Tasks | One row per task. Enter Level (1 = phase/summary, 2 = task, 3 = sub-task...), Task Name, Duration in working days (0 = milestone), and up to four predecessors by UID with link type (FS, SS, FF, SF) and lag in days (negative = lead). A row becomes a SUMMARY automatically when the rows beneath it have a higher level; its dates, work, cost and progress roll up. Optional Deadline: Deadline Check shows 'Late by Nd'. Hover over a column header for what it means.
4. Set the baseline | When the plan is agreed: on Tasks, select the 5 'BL Source' columns (all task rows), Copy, then select the first 'Baseline Start' cell and Paste Special > Values. Planned Start/Finish now stay frozen (like MS Project's Baseline) and the variance columns compare against it. To re-baseline, repeat; to clear it, delete the 5 Baseline columns' contents.
5. Track progress | Enter Actual Start, Actual Finish and % Complete. Forecast Start/Finish then use actuals and push every dependent task. Start / Finish / Duration / Work / Cost Var and Status flag slippage. Optionally enter Actual Cost (cost to date) on detail tasks; blank = Cost x Progress.
Critical path | Late Start / Late Finish come from a backward pass from the forecast project finish (and any deadline). Total Slack = how far a task can slip before it delays the project or a deadline; Free Slack = before it delays a successor. Critical = slack <= Settings > CriticalSlackDays on an unfinished task. A missed deadline gives negative slack to the task and the chain feeding it.
6. Gantt | Read-only view: dark outline = planned dates, green = done, blue = remaining on track, red = remaining on the critical path, orange = remaining but late vs plan, dark grey = summary, purple = milestone, red cell = deadline, red border = status date. Change GanttStart / GanttPeriod (1 = days, 7 = weeks, 30 = months, 91 = quarters) on Settings to scroll or zoom. Collapse the outline with the 1 2 3 buttons at the top left (rows are grouped by Level), or set Settings > OutlineShowLevel and filter Show = Yes (also on Tasks).
6b. Roadmap | One landscape page for sponsors: phases and milestones with their dates, drawn by month (blue = forecast, green = done, amber = late vs plan, outline = planned, purple = milestone, red = deadline missed). Settings > RoadmapStart scrolls the 18 months shown.
7. Sprints | Sprint calendar from Settings. Each task is tagged with the sprint its forecast start falls in. Work hours are prorated across sprints per resource, compared against capacity (Max Units x Hours/day x working days); over-allocations turn red. Optional agile columns: Story Points and Planned Sprint on Tasks (Planned Sprint wins over the automatic sprint), Points Capacity on Sprints; the table then shows committed and done points, velocity and the release burndown.
8. Dashboard | KPIs (including overall RAG, SPI, CPI, missed deadlines, link problems), status counts, upcoming milestones and sprint load vs capacity.
9. Status Report | For steering meetings: overall RAG and RAG by area (schedule, SPI, CPI, deadlines, critical path, plan quality), calculated from the thresholds on Settings (RAG...). Type a PM RAG to override one and say why in Comment. Earned value (BAC, PV, EV, AC, SPI, CPI, EAC, VAC, TCPI) and a commentary box for the period.
10. Schedule Report | Phase summary with RAG, all milestones, late tasks, tasks starting and due in the look-ahead window (Settings > LookaheadDays) and open critical tasks. Lists update with every edit; drag a list's bottom corner down to show more rows.
11. Resource Report | Per resource: work, done, remaining, cost, actual cost, late and critical tasks, peak week and weeks over capacity. Weekly hours and utilisation grids by week from Settings > ResourceWeekStart (red = over capacity), and a team hours vs capacity chart.
12. Agile Report | Story points: scope, done, remaining, velocity (last 3 closed sprints) and the sprint it forecasts finishing in; the current sprint's backlog and daily burndown; release burndown and committed vs done charts.
Leave | Leave sheet: one row per person, one column per month (Jan-26 ... Dec-28; add a month by typing e.g. Jan-29 in the next header cell). Type the days off: '16, 17(0.5)' under Nov-26 = all of 16 November and half of the 17th. Weekends and holidays are ignored. Leave lowers capacity on the Resource Report and Sprints and can make a task Over-allocated; it does not move task dates.
13. RAID | Risks, assumptions, issues and dependencies: owner, due date, probability and impact (1-5). Score = probability x impact (issues count as probability 5); Rating from Settings > RAIDHighScore / RAIDMediumScore; Overdue when not closed past its due date. Link a task by UID. The Status Report lists the top open items and rates RAID amber when any open item is High.
14. Decisions and Changes | Decision log (what, options and reasons, who, status) and change request log (schedule and cost impact, status, who decided). The Status Report totals approved and pending changes. Approving a change doesn't edit the plan: update the tasks, and re-baseline if the sponsor agrees.
15. History | On each reporting date, copy the SnapshotNow row on History and Paste Special > Values onto the first empty row of StatusHistory. Trend charts: forecast vs planned finish, earned value S-curve, SPI / CPI and a story-point burn-up that shows scope changes.
Earned value | Set a baseline first: without one, Budget = current Cost and PV follows the current plan, so SPI and CPI only show progress against the latest plan. PV = budget of work planned before the status date; EV = Budget x Progress; AC = Actual Cost. SPI = EV/PV, CPI = EV/AC, EAC = AC + (BAC - EV)/CPI.
CELL COLOURS
Blue text | Input - type here.
Black text on grey | Formula - do not overwrite. Summary rows grey-out inputs that are ignored.
Dark blue header | Input column. Dark grey header = calculated. Light grey header = helper column (hidden, grouped).
RULES (same as MS Project)
ID and UID | ID = position of the task (renumbers when rows move, like MS Project). UID = permanent number that predecessors refer to, so links survive inserting, deleting and moving rows. A duplicate or missing UID turns red.
Inserting tasks | Tasks is an Excel Table: right-click a row > Insert > Table Rows Above (or type in the row under the table). Every formula fills in automatically. Set the new task's UID to Settings > NextFreeUID (also shown at the top of Tasks).
Outline levels | Each row's Level may be at most 1 higher than the row above. A '?' in WBS (red) means a level jump.
Predecessors | Enter the predecessor's UID. A predecessor must be a detail task listed ABOVE its successor (order tasks roughly by date). Links that break this, or point to an empty row or a missing UID, are ignored and explained in the Link Check column (red). Summary rows ignore Duration / Predecessors / Actuals - they roll up. The rule keeps the schedule and the critical path consistent and rules out circular references.
Mode | Auto = scheduled from predecessors, project start and the constraint. Manual = pinned to the Constraint Date.
Constraints | Pick an MS Project constraint and enter its Constraint Date (a date alone = Start No Earlier Than). Start / Finish No Earlier Than push the task later; Start / Finish No Later Than and Must Start / Finish On win over predecessors (as in MS Project), so a conflict shows as negative slack. As Late As Possible moves the task later by its free slack: it finishes just in time for its successors and moves nothing else (its planned dates move by the same days).
Rescheduling | Settings > RescheduleAfterStatus = Yes moves incomplete work to after the status date (like MS Project 'Update Project'), so late tasks push successors.
Capacity | Tables grow when you add rows: Tasks starts with 200 rows, Resources 50, Assignments 100, Sprints 26, Holidays 100. The Gantt and MSP_Tasks sheets show the first 200 tasks (the Gantt says so when there are more); the Gantt timeline has 150 columns; the per-resource grids on Sprints and Resource Report show the first 25 resources and the Resource Report 26 weeks. To change these sizes, rebuild with scripts/build_planner.py --tasks / --resources / --assignments / --grid-resources / --sprints / --gantt-columns / --weeks (see README).
Speed | An edit recalculates in well under a second for typical plans (about 0.05 s for 200 tasks). Each change to the build is timed in CI; see docs/ARCHITECTURE.md in the repository. Keep the status date typed (not =TODAY()), which would recalculate everything after every edit.
MOVING TO MICROSOFT PROJECT
Best: MS Project XML | Save this workbook, then convert it with the browser page docs/export.html in the repository (nothing to install; works on a phone; the file stays on your device) or python scripts/export_mspdi.py. In MS Project: File > Open > the .xml > 'Open as a new project'. It carries the calendar and holidays, links by UID with lags, constraints, deadlines, actuals, the baseline, resources, assignments, Sprint (Text1) and Story Points (Number1), so MS Project schedules the plan the same way.
From MS Project | MS Project > File > Save As > XML, then choose the .xml on docs/export.html (or run python scripts/import_mspdi.py): you get a new planner workbook with the project's tasks, links, calendar, holidays, resources, assignments, baseline and leave. Anything the planner can't hold is listed and noted on the task.
Or: Import Wizard | The MSP_Tasks / MSP_Resources sheets below. Carries less (no calendar or holidays).
One-time setting | MS Project > File > Options > Trust Center > Trust Center Settings > Legacy Formats > 'Allow loading files with legacy or non-default file formats'.
Import | In MS Project: File > Open > choose this .xlsx > Import Wizard > New map > 'As a new project' > tick Tasks (and Resources) > Tasks source worksheet = MSP_Tasks, Resources = MSP_Resources. Column headers already use MS Project field names, so the wizard maps them automatically. Map 'Predecessors' (by ID) for a new project; 'Unique ID' and 'Unique ID Predecessors' are for merging into an existing one.
Tip: Start/Finish | For auto-scheduled tasks map Duration + Predecessors (+ Constraint Type/Date) and set Start/Finish to '(not mapped)' - importing Start/Finish makes MS Project add fixed 'Start No Earlier Than' constraints. Map Baseline Start/Finish to keep the plan, and Actual Start/Finish/% Complete for progress.
Rows | Blank MSP_Tasks rows import as blank tasks - delete them in MS Project, or filter the table to non-blank names and copy those rows to a new sheet before importing.
From MS Project to Excel | MS Project > File > Save As > Excel Workbook, then paste Name / Outline Level / Duration / Predecessors etc. into the Tasks input columns (split '3FS+2d' into UID, Type, Lag).
NAMES AND TABLES (Formulas > Name Manager)
Tables | Tasks, ResourceTable, AssignmentTable, SprintTable, HolidayTable, GanttView, MSPTasks, MSPResources, KPIs, StatusSummary, NextMilestones, OverallStatus, StatusRAG, EarnedValue, StatusNotes, PhaseSummary, MilestoneReport, LateTasks, StartingSoon, DueSoon, CriticalTasks, ResourceSummary, AgileKPIs, SprintBacklog, SprintBurndown, RAIDLog, DecisionLog, ChangeLog, TopRAID, ChangeControl, SnapshotNow, StatusHistory and the List* dropdown tables. Inside a table, formulas read [@Column] (this row).
Settings | ProjectStart, StatusDate, StatusWorkday, WorkWeek, Holidays, HoursPerDay, DefaultUnits, RescheduleAfterStatus, GanttStart, GanttPeriod, OutlineShowLevel, RoadmapStart, Sprint1Start, SprintLength, SprintCount, SprintPrefix, SprintLastEnd, CriticalSlackDays, ProjectFinish, PlannedFinish, FinishVarianceDays, LookaheadDays, RAGAmberSlipDays, RAGRedSlipDays, RAGAmberIndex, RAGRedIndex, ResourceWeekStart, CurrentSprint, TotalPoints, RAIDHighScore, RAIDMediumScore, NextFreeUID. Report values: ProjectRAG, evm_BAC, evm_PV, evm_EV, evm_AC, evm_SPI, evm_CPI, evm_EAC ...
Task columns | tsk_ID, tsk_UID, tsk_WBS, tsk_Name, tsk_Duration, tsk_PlanStart, tsk_FcFinish, tsk_Status, tsk_Resource, tsk_Work, tsk_Cost ... each is Tasks[Column], so it grows with the table. Other sheets read Tasks only through these names.
Resources / Sprints | res_Name, res_MaxUnits, res_Rate, ... spr_Name, spr_Start, spr_End, spr_WorkDays, spr_Capacity, spr_Work
Key formulas | Calculated start = WORKDAY.INTL(MIN(MAX(ProjectStart, [@_ConstraintLow], predecessor drivers), [@_ConstraintHigh]) - 1, 1, WorkWeek, Holidays). Predecessor driver (FS) = WORKDAY.INTL(OFFSET(Tasks[[#Headers],[_LeafCalcFinish]], [@_Pred1Pos], 0), 1 + Lag, WorkWeek, Holidays). Planned Start = Baseline Start if set, else calculated. Summary start = MIN(INDEX(Tasks[_LeafCalcStart], [@_Row]+1):INDEX(Tasks[_LeafCalcStart], [@_Row]+[@_Descendants])), where _Descendants = COUNTIF(Tasks[WBS], [@WBS] & ".*").

## Dashboard
Customer Portal Implementation - Dashboard
Project manager: Priya Sharma Status date: Sun 25-Oct-2026
| Key indicator | Value | Status | Count
| Planned start | 2026-09-07 | Complete | 9
| Planned finish | 2027-01-06 | In Progress | 0
| Forecast finish | 2027-01-06 | Behind | 2
| Finish variance (work days) | 0 | Late Start | 1
| Overall progress (duration-weighted) | 43.42% | Not Started | 11
| Planned progress by status date | 55.48%
| Detail tasks | 23
| Milestones | 5
| Total work (hrs) | 868
| Total cost | 69020
| Current sprint | Sprint 4
| Baseline | Not set (planned = calculated)
| Open critical tasks | 11
| Missed deadlines | 1
| Link problems (see Tasks > Link Check) | 0
| Overall status (see Status Report) | Red
| Schedule performance (SPI) | 0.76153
| Cost performance (CPI) | 0.93947
| Forecast cost at completion (EAC) | 73467.1649
| Story points done / total | 33 / 82
| Open risks / issues (see RAID) | 2 / 1
| Tasks with an over-allocated resource | 3
| Change requests awaiting decision | 1
| Next milestones (forecast) | Forecast date
| Build complete | 2026-11-09
| Go-live | 2026-12-15
| Project closed | 2027-01-06
Formulas:
Value = IFERROR(INDEX(tsk_FcFinish,MATCH(SMALL(tsk_MilestoneKey,(ROW()-ROW(NextMilestones[[#Headers],[Next milestones (forecast)]]))),tsk_MilestoneKey,0)),"")

## Roadmap
Customer Portal Implementation - Roadmap
Status date 25-Oct-2026 Forecast finish 06-Jan-2027 (0 working days vs plan)
[10 empty] | 2026 |  |  |  | 2027 | [11 empty] | 2028
[10 empty] | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2028-01-01 | 2028-02-01
Phases: 5
| _Task | WBS | Phase | Planned Start | Planned Finish | Start | Finish | Progress | Finish Var
| 1 | 1 | Initiation | 2026-09-07 | 2026-09-11 | 2026-09-07 | 2026-09-14 | 100% | 1
| 5 | 2 | Requirements & Design | 2026-09-14 | 2026-10-01 | 2026-09-15 | 2026-10-06 | 100% | 3
| 10 | 3 | Build | 2026-10-02 | 2026-10-30 | 2026-10-07 | 2026-11-09 | 45.13% | 6
| 20 | 4 | Test & Release | 2026-11-02 | 2027-01-04 | 2026-11-10 | 2027-01-04 | 0% | 0
| 27 | 5 | Project Close | 2026-11-16 | 2027-01-06 | 2026-11-16 | 2027-01-06 | 0% | 0
Milestones (in planned order): 5
| _Task | WBS | Milestone | Planned | Deadline | Forecast | Deadline Check | Status | Finish Var
| 4 | 1.3 | Kickoff complete | 2026-09-11 |  | 2026-09-14 |  | Complete | 1
| 9 | 2.4 | Design sign-off | 2026-10-01 |  | 2026-10-06 |  | Complete | 3
| 19 | 3.3 | Build complete | 2026-10-30 | 2026-11-06 | 2026-11-09 | Late by 1d | Not Started | 6
| 25 | 4.5 | Go-live | 2026-12-15 | 2026-12-18 | 2026-12-15 | OK | Not Started | 0
| 30 | 5.3 | Project closed | 2027-01-06 |  | 2027-01-06 |  | Not Started | 0
|  |  | Forecast |  | Done |  | Late vs plan |  | Planned (outline)
|  |  | Milestone |  | Deadline missed |  | Status date month
Months: Settings > RoadmapStart. Lists: drag a table's corner down for more rows. The timeline is conditional formatting only.
Formulas:
Planned Start = IF(RoadmapPhases[[#This Row],[_Task]]="","",IF(N(INDEX(tsk_PlanStart,RoadmapPhases[[#This Row],[_Task]]))=0,"",INDEX(tsk_PlanStart,RoadmapPhases[[#This Row],[_Task]])))
Planned Start = IF(RoadmapMilestones[[#This Row],[_Task]]="","",IF(N(INDEX(tsk_PlanFinish,RoadmapMilestones[[#This Row],[_Task]]))=0,"",INDEX(tsk_PlanFinish,RoadmapMilestones[[#This Row],[_Task]])))
Planned Finish = IF(RoadmapPhases[[#This Row],[_Task]]="","",IF(N(INDEX(tsk_PlanFinish,RoadmapPhases[[#This Row],[_Task]]))=0,"",INDEX(tsk_PlanFinish,RoadmapPhases[[#This Row],[_Task]])))
Planned Finish = IF(RoadmapMilestones[[#This Row],[_Task]]="","",IF(N(INDEX(tsk_Deadline,RoadmapMilestones[[#This Row],[_Task]]))=0,"",INDEX(tsk_Deadline,RoadmapMilestones[[#This Row],[_Task]])))
Start = IF(RoadmapPhases[[#This Row],[_Task]]="","",IF(N(INDEX(tsk_FcStart,RoadmapPhases[[#This Row],[_Task]]))=0,"",INDEX(tsk_FcStart,RoadmapPhases[[#This Row],[_Task]])))
Start = IF(RoadmapMilestones[[#This Row],[_Task]]="","",IF(N(INDEX(tsk_FcFinish,RoadmapMilestones[[#This Row],[_Task]]))=0,"",INDEX(tsk_FcFinish,RoadmapMilestones[[#This Row],[_Task]])))
Finish = IF(RoadmapPhases[[#This Row],[_Task]]="","",IF(N(INDEX(tsk_FcFinish,RoadmapPhases[[#This Row],[_Task]]))=0,"",INDEX(tsk_FcFinish,RoadmapPhases[[#This Row],[_Task]])))
Note on B7: Row of the task in the Tasks table (helper, hidden).
Note on B20: Row of the task in the Tasks table (helper, hidden).

## Status Report
Customer Portal Implementation - Status Report
Status date Sun 25-Oct-2026 Project manager: Priya Sharma Forecast finish Wed 06-Jan-2027 (0 working days vs plan)
| Area | Measure | Value | Calculated | PM RAG | RAG | Comment
| Overall | Worst of the areas below | 2 red, 3 amber | Red |  | Red
| Area | Measure | Value | Calculated | PM RAG | RAG | Comment
| Schedule | Forecast finish vs plan (working days) | 0 | Green |  | Green
| Schedule performance | SPI = earned value / planned value | 0.76153 | Red |  | Red
| Cost performance | CPI = earned value / actual cost | 0.93947 | Amber |  | Amber
| Deadlines | Tasks forecast to miss their deadline | 1 | Red |  | Red
| Critical path | Critical tasks forecast to finish late | 5 | Amber |  | Amber
| RAID | Open high-rated risks, issues, dependencies, assumptions | 3 | Amber |  | Amber
| Plan quality | Ignored links and outline errors (see Tasks) | 0 | Green |  | Green
EARNED VALUE at the status date
| Measure | Meaning | Value
| Budget at completion (BAC) | Baseline Cost once a baseline is set, otherwise Cost. | 69020
| Planned value (PV) | Budget of the work planned before the status date. | 40760
| Earned value (EV) | Budget of the work done (Budget x Progress). | 31040
| Actual cost (AC) | Actual Cost on Tasks; Cost x Progress where blank. | 33040
| Schedule variance (SV) | EV - PV. Negative = behind plan. | -9720
| Cost variance (CV) | EV - AC. Negative = over cost. | -2000
| Schedule performance index (SPI) | EV / PV. Below 1 = behind. | 0.76153
| Cost performance index (CPI) | EV / AC. Below 1 = over cost. | 0.93947
| Estimate at completion (EAC) | AC + (BAC - EV) / CPI: forecast cost at the current CPI. | 73467.1649
| Estimate to complete (ETC) | EAC - AC: forecast cost of the remaining work. | 40427.1649
| Variance at completion (VAC) | BAC - EAC. Negative = forecast overrun. | -4447.1649
| To-complete performance index (TCPI) | CPI the remaining work needs to finish on budget. | 1.0556
| % complete (earned) | EV / BAC. | 44.97%
| % complete (planned) | PV / BAC. | 59.06%
TOP OPEN RAID ITEMS (by score): 5
_Task | Item | Response | Owner | Due | Score | Rating | Task
3 | Issue 3: Core API endpoints running 6 days behind plan | Add a second developer for two weeks (change request CR 2). | Priya Sharma | 2026-10-23 | 20 | High | Core API endpoints
1 | Risk 1: Payment provider certification takes longer than planned | Start the certification paperwork now; book the provider's test slot. | Jordan Lee | 2026-10-30 | 16 | High | Payment gateway integration
5 | Dependency 5: Test environment delivered by IT operations by 9 November | Weekly check-in with IT operations. | Alex Chen | 2026-11-09 | 15 | High | System integration testing
2 | Risk 2: UX designer on leave for two weeks in November | Agree cover with the design agency. | Casey Kim | 2026-11-02 | 9 | Medium | Accessibility review
4 | Assumption 4: Client UAT team available from 7 December | Confirm names and dates at the November steering committee. | Morgan Patel | 2026-11-20 | 8 | Medium | User acceptance testing
CHANGE CONTROL AND DECISIONS
| Measure | Source | Value
| Change requests awaiting decision | Changes | 1
| Change requests approved or implemented | Changes | 1
| Approved schedule impact (working days) | Changes | 2
| Approved cost impact | Changes | 1360
| Cost impact awaiting decision | Changes | 6800
| Decisions awaiting approval | Decisions | 1
| Overdue RAID actions | RAID | 1
COMMENTARY for this period (type in the Notes column)
| Section | Notes
Summary
Achievements this period
Planned for next period
Issues and escalations
Decisions needed
Risks to watch
Formulas:
Calculated = IF(TopRAID[[#This Row],[_Task]]="","",IF(N(INDEX(raid_Due,TopRAID[[#This Row],[_Task]]))=0,"",INDEX(raid_Due,TopRAID[[#This Row],[_Task]])))
Note on A34: Row of the task in the Tasks table (helper, hidden).
Note on E4: RAG from the thresholds on Settings (RAGAmberSlipDays, RAGRedSlipDays, RAGAmberIndex, RAGRedIndex).
Note on E7: RAG from the thresholds on Settings (RAGAmberSlipDays, RAGRedSlipDays, RAGAmberIndex, RAGRedIndex).
Note on F4: Optional override by the project manager: Green, Amber or Red.
Note on F7: Optional override by the project manager: Green, Amber or Red.
Note on G4: Reported RAG: the PM override if there is one, otherwise the calculated RAG.
Note on G7: Reported RAG: the PM override if there is one, otherwise the calculated RAG.
Note on H4: Why: especially when the PM RAG differs from the calculated one.
Note on H7: Why: especially when the PM RAG differs from the calculated one.

## Schedule Report
Customer Portal Implementation - Schedule Report
Status date Sun 25-Oct-2026 Forecast finish Wed 06-Jan-2027 (0 working days vs plan)
Phases (outline level 1): 5
| _Task | WBS | Phase | Planned Finish | Forecast Finish | Finish Var | Progress | Budget | PV | EV | AC | SPI | CPI | Open Critical | RAG
| 1 | 1 | Initiation | 2026-09-11 | 2026-09-14 | 1 | 100% | 3400 | 3400 | 3400 | 4160 | 1 | 0.81731 | 0 | Red
| 5 | 2 | Requirements & Design | 2026-10-01 | 2026-10-06 | 3 | 100% | 14180 | 14180 | 14180 | 14740 | 1 | 0.96201 | 0 | Amber
| 10 | 3 | Build | 2026-10-30 | 2026-11-09 | 6 | 45.13% | 30300 | 23180 | 13460 | 14140 | 0.58067 | 0.95191 | 5 | Red
| 20 | 4 | Test & Release | 2027-01-04 | 2027-01-04 | 0 | 0% | 18860 | 0 | 0 | 0 |  |  | 4 | Green
| 27 | 5 | Project Close | 2027-01-06 | 2027-01-06 | 0 | 0% | 2280 | 0 | 0 | 0 |  |  | 2 | Green
Milestones (in planned order): 5
| _Task | WBS | Milestone | Planned | Forecast | Finish Var | Deadline | Deadline Check | Status
| 4 | 1.3 | Kickoff complete | 2026-09-11 | 2026-09-14 | 1 |  |  | Complete
| 9 | 2.4 | Design sign-off | 2026-10-01 | 2026-10-06 | 3 |  |  | Complete
| 19 | 3.3 | Build complete | 2026-10-30 | 2026-11-09 | 6 | 2026-11-06 | Late by 1d | Not Started
| 25 | 4.5 | Go-live | 2026-12-15 | 2026-12-15 | 0 | 2026-12-18 | OK | Not Started
| 30 | 5.3 | Project closed | 2027-01-06 | 2027-01-06 | 0 |  |  | Not Started
Late tasks (most days late first): 7
| _Task | WBS | Task | Resource | Planned Finish | Forecast Finish | Finish Var | Status | Critical
| 13 | 3.1.2 | Core API endpoints | Jordan Lee | 2026-10-22 | 2026-10-30 | 6 | Behind | Yes
| 14 | 3.1.3 | Payment gateway integration | Jordan Lee | 2026-10-30 | 2026-11-09 | 6 | Late Start | Yes
| 17 | 3.2.2 | Feature screens | Sam Rivera, Casey Kim[50%] | 2026-10-28 | 2026-11-05 | 6 | Behind | Yes
| 18 | 3.2.3 | Accessibility review | Casey Kim[50%] | 2026-10-29 | 2026-11-06 | 6 | Not Started | Yes
| 19 | 3.3 | Build complete |  | 2026-10-30 | 2026-11-09 | 6 | Not Started | Yes
| 21 | 4.1 | System integration testing | Taylor Morgan, Sam Rivera[50%] | 2026-11-11 | 2026-11-19 | 6 | Not Started
| 23 | 4.3 | Training & user guides | Casey Kim[50%] | 2026-11-10 | 2026-11-18 | 6 | Not Started
Starting by Fri 06-Nov (look-ahead 10 working days): 2
| _Task | WBS | Task | Resource | Forecast Start | Forecast Finish | Duration | Predecessors | Critical
| 14 | 3.1.3 | Payment gateway integration | Jordan Lee | 2026-11-02 | 2026-11-09 | 6 | 13 | Yes
| 18 | 3.2.3 | Accessibility review | Casey Kim[50%] | 2026-11-04 | 2026-11-06 | 3 | 17FF+1d | Yes
Due by Fri 06-Nov: 3
| _Task | WBS | Task | Resource | Forecast Finish | Progress | Deadline Check | Status | Critical
| 13 | 3.1.2 | Core API endpoints | Jordan Lee | 2026-10-30 | 50% |  | Behind | Yes
| 17 | 3.2.2 | Feature screens | Sam Rivera, Casey Kim[50%] | 2026-11-05 | 25% |  | Behind | Yes
| 18 | 3.2.3 | Accessibility review | Casey Kim[50%] | 2026-11-06 | 0% |  | Not Started | Yes
Open critical tasks (by forecast start): 11
| _Task | WBS | Task | Resource | Forecast Start | Forecast Finish | Total Slack | Deadline Check | Status
| 13 | 3.1.2 | Core API endpoints | Jordan Lee | 2026-10-15 | 2026-10-30 | -1 |  | Behind
| 17 | 3.2.2 | Feature screens | Sam Rivera, Casey Kim[50%] | 2026-10-19 | 2026-11-05 | 0 |  | Behind
| 14 | 3.1.3 | Payment gateway integration | Jordan Lee | 2026-11-02 | 2026-11-09 | -1 |  | Late Start
| 18 | 3.2.3 | Accessibility review | Casey Kim[50%] | 2026-11-04 | 2026-11-06 | 0 |  | Not Started
| 19 | 3.3 | Build complete |  | 2026-11-09 | 2026-11-09 | -1 | Late by 1d | Not Started
| 22 | 4.2 | User acceptance testing | Morgan Patel, Taylor Morgan | 2026-12-07 | 2026-12-14 | 0 |  | Not Started
| 24 | 4.4 | Go-live readiness review | Priya Sharma | 2026-12-15 | 2026-12-15 | 0 |  | Not Started
| 25 | 4.5 | Go-live |  | 2026-12-15 | 2026-12-15 | 0 | OK | Not Started
| 26 | 4.6 | Hypercare support | Jordan Lee[50%] | 2026-12-16 | 2027-01-04 | 0 |  | Not Started
| 29 | 5.2 | Lessons learned | Priya Sharma | 2027-01-05 | 2027-01-06 | 0 |  | Not Started
| 30 | 5.3 | Project closed |  | 2027-01-06 | 2027-01-06 | 0 |  | Not Started
Formulas:
Planned Finish = IF(PhaseSummary[[#This Row],[_Task]]="","",IF(N(INDEX(tsk_PlanFinish,PhaseSummary[[#This Row],[_Task]]))=0,"",INDEX(tsk_PlanFinish,PhaseSummary[[#This Row],[_Task]])))
Planned Finish = IF(MilestoneReport[[#This Row],[_Task]]="","",IF(N(INDEX(tsk_PlanFinish,MilestoneReport[[#This Row],[_Task]]))=0,"",INDEX(tsk_PlanFinish,MilestoneReport[[#This Row],[_Task]])))
Forecast Finish = IF(PhaseSummary[[#This Row],[_Task]]="","",IF(N(INDEX(tsk_FcFinish,PhaseSummary[[#This Row],[_Task]]))=0,"",INDEX(tsk_FcFinish,PhaseSummary[[#This Row],[_Task]])))
Forecast Finish = IF(MilestoneReport[[#This Row],[_Task]]="","",IF(N(INDEX(tsk_FcFinish,MilestoneReport[[#This Row],[_Task]]))=0,"",INDEX(tsk_FcFinish,MilestoneReport[[#This Row],[_Task]])))
Progress = IF(MilestoneReport[[#This Row],[_Task]]="","",IF(N(INDEX(tsk_Deadline,MilestoneReport[[#This Row],[_Task]]))=0,"",INDEX(tsk_Deadline,MilestoneReport[[#This Row],[_Task]])))
Finish Var = IF(LateTasks[[#This Row],[_Task]]="","",IF(N(INDEX(tsk_FcFinish,LateTasks[[#This Row],[_Task]]))=0,"",INDEX(tsk_FcFinish,LateTasks[[#This Row],[_Task]])))
Finish Var = IF(StartingSoon[[#This Row],[_Task]]="","",IF(N(INDEX(tsk_FcFinish,StartingSoon[[#This Row],[_Task]]))=0,"",INDEX(tsk_FcFinish,StartingSoon[[#This Row],[_Task]])))
Note on B5: Row of the task in the Tasks table (helper, hidden).
Note on B18: Row of the task in the Tasks table (helper, hidden).
Note on B36: Row of the task in the Tasks table (helper, hidden).
Note on B54: Row of the task in the Tasks table (helper, hidden).
Note on B72: Row of the task in the Tasks table (helper, hidden).
Note on B90: Row of the task in the Tasks table (helper, hidden).
Note on M5: Earned value / planned value. Below 1 = behind.
Note on N5: Earned value / actual cost. Below 1 = over cost.
Note on O5: Unfinished critical tasks in the phase.
Note on P5: Worst of finish slip, SPI and CPI against the Settings thresholds.

## Resource Report
Customer Portal Implementation - Resource Report
Weeks from Mon 05-Oct-2026 (Settings > ResourceWeekStart). Hours are each task's work spread over its forecast working days; red = more than Max Units x HoursPerDay x working days in the week, less leave (Leave sheet).
RESOURCES
| Resource | Max Units | Tasks | Work | Work Done | Remaining | Cost | Actual Cost | Late Tasks | Open Critical | Peak Week (h) | Peak Use | Weeks Over | Leave Days
| Priya Sharma | 50% | 4 | 56 | 24 | 32 | 5320 | 3040 | 0 | 2 | 16 | 80% | 0 | 0
| Morgan Patel | 100% | 3 | 128 | 80 | 48 | 8960 | 6160 | 0 | 1 | 40 | 100% | 0 | 3
| Alex Chen | 50% | 1 | 40 | 40 | 0 | 4400 | 4400 | 0 | 0 | 0 | 0% | 0 | 0
| Casey Kim | 100% | 4 | 128 | 60 | 68 | 9600 | 4500 | 3 | 2 | 25.7143 | 300% | 1 | 9.5
| Jordan Lee | 100% | 5 | 228 | 100 | 128 | 19380 | 9180 | 2 | 3 | 40 | 300% | 2 | 3.5
| Sam Rivera | 100% | 3 | 176 | 72 | 104 | 14080 | 5760 | 2 | 1 | 34.2857 | 85.71% | 0 | 0.5
| Taylor Morgan | 100% | 2 | 112 | 0 | 112 | 7280 | 0 | 1 | 1 | 40 | 100% | 0 | 0
Weekly hours by resource
| Resource | Max Units | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29
| Working days |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Priya Sharma | 50% | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Morgan Patel | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Alex Chen | 50% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Casey Kim | 100% | 13.7143 | 0 | 17.1429 | 17.1429 | 25.7143 | 8 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Jordan Lee | 100% | 20 | 33.3333 | 33.3333 | 33.3333 | 40 | 8 | 0 | 0 | 0 | 0 | 12 | 12 | 12 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sam Rivera | 100% | 18 | 30 | 34.2857 | 34.2857 | 27.4286 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Taylor Morgan | 100% | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 0 | 0 | 40 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Team hours |  | 51.7143 | 63.3333 | 84.7619 | 84.7619 | 93.1429 | 64 | 68 | 0 | 0 | 80 | 36 | 12 | 12 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Team capacity |  | 240 | 240 | 240 | 232 | 236 | 240 | 204 | 200 | 240 | 240 | 240 | 124 | 120 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240
Weekly utilisation by resource (hours / capacity after leave)
| Resource | Max Units | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29
| Working days |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Priya Sharma | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 0% | 0% | 0% | 40% | 0% | 0% | 80% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Morgan Patel | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 20% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Alex Chen | 50% | bar: 2026-10-05 to 2027-03-29
| Casey Kim | 100% | 34.29% | 0% | 42.86% | 42.86% | 64.29% | 20% | 300% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Jordan Lee | 100% | 50% | 83.33% | 83.33% | 104.2% | 100% | 20% | 0% | 0% | 0% | 0% | 30% | 300% | 50% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Sam Rivera | 100% | 45% | 75% | 85.71% | 85.71% | 76.19% | 40% | 40% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Taylor Morgan | 100% | 0% | 0% | 0% | 0% | 0% | 80% | 80% | 0% | 0% | 100% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Leave by resource (working days, from the Leave sheet)
| Resource | _Leave Row | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29
| _Leave column: week month |  | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12 | 12 | 13 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 15 | 15 | 15 | 15 | 16 | 16 | 16 | 16 | 16
| _Leave column: next month |  | 12 | 12 | 12 | 12 | 13 | 13 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 15 | 15 | 15 | 15 | 16 | 16 | 16 | 16 | 17 | 17 | 17 | 17 | 17
| Priya Sharma | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Morgan Patel | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Alex Chen | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Casey Kim | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Jordan Lee | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sam Rivera | 3 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Taylor Morgan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative hours at each week boundary (helper for the weekly grids)
|  |  | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 32 | 32 | 32 | 32 | 40 | 40 | 40 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56
|  |  | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 120 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128
|  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
|  |  | 34.2857 | 48 | 48 | 65.1429 | 82.2857 | 108 | 116 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128
|  |  | 20 | 40 | 73.3333 | 106.6667 | 140 | 180 | 188 | 188 | 188 | 188 | 188 | 200 | 212 | 224 | 228 | 228 | 228 | 228 | 228 | 228 | 228 | 228 | 228 | 228 | 228 | 228 | 228
|  |  | 0 | 18 | 48 | 82.2857 | 116.5714 | 144 | 160 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 64 | 64 | 64 | 104 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112 | 112
Note on E5: Assigned hours.
Note on F5: Work x Progress.
Note on J5: Unfinished tasks forecast to finish after plan, or not started on time (Schedule Report).
Note on L5: Most hours in any week shown in the grid below.
Note on M5: Highest weekly utilisation in the grid.
Note on N5: Weeks in the grid above 100% of capacity (after leave).
Note on O5: Working days of leave in the weeks shown below (Leave sheet).

## Agile Report
Customer Portal Implementation - Agile Report
Status date Sun 25-Oct-2026 Sprint length 14 days. Per-sprint numbers: Sprints sheet. Enter Story Points (and optionally Planned Sprint) on Tasks.
RELEASE
|  | Measure | Value
|  | Total story points (scope) | 82
|  | Done by the status date | 33
|  | Remaining | 49
|  | Velocity (average of the last 3 closed sprints) | 11
|  | Sprints needed at that velocity | 5
|  | Sprints closed | 3
|  | Forecast to finish in | Sprint 8
|  | Forecast finish (velocity) | 2026-12-27
|  | Forecast finish (schedule) | 2027-01-06
|  | Current sprint | Sprint 4
|  | Current sprint: committed points | 8
|  | Current sprint: done so far | 0
|  | Tasks without story points (not milestones) | 0
Current sprint backlog (Sprint 4): 1
| _Task | Task | Story Points | Resource | Forecast Finish | Progress | Status
| 17 | Feature screens | 8 | Sam Rivera, Casey Kim[50%] | 2026-11-05 | 25% | Behind
CURRENT SPRINT BURNDOWN (story points of the tasks in the sprint)
|  | Day | Remaining | Ideal | _ChartDay | _ChartRemaining | _ChartIdeal
|  | 2026-10-19 | 8 | 7.2 | 19-Oct | 8 | 7.2
|  | 2026-10-20 | 8 | 6.4 | 20-Oct | 8 | 6.4
|  | 2026-10-21 | 8 | 5.6 | 21-Oct | 8 | 5.6
|  | 2026-10-22 | 8 | 4.8 | 22-Oct | 8 | 4.8
|  | 2026-10-23 | 8 | 4 | 23-Oct | 8 | 4
|  | 2026-10-24 | 8 | 4 | 24-Oct | 8 | 4
|  | 2026-10-25 | 8 | 4 | 25-Oct | 8 | 4
|  | 2026-10-26 |  | 3.2 | 26-Oct | #N/A | 3.2
|  | 2026-10-27 |  | 2.4 | 27-Oct | #N/A | 2.4
|  | 2026-10-28 |  | 1.6 | 28-Oct | #N/A | 1.6
|  | 2026-10-29 |  | 0.8 | 29-Oct | #N/A | 0.8
|  | 2026-10-30 |  | 0 | 30-Oct | #N/A | 0
|  | 2026-10-31 |  | 0 | 31-Oct | #N/A | 0
|  | 2026-11-01 |  | 0 | 01-Nov | #N/A | 0
[6 empty] | #N/A | #N/A
[6 empty] | #N/A | #N/A
[6 empty] | #N/A | #N/A
[6 empty] | #N/A | #N/A
[6 empty] | #N/A | #N/A
[6 empty] | #N/A | #N/A
[6 empty] | #N/A | #N/A
[6 empty] | #N/A | #N/A
[6 empty] | #N/A | #N/A
[6 empty] | #N/A | #N/A
[6 empty] | #N/A | #N/A
[6 empty] | #N/A | #N/A
[6 empty] | #N/A | #N/A
[6 empty] | #N/A | #N/A
[6 empty] | #N/A | #N/A
[6 empty] | #N/A | #N/A
[6 empty] | #N/A | #N/A
Formulas:
Forecast Finish = IF(SprintBacklog[[#This Row],[_Task]]="","",IF(N(INDEX(tsk_FcFinish,SprintBacklog[[#This Row],[_Task]]))=0,"",INDEX(tsk_FcFinish,SprintBacklog[[#This Row],[_Task]])))
Task = IF(OR(CurrentSprint="",ROW()-ROW(SprintBurndown[[#Headers],[Day]])>SprintLength),"",CurrentSprintStart+ROW()-ROW(SprintBurndown[[#Headers],[Day]])-1)
Resource = IF(SprintBurndown[[#This Row],[Day]]="","",agl_CurCommitted*MAX(0,1-NETWORKDAYS.INTL(CurrentSprintStart,SprintBurndown[[#This Row],[Day]],WorkWeek,Holidays)/MAX(1,NETWORKDAYS.INTL(CurrentSprintStart,CurrentSprintEnd,WorkWeek,Holidays))))
Note on B20: Row of the task in the Tasks table (helper, hidden).
Note on D43: Committed points not yet done at the end of the day (blank after the status date).
Note on E43: Straight line over the sprint's working days.

## RAID
RAID Log: Risks, Assumptions, Issues, Dependencies
Type in the blue columns. Score = Probability x Impact (1-5 each; an issue counts as probability 5). Rating thresholds: Settings > RAIDHighScore / RAIDMediumScore. Link a task by its UID.
| Ref | Type | Title | Owner | Raised | Due | Status | Probability | Impact | Score | Rating | Overdue | Task UID | Task | Task Finish | Response | Update | _Label | _TopKey
| 1 | Risk | Payment provider certification takes longer than planned | Jordan Lee | 2026-10-01 | 2026-10-30 | Open | 4 | 4 | 16 | High |  | 14 | Payment gateway integration | 2026-11-09 | Start the certification paperwork now; book the provider's test slot. | Paperwork submitted 20-Oct. | Risk 1: Payment provider certification takes longer than planned | 17
| 2 | Risk | UX designer on leave for two weeks in November | Casey Kim | 2026-10-05 | 2026-11-02 | Open | 3 | 3 | 9 | Medium |  | 18 | Accessibility review | 2026-11-06 | Agree cover with the design agency. |  | Risk 2: UX designer on leave for two weeks in November | 10
| 3 | Issue | Core API endpoints running 6 days behind plan | Priya Sharma | 2026-10-20 | 2026-10-23 | In Progress |  | 4 | 20 | High | Overdue | 13 | Core API endpoints | 2026-10-30 | Add a second developer for two weeks (change request CR 2). | Escalated to sponsor. | Issue 3: Core API endpoints running 6 days behind plan | 21
| 4 | Assumption | Client UAT team available from 7 December | Morgan Patel | 2026-09-15 | 2026-11-20 | Open | 2 | 4 | 8 | Medium |  | 22 | User acceptance testing | 2026-12-14 | Confirm names and dates at the November steering committee. |  | Assumption 4: Client UAT team available from 7 December | 9
| 5 | Dependency | Test environment delivered by IT operations by 9 November | Alex Chen | 2026-09-30 | 2026-11-09 | Open | 3 | 5 | 15 | High |  | 21 | System integration testing | 2026-11-19 | Weekly check-in with IT operations. | Hardware ordered. | Dependency 5: Test environment delivered by IT operations by 9 November | 16
| 6 | Risk | Scope creep on the reporting screens | Priya Sharma | 2026-09-10 | 2026-10-09 | Closed | 2 | 3 | 6 | Low |  | 17 | Feature screens | 2026-11-05 | Reporting screens moved to phase 2 (decision D 2). | Closed 09-Oct. | Risk 6: Scope creep on the reporting screens
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
Formulas:
Task Finish = IF(N(RAIDLog[[#This Row],[Task UID]])=0,"",IFERROR(INDEX(tsk_FcFinish,MATCH(RAIDLog[[#This Row],[Task UID]],tsk_UID,0)),""))
Note on B4: Permanent number, quoted in reports and other logs (e.g. RAID 3).
Note on G4: Date the next action or the mitigation is due.
Note on I4: 1 (rare) to 5 (almost certain). Ignored for issues.
Note on J4: 1 (minor) to 5 (severe).
Note on K4: Probability x Impact; an issue counts as probability 5.
Note on M4: Not closed and the due date is before the status date.
Note on N4: UID of the task this item affects (optional).
Note on P4: The linked task's forecast finish.
Note on Q4: Mitigation, contingency or action.
Note on R4: Latest progress note.
Note on S4: Type, Ref and Title in one cell, for the Status Report.
Note on T4: Open items ranked by score (the Status Report's top list).

## Decisions
Decision Log
One row per decision. Link the task (UID) and RAID item it relates to.
| Ref | Date | Decision | Options and Reasons | Decided By | Status | Waiting (days) | Task UID | Task | RAID Ref
| 1 | 2026-09-14 | Use the existing identity provider for customer log-in | Options: build our own, buy a new service, reuse. Reuse is cheapest and already security-approved. | Steering committee | Approved |  | 12 | Data model & database setup
| 2 | 2026-10-09 | Move the reporting screens to phase 2 | Keeps the Build deadline (06-Nov). Reporting is not needed for go-live. | Sponsor | Approved |  | 17 | Feature screens | 6
| 3 | 2026-10-22 | Add a second developer to the core API for two weeks | Recovers about 4 of the 6 days' slip. Cost in change request CR 2. | Sponsor | Proposed | 3 | 13 | Core API endpoints | 3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
Note on H4: Days a proposed decision has waited, to the status date.

## Changes
Change Request Log
Schedule impact in working days (negative = saves time) and cost impact as estimated when raised. Approving a request doesn't change the plan: update the tasks, and re-baseline if agreed.
| Ref | Raised | Requested By | Title | Reason | Schedule Impact | Cost Impact | Status | Decided | Decided By | Waiting (days) | Task UID | Task
| 1 | 2026-09-28 | Marketing | Add a newsletter sign-up to the portal | Supports the launch campaign. | 2 | 1360 | Approved | 2026-10-02 | Sponsor |  | 17 | Feature screens
| 2 | 2026-10-22 | Priya Sharma | Second developer on the core API for two weeks | Recovers most of the API slip (RAID 3). | -4 | 6800 | Under Review |  |  | 3 | 13 | Core API endpoints
| 3 | 2026-10-12 | Sales | Live chat on every page | Nice to have; not needed for go-live. | 8 | 9600 | Rejected | 2026-10-16 | Steering committee
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
Note on G4: Working days (negative = saves time).
Note on L4: Days an undecided request has waited, to the status date.

## History
Status History
On each reporting date: select the SnapshotNow row below, Copy, then click the first empty row of StatusHistory and Paste Special > Values. The trend charts update from StatusHistory.
| Status Date | Forecast Finish | Planned Finish | Finish Var | % Earned | % Planned | BAC | PV | EV | AC | SPI | CPI | EAC | Points Done | Total Points | Open Risks | Open Issues | Pending Changes | RAG
| 2026-10-25 | 2027-01-06 | 2027-01-06 | 0 | 44.97% | 59.06% | 69020 | 40760 | 31040 | 33040 | 0.76153 | 0.93947 | 73467.1649 | 33 | 82 | 2 | 1 | 1 | Red
StatusHistory: one row per reporting date (values pasted from SnapshotNow)
| Status Date | Forecast Finish | Planned Finish | Finish Var | % Earned | % Planned | BAC | PV | EV | AC | SPI | CPI | EAC | Points Done | Total Points | Open Risks | Open Issues | Pending Changes | RAG
| 2026-09-27 | 2026-12-28 | 2026-12-28 | 0 | 17% | 19% | 58040 | 11028 | 9867 | 10064 | 0.89 | 0.98 | 59199 | 5 | 76 | 2 | 0 | 0 | Green
| 2026-10-04 | 2026-12-29 | 2026-12-28 | 1 | 27% | 31% | 58040 | 17992 | 15671 | 16298 | 0.87 | 0.96 | 60362 | 18 | 78 | 3 | 0 | 1 | Green
| 2026-10-11 | 2026-12-31 | 2026-12-28 | 3 | 36% | 43% | 58040 | 24957 | 20894 | 21939 | 0.84 | 0.95 | 60943 | 23 | 82 | 3 | 0 | 0 | Amber
| 2026-10-18 | 2027-01-04 | 2026-12-28 | 5 | 44% | 54% | 58040 | 31342 | 25538 | 27070 | 0.81 | 0.94 | 61522 | 33 | 82 | 4 | 1 | 0 | Amber

## Settings
Project Settings
Blue = edit me. Grey = calculated. Column D shows the defined name every formula uses for that setting.
| Setting | Value | Named range | Notes
| Project name | Customer Portal Implementation | ProjectName | Shown on every sheet title.
| Project manager | Priya Sharma | ProjectManager
| Project start date | 2026-09-07 | ProjectStartDate | Required. Tasks without predecessors start here (moved to the next working day if needed).
| Project start (in use) | 2026-09-07 | ProjectStart | Copy of the date above (dates show as 1900 until it is entered).
| Status date | 2026-10-25 | StatusDateInput | The date progress is reported as of. Type it, or press Ctrl+; for today. It is a typed date rather than TODAY() on purpose: TODAY() would make Excel recalculate the whole schedule after every edit.
| Status date (in use) | 2026-10-25 | StatusDate | The project start until a status date is entered. Drives Status, the red status-date line on the Gantt and rescheduling of late work.
| First working day on/after status date | 2026-10-26 | StatusWorkday
| Reschedule incomplete work after status date? | Yes | RescheduleAfterStatus | Yes = like MS Project 'move incomplete parts after status date': unstarted tasks can't start before the status date and in-progress tasks finish their remaining duration after it, pushing all successors.
| Working hours per day | 8 | HoursPerDay | Work (hrs) = Duration x Hours/day x Units.
| Default assignment units | 100% | DefaultUnits | Used when a task has a resource but Units is blank. 100% = full time.
| Monday is a working day | Yes | WorkMon | Working-week calendar (Yes/No). Feeds every WORKDAY / NETWORKDAYS formula.
| Tuesday is a working day | Yes | WorkTue
| Wednesday is a working day | Yes | WorkWed
| Thursday is a working day | Yes | WorkThu
| Friday is a working day | Yes | WorkFri
| Saturday is a working day | No | WorkSat
| Sunday is a working day | No | WorkSun
| Weekend mask (calculated) | 0000011 | WorkWeek | 7-character Mon..Sun string used by WORKDAY.INTL (1 = non-working).
| Gantt timeline start | 2026-09-07 | GanttStart | Defaults to the Monday of the project start week. Overwrite with any date to scroll the timeline.
| Gantt days per column | 1 | GanttPeriod | 1 = daily timeline, 7 = weekly, 30 = monthly (calendar months), 91 = quarterly (calendar quarters).
| Show tasks down to outline level | 9 | OutlineShowLevel | Tasks and Gantt > Show is Yes for rows at this level or above: filter Show = Yes to see only phases (1), phases and tasks (2) ... Reapply the filter (Data > Reapply) after changing it.
| Roadmap first month | 2026-09-01 | RoadmapStart | The Roadmap sheet's first month. Overwrite with the first of any month to scroll it.
| Sprint 1 start date | 2026-09-07 | Sprint1Start | Defaults to the project start. Overwrite to align with your sprint calendar.
| Sprint length (calendar days) | 14 | SprintLength | 14 = two-week sprints.
| Number of sprints | 12 | SprintCount | Up to the number of rows in the Sprints table (26; add rows to the table for more). Tasks outside the sprint range are labelled 'Backlog'.
| Sprint name prefix | Sprint | SprintPrefix | Sprint names = prefix & number.
| Last sprint end (calculated) | 2027-02-21 | SprintLastEnd
| Sprint containing the status date (calculated) | Sprint 4 | CurrentSprint | Blank outside the sprint calendar. Agile Report shows its backlog and daily burndown.
| Current sprint start (calculated) | 2026-10-19 | CurrentSprintStart
| Current sprint end (calculated) | 2026-11-01 | CurrentSprintEnd
| Total story points (calculated) | 82 | TotalPoints | Story points on all detail tasks: the release scope for burndown and burn-up.
| Critical when total slack is at most (days) | 0 | CriticalSlackDays | 0 = only tasks with no slack (or negative slack from a missed deadline) are critical, like MS Project.
| Forecast project finish (calculated) | 2027-01-06 | ProjectFinish | The critical path's backward pass starts here (the detail tasks' early finish).
| Planned project finish (calculated) | 2027-01-06 | PlannedFinish | Baseline finish once a baseline is set.
| Project finish variance (calculated, working days) | 0 | FinishVarianceDays | Forecast finish minus planned finish. Positive = late.
| Look-ahead window (working days) | 10 | LookaheadDays | Schedule Report lists tasks starting or due within this many working days of the status date.
| Look-ahead window ends (calculated) | 2026-11-06 | LookaheadEnd
| RAG: amber when the finish slips by (working days) | 3 | RAGAmberSlipDays | Status Report thresholds. A finish slip of at least this many working days is amber.
| RAG: red when the finish slips by (working days) | 10 | RAGRedSlipDays
| RAG: amber when SPI or CPI is below | 0.95 | RAGAmberIndex | SPI = earned value / planned value; CPI = earned value / actual cost. 1.00 = on plan.
| RAG: red when SPI or CPI is below | 0.85 | RAGRedIndex
| RAID: high rating from score | 15 | RAIDHighScore | Score = probability x impact (1-25). At or above this a risk or issue is rated High.
| RAID: medium rating from score | 8 | RAIDMediumScore
| Resource Report first week | 2026-10-05 | ResourceWeekStart | Defaults to the Monday two weeks before the status date. Overwrite with any Monday to scroll the weekly grids.
| Next free task UID (calculated) | 201 | NextFreeUID | Give a newly inserted task row this UID (see Instructions > Inserting tasks).

## Tasks
Customer Portal Implementation - Task Entry
Type in BLUE columns only. Level = outline level (1 = phase, 2 = task, 3 = sub-task). Predecessors refer to the UID column. Planned = Baseline once set, otherwise calculated from Duration + Predecessors. Forecast also uses Actuals, so slips ripple to every successor. Insert rows inside the table: formulas fill in automatically.
Next free UID for a new row: 201
IDENTITY | [5 empty] | SCHEDULING INPUTS | [16 empty] | PLAN / ACTUAL / FORECAST | [5 empty] | VARIANCE |  | CRITICAL PATH |  |  |  |  | CHECKS |  | PROGRESS |  |  | RESOURCES & SPRINT | [11 empty] | SET BASELINE: copy these 5 columns, then Paste Special > Values onto the 5 Baseline columns | [9 empty] | VARIANCE vs BASELINE |  |  | EARNED VALUE (at status date) |  |  |  | HELPER COLUMNS (hidden - click + above to show)
ID | UID | WBS | Level | Show | Task Name | Mode | Duration | Pred1 UID | Pred1 Type | Pred1 Lag | Pred2 UID | Pred2 Type | Pred2 Lag | Pred3 UID | Pred3 Type | Pred3 Lag | Pred4 UID | Pred4 Type | Pred4 Lag | Constraint | Constraint Date | Deadline | Planned Start | Planned Finish | Actual Start | Actual Finish | Forecast Start | Forecast Finish | Start Var | Finish Var | Late Start | Late Finish | Total Slack | Free Slack | Critical | Deadline Check | Link Check | % Complete | Progress | Status | Resource | Units | Resource Names | Over-allocated | Work | Cost | Actual Cost | Planned Sprint | Sprint | Story Points | Predecessors | Notes | BL Source Start | BL Source Finish | BL Source Duration | BL Source Work | BL Source Cost | Baseline Start | Baseline Finish | Baseline Duration | Baseline Work | Baseline Cost | Duration Var | Work Var | Cost Var | Budget | PV | EV | AC | _Level | _Row | _ParentRow | _NextLevel | _IsSummary | _Descendants | _IsLeaf | _Pred1Pos | _Pred2Pos | _Pred3Pos | _Pred4Pos | _ConstraintCode | _ConstraintStart | _ConstraintLow | _ConstraintHigh | _LeafCalcStart | _LeafCalcFinish | _LeafFcstStart | _LeafFcstFinish | _LeafProgress | _LeafWork | _LeafCost | _LeafTotalWork | _LeafTotalCost | _ResourceAC | _Pred1FinishKey | _Pred2FinishKey | _Pred3FinishKey | _Pred4FinishKey | _Pred1SlackKey | _Pred2SlackKey | _Pred3SlackKey | _Pred4SlackKey | _LastSuccessorRow | _SuccessorFinishLimit | _LeafLateFinish | _LeafLateStart | _LeafTotalSlack | _LeafCritical | _AlapShift | _ShownCalcStart | _ShownCalcFinish | _ShownFcstStart | _ShownFcstFinish | _CalcStart | _CalcFinish | _Pred1Problem | _Pred2Problem | _Pred3Problem | _Pred4Problem | _Pred1PlanDriver | _Pred2PlanDriver | _Pred3PlanDriver | _Pred4PlanDriver | _Pred1FcstDriver | _Pred2FcstDriver | _Pred3FcstDriver | _Pred4FcstDriver | _StartWorkday | _FinishWorkday | _WorkPerWorkday | _WorkBeforeStart | _WeightDur | _WeightDone | _UIDPredecessors | _MilestoneKey | _PlannedPct | _LeafBudget | _LeafPV | _LeafEV | _LeafAC | _Phase | _PhaseKey | _MilestoneOrder | _LateKey | _StartSoonKey | _DueSoonKey | _CriticalKey | _LeafWorkDone | _DoneDate | _LeafPoints | _CurrentSprintKey
1 | 1 | 1 | 1 | Yes | Initiation | Auto | [16 empty] | 2026-09-07 | 2026-09-11 |  |  | 2026-09-07 | 2026-09-14 | 0 | 1 | 2026-09-14 | 2026-09-18 | 4 | [5 empty] | 100% | Complete |  |  |  |  | 40 | 3400 | [5 empty] | Phase 1 - summary rows roll up dates, work, cost and progress automatically. | 2026-09-07 | 2026-09-14 | 6 | 40 | 3400 | [8 empty] | 3400 | 3400 | 3400 | 4160 | 1 | 1 | 0 | 2 | TRUE | 3 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 |  |  |  |  | 2026-09-07 | 2026-09-11 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | [5 empty] | 0 |  | 0
2 | 2 | 1.1 | 2 | Yes | Project charter & scope statement | Auto | 3 | [15 empty] | 2026-09-07 | 2026-09-09 | 2026-09-07 | 2026-09-10 | 2026-09-07 | 2026-09-10 | 0 | 1 | 2026-09-14 | 2026-09-16 | 4 | 0 |  |  |  | 100% | 100% | Complete | Priya Sharma |  | Priya Sharma |  | 24 | 2280 | 3040 |  | Sprint 1 | 3 |  | Took 1 extra day for sponsor sign-off. | 2026-09-07 | 2026-09-10 | 3 | 24 | 2280 | [8 empty] | 2280 | 2280 | 2280 | 3040 | 2 | 2 | 6 | 2 | FALSE | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2958465 | 2026-09-07 | 2026-09-09 | 2026-09-07 | 2026-09-10 | 1 | 24 | 2280 | 24 | 2280 | 3040 | [8 empty] | 3 | 2026-09-16 | 2026-09-16 | 2026-09-14 | 4 | FALSE | 0 | 2026-09-07 | 2026-09-09 | 2026-09-07 | 2026-09-10 | 2026-09-07 | 2026-09-09 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 6 | 0 | 3 | 3 |  |  | 1 | 2280 | 2280 | 2280 | 3040 | 1 | [6 empty] | 24 | 2026-09-10 | 3
3 | 3 | 1.2 | 2 | Yes | Stakeholder kickoff workshop | Auto | 2 | 2 | FS | [13 empty] | 2026-09-10 | 2026-09-11 | 2026-09-11 | 2026-09-14 | 2026-09-11 | 2026-09-14 | 1 | 1 | 2026-09-17 | 2026-09-18 | 4 | 0 |  |  |  | 100% | 100% | Complete | Morgan Patel |  | Morgan Patel |  | 16 | 1120 |  |  | Sprint 1 | 2 | 2 |  | 2026-09-11 | 2026-09-14 | 2 | 16 | 1120 | [8 empty] | 1120 | 1120 | 1120 | 1120 | 2 | 3 | 6 | 2 | FALSE | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2958465 | 2026-09-10 | 2026-09-11 | 2026-09-11 | 2026-09-14 | 1 | 16 | 1120 | 16 | 1120 | 1120 | 2912184 |  |  |  | 100000 |  |  |  | 4 | 2026-09-18 | 2026-09-18 | 2026-09-17 | 4 | FALSE | 0 | 2026-09-10 | 2026-09-11 | 2026-09-11 | 2026-09-14 | 2026-09-10 | 2026-09-11 |  |  |  |  | 2026-09-10 | 0 | 0 | 0 | 2026-09-11 | 0 | 0 | 0 | 5 | 6 | 8 | 32 | 2 | 2 | 2 |  | 1 | 1120 | 1120 | 1120 | 1120 | 1 | [6 empty] | 16 | 2026-09-14 | 2
4 | 4 | 1.3 | 2 | Yes | Kickoff complete | Auto | 0 | 3 | FS | [13 empty] | 2026-09-11 | 2026-09-11 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 1 | 1 | 2026-09-18 | 2026-09-18 | 4 | 0 |  |  |  | 100% | 100% | Complete |  |  |  |  | 0 | 0 |  |  | Sprint 1 |  | 3 | Milestone (Duration 0). | 2026-09-14 | 2026-09-14 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 2 | 4 | 6 | 1 | FALSE | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2958465 | 2026-09-11 | 2026-09-11 | 2026-09-14 | 2026-09-14 | 1 | 0 | 0 | 0 | 0 | 0 | 2912182 |  |  |  | 100000 |  |  |  | 6 | 2026-09-18 | 2026-09-18 | 2026-09-18 | 4 | FALSE | 0 | 2026-09-11 | 2026-09-11 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 |  |  |  |  | 2026-09-11 | 0 | 0 | 0 | 2026-09-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 3 |  | 1 | 0 | 0 | 0 | 0 | 1 |  | 2026-09-11 |  |  |  |  | 0 | 2026-09-14 | 0
5 | 5 | 2 | 1 | Yes | Requirements & Design | Auto | [16 empty] | 2026-09-14 | 2026-10-01 |  |  | 2026-09-15 | 2026-10-06 | 1 | 3 | 2026-09-21 | 2026-10-08 | 2 | [5 empty] | 100% | Complete |  |  |  |  | 172 | 14180 | [6 empty] | 2026-09-15 | 2026-10-06 | 16 | 172 | 14180 | [8 empty] | 14180 | 14180 | 14180 | 14740 | 1 | 5 | 0 | 2 | TRUE | 4 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 |  |  |  |  | 2026-09-14 | 2026-10-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2 | 5 | [5 empty] | 0 |  | 0
6 | 6 | 2.1 | 2 | Yes | Requirements gathering | Auto | 8 | 4 | FS | [13 empty] | 2026-09-14 | 2026-09-23 | 2026-09-15 | 2026-09-25 | 2026-09-15 | 2026-09-25 | 1 | 2 | 2026-09-21 | 2026-09-30 | 3 | 0 |  |  |  | 100% | 100% | Complete | Morgan Patel |  | Morgan Patel |  | 64 | 4480 | 5040 |  | Sprint 1 | 8 | 4 |  | 2026-09-15 | 2026-09-25 | 8 | 64 | 4480 | [8 empty] | 4480 | 4480 | 4480 | 5040 | 2 | 6 | 10 | 2 | FALSE | 0 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2958465 | 2026-09-14 | 2026-09-23 | 2026-09-15 | 2026-09-25 | 1 | 64 | 4480 | 64 | 4480 | 5040 | 2912182 |  |  |  | 100000 |  |  |  | 8 | 2026-09-30 | 2026-09-30 | 2026-09-21 | 3 | FALSE | 0 | 2026-09-14 | 2026-09-23 | 2026-09-15 | 2026-09-25 | 2026-09-14 | 2026-09-23 |  |  |  |  | 2026-09-14 | 0 | 0 | 0 | 2026-09-15 | 0 | 0 | 0 | 7 | 15 | 7.1111 | 42.6667 | 8 | 8 | 4 |  | 1 | 4480 | 4480 | 4480 | 5040 | 2 | [6 empty] | 64 | 2026-09-25 | 8
7 | 7 | 2.2 | 2 | Yes | Solution architecture | Auto | 5 | 6 | SS | 3 | [12 empty] | 2026-09-17 | 2026-09-23 | 2026-09-18 | 2026-09-25 | 2026-09-18 | 2026-09-25 | 1 | 2 | 2026-10-02 | 2026-10-08 | 9 | 7 |  |  |  | 100% | 100% | Complete | Alex Chen |  | Alex Chen, Jordan Lee[50%] |  | 60 | 6100 |  |  | Sprint 1 | 5 | 6SS+3d | Start-to-Start + 3 day lag example. | 2026-09-18 | 2026-09-25 | 5 | 60 | 6100 | [8 empty] | 6100 | 6100 | 6100 | 6100 | 2 | 7 | 10 | 2 | FALSE | 0 | 1 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 2958465 | 2026-09-17 | 2026-09-23 | 2026-09-18 | 2026-09-25 | 1 | 40 | 4400 | 60 | 6100 | 4400 | 2912162 |  |  |  | 100000 |  |  |  | 9 | 2026-10-08 | 2026-10-08 | 2026-10-02 | 9 | FALSE | 0 | 2026-09-17 | 2026-09-23 | 2026-09-18 | 2026-09-25 | 2026-09-17 | 2026-09-23 |  |  |  |  | 2026-09-17 | 0 | 0 | 0 | 2026-09-18 | 0 | 0 | 0 | 10 | 15 | 6.6667 | 60 | 5 | 5 | 6SS+3d |  | 1 | 6100 | 6100 | 6100 | 6100 | 2 | [6 empty] | 40 | 2026-09-25 | 5
8 | 8 | 2.3 | 2 | Yes | UX wireframes & prototype | Auto | 6 | 6 | FS | [13 empty] | 2026-09-24 | 2026-10-01 | 2026-09-28 | 2026-10-06 | 2026-09-28 | 2026-10-06 | 2 | 3 | 2026-10-01 | 2026-10-08 | 2 | 0 |  |  |  | 100% | 100% | Complete | Casey Kim |  | Casey Kim |  | 48 | 3600 |  |  | Sprint 2 | 5 | 6 |  | 2026-09-28 | 2026-10-06 | 6 | 48 | 3600 | [8 empty] | 3600 | 3600 | 3600 | 3600 | 2 | 8 | 10 | 2 | FALSE | 0 | 1 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 2958465 | 2026-09-24 | 2026-10-01 | 2026-09-28 | 2026-10-06 | 1 | 48 | 3600 | 48 | 3600 | 3600 | 2912170 |  |  |  | 100000 |  |  |  | 9 | 2026-10-08 | 2026-10-08 | 2026-10-01 | 2 | FALSE | 0 | 2026-09-24 | 2026-10-01 | 2026-09-28 | 2026-10-06 | 2026-09-24 | 2026-10-01 |  |  |  |  | 2026-09-24 | 0 | 0 | 0 | 2026-09-28 | 0 | 0 | 0 | 16 | 22 | 6.8571 | 102.8571 | 6 | 6 | 6 |  | 1 | 3600 | 3600 | 3600 | 3600 | 2 | [6 empty] | 48 | 2026-10-06 | 5
9 | 9 | 2.4 | 2 | Yes | Design sign-off | Auto | 0 | 7 | FS |  | 8 | FS | [10 empty] | 2026-10-01 | 2026-10-01 | 2026-10-06 | 2026-10-06 | 2026-10-06 | 2026-10-06 | 3 | 3 | 2026-10-08 | 2026-10-08 | 2 | 0 |  |  |  | 100% | 100% | Complete |  |  |  |  | 0 | 0 |  |  | Sprint 3 |  | 7,8 | Two predecessors - waits for the later one. | 2026-10-06 | 2026-10-06 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 2 | 9 | 10 | 1 | FALSE | 0 | 1 | 7 | 8 | 0 | 0 | 0 | 0 | 0 | 2958465 | 2026-10-01 | 2026-10-01 | 2026-10-06 | 2026-10-06 | 1 | 0 | 0 | 0 | 0 | 0 | 2912162 | 2912162 |  |  | 99993 | 100000 |  |  | 16 | 2026-10-08 | 2026-10-08 | 2026-10-08 | 2 | FALSE | 0 | 2026-10-01 | 2026-10-01 | 2026-10-06 | 2026-10-06 | 2026-10-01 | 2026-10-01 |  |  |  |  | 2026-09-23 | 2026-10-01 | 0 | 0 | 2026-09-25 | 2026-10-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 7,8 |  | 1 | 0 | 0 | 0 | 0 | 2 |  | 2026-10-01 |  |  |  |  | 0 | 2026-10-06 | 0
10 | 10 | 3 | 1 | Yes | Build | Auto | [16 empty] | 2026-10-02 | 2026-10-30 |  |  | 2026-10-07 | 2026-11-09 | 3 | 6 | 2026-10-09 | 2026-11-06 | -1 |  | Yes |  |  |  | 45.13% | Behind |  |  |  |  | 372 | 30300 | [6 empty] | 2026-10-07 | 2026-11-09 | 24 | 372 | 30300 | [8 empty] | 30300 | 23180 | 13460 | 14140 | 1 | 10 | 0 | 2 | TRUE | 9 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 |  |  |  |  | 2026-10-02 | 2026-10-30 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3 | 10 | [5 empty] | 0 |  | 0
11 | 11 | 3.1 | 2 | Yes | Backend | Auto | [16 empty] | 2026-10-02 | 2026-10-30 |  |  | 2026-10-07 | 2026-11-09 | 3 | 6 | 2026-10-09 | 2026-11-06 | -1 |  | Yes |  |  |  | 47.62% | Behind |  |  |  |  | 168 | 14280 | [5 empty] | Level-2 summary with sub-tasks. | 2026-10-07 | 2026-11-09 | 24 | 168 | 14280 | [8 empty] | 14280 | 10880 | 6800 | 7480 | 2 | 11 | 15 | 3 | TRUE | 3 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 |  |  |  |  | 2026-10-02 | 2026-10-30 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3 | [6 empty] | 0 |  | 0
12 | 12 | 3.1.1 | 3 | Yes | Data model & database setup | Auto | 5 | 9 | FS | [13 empty] | 2026-10-02 | 2026-10-08 | 2026-10-07 | 2026-10-14 | 2026-10-07 | 2026-10-14 | 3 | 4 | 2026-10-09 | 2026-10-15 | 1 | 0 |  |  |  | 100% | 100% | Complete | Jordan Lee |  | Jordan Lee |  | 40 | 3400 |  |  | Sprint 3 | 5 | 9 |  | 2026-10-07 | 2026-10-14 | 5 | 40 | 3400 | [8 empty] | 3400 | 3400 | 3400 | 3400 | 3 | 12 | 16 | 3 | FALSE | 0 | 1 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 2958465 | 2026-10-02 | 2026-10-08 | 2026-10-07 | 2026-10-14 | 1 | 40 | 3400 | 40 | 3400 | 3400 | 2912162 |  |  |  | 100000 |  |  |  | 13 | 2026-10-15 | 2026-10-15 | 2026-10-09 | 1 | FALSE | 0 | 2026-10-02 | 2026-10-08 | 2026-10-07 | 2026-10-14 | 2026-10-02 | 2026-10-08 |  |  |  |  | 2026-10-02 | 0 | 0 | 0 | 2026-10-07 | 0 | 0 | 0 | 23 | 28 | 6.6667 | 146.6667 | 5 | 5 | 9 |  | 1 | 3400 | 3400 | 3400 | 3400 | 3 | [6 empty] | 40 | 2026-10-14 | 5
13 | 13 | 3.1.2 | 3 | Yes | Core API endpoints | Auto | 10 | 12 | FS | [13 empty] | 2026-10-09 | 2026-10-22 | 2026-10-15 |  | 2026-10-15 | 2026-10-30 | 4 | 6 | 2026-10-16 | 2026-10-29 | -1 | -1 | Yes |  |  | 50% | 50% | Behind | Jordan Lee |  | Jordan Lee | Yes | 80 | 6800 | 4080 |  | Sprint 3 | 8 | 12 | In progress - enter % Complete; forecast finish adjusts. | 2026-10-15 | 2026-10-30 | 10 | 80 | 6800 | [8 empty] | 6800 | 6800 | 3400 | 4080 | 3 | 13 | 16 | 3 | FALSE | 0 | 1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 2958465 | 2026-10-09 | 2026-10-22 | 2026-10-15 | 2026-10-30 | 0.5 | 80 | 6800 | 80 | 6800 | 4080 | 2912155 |  |  |  | 100000 |  |  |  | 17 | 2026-10-29 | 2026-10-29 | 2026-10-16 | -1 | TRUE | 0 | 2026-10-09 | 2026-10-22 | 2026-10-15 | 2026-10-30 | 2026-10-09 | 2026-10-22 |  |  |  |  | 2026-10-09 | 0 | 0 | 0 | 2026-10-15 | 0 | 0 | 0 | 29 | 40 | 6.6667 | 186.6667 | 10 | 5 | 12 |  | 1 | 6800 | 6800 | 3400 | 4080 | 3 |  |  | 7 |  | 2026-10-30 | 2026-10-15 | 40 |  | 8
14 | 14 | 3.1.3 | 3 | Yes | Payment gateway integration | Auto | 6 | 13 | FS | [13 empty] | 2026-10-23 | 2026-10-30 |  |  | 2026-11-02 | 2026-11-09 | 6 | 6 | 2026-10-30 | 2026-11-06 | -1 | -1 | Yes |  |  |  | 0% | Late Start | Jordan Lee |  | Jordan Lee |  | 48 | 4080 |  |  | Sprint 5 | 5 | 13 |  | 2026-11-02 | 2026-11-09 | 6 | 48 | 4080 | [8 empty] | 4080 | 680 | 0 | 0 | 3 | 14 | 16 | 2 | FALSE | 0 | 1 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 2958465 | 2026-10-23 | 2026-10-30 | 2026-11-02 | 2026-11-09 | 0 | 48 | 4080 | 48 | 4080 | 0 | 2912141 |  |  |  | 100000 |  |  |  | 19 | 2026-11-06 | 2026-11-06 | 2026-10-30 | -1 | TRUE | 0 | 2026-10-23 | 2026-10-30 | 2026-11-02 | 2026-11-09 | 2026-10-23 | 2026-10-30 |  |  |  |  | 2026-10-23 | 0 | 0 | 0 | 2026-11-02 | 0 | 0 | 0 | 41 | 46 | 8 | 320 | 6 | 0 | 13 |  | 0.16667 | 4080 | 680 | 0 | 0 | 3 |  |  | 7 | 2026-11-02 |  | 2026-11-02 | 0 |  | 5
15 | 15 | 3.2 | 2 | Yes | Frontend | Auto | [16 empty] | 2026-10-02 | 2026-10-29 |  |  | 2026-10-07 | 2026-11-06 | 3 | 6 | 2026-10-13 | 2026-11-06 | 0 |  | Yes |  |  |  | 42.86% | Behind |  |  |  |  | 204 | 16020 | [6 empty] | 2026-10-07 | 2026-11-06 | 23 | 204 | 16020 | [8 empty] | 16020 | 12300 | 6660 | 6660 | 2 | 15 | 15 | 3 | TRUE | 3 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 |  |  |  |  | 2026-10-02 | 2026-10-29 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3 | [6 empty] | 0 |  | 0
16 | 16 | 3.2.1 | 3 | Yes | UI component library | Auto | 6 | 9 | FS | [13 empty] | 2026-10-02 | 2026-10-09 | 2026-10-07 | 2026-10-16 | 2026-10-07 | 2026-10-16 | 3 | 5 | 2026-10-13 | 2026-10-20 | 2 | 0 |  |  |  | 100% | 100% | Complete | Sam Rivera |  | Sam Rivera |  | 48 | 3840 |  |  | Sprint 3 | 5 | 9 |  | 2026-10-07 | 2026-10-16 | 6 | 48 | 3840 | [8 empty] | 3840 | 3840 | 3840 | 3840 | 3 | 16 | 20 | 3 | FALSE | 0 | 1 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 2958465 | 2026-10-02 | 2026-10-09 | 2026-10-07 | 2026-10-16 | 1 | 48 | 3840 | 48 | 3840 | 3840 | 2912158 |  |  |  | 100000 |  |  |  | 17 | 2026-10-20 | 2026-10-20 | 2026-10-13 | 2 | FALSE | 0 | 2026-10-02 | 2026-10-09 | 2026-10-07 | 2026-10-16 | 2026-10-02 | 2026-10-09 |  |  |  |  | 2026-10-02 | 0 | 0 | 0 | 2026-10-07 | 0 | 0 | 0 | 23 | 30 | 6 | 132 | 6 | 6 | 9 |  | 1 | 3840 | 3840 | 3840 | 3840 | 3 | [6 empty] | 48 | 2026-10-16 | 5
17 | 17 | 3.2.2 | 3 | Yes | Feature screens | Auto | 12 | 16 | FS |  | 13 | SS | 2 | [9 empty] | 2026-10-13 | 2026-10-28 | 2026-10-19 |  | 2026-10-19 | 2026-11-05 | 4 | 6 | 2026-10-21 | 2026-11-05 | 0 | 0 | Yes |  |  | 25% | 25% | Behind | Sam Rivera |  | Sam Rivera, Casey Kim[50%] |  | 144 | 11280 |  |  | Sprint 4 | 8 | 16,13SS+2d |  | 2026-10-19 | 2026-11-05 | 12 | 144 | 11280 | [8 empty] | 11280 | 8460 | 2820 | 2820 | 3 | 17 | 20 | 3 | FALSE | 0 | 1 | 16 | 13 | 0 | 0 | 0 | 0 | 0 | 2958465 | 2026-10-13 | 2026-10-28 | 2026-10-19 | 2026-11-05 | 0.25 | 96 | 7680 | 144 | 11280 | 1920 | 2912150 | 2912140 |  |  | 100000 | 100000 |  |  | 18 | 2026-11-05 | 2026-11-05 | 2026-10-21 | 0 | TRUE | 0 | 2026-10-13 | 2026-10-28 | 2026-10-19 | 2026-11-05 | 2026-10-13 | 2026-10-28 |  |  |  |  | 2026-10-12 | 2026-10-13 | 0 | 0 | 2026-10-19 | 2026-10-19 | 0 | 0 | 31 | 44 | 6.8571 | 205.7143 | 12 | 3 | 16,13SS+2d |  | 0.75 | 11280 | 8460 | 2820 | 2820 | 3 |  |  | 7 |  | 2026-11-05 | 2026-10-19 | 24 |  | 8 | 17
18 | 18 | 3.2.3 | 3 | Yes | Accessibility review | Auto | 3 | 17 | FF | 1 | [12 empty] | 2026-10-27 | 2026-10-29 |  |  | 2026-11-04 | 2026-11-06 | 6 | 6 | 2026-11-04 | 2026-11-06 | 0 | 0 | Yes |  |  |  | 0% | Not Started | Casey Kim | 50% | Casey Kim[50%] |  | 12 | 900 |  |  | Sprint 5 | 3 | 17FF+1d | Finish-to-Finish + 1 day; 50% units. | 2026-11-04 | 2026-11-06 | 3 | 12 | 900 | [8 empty] | 900 | 0 | 0 | 0 | 3 | 18 | 20 | 2 | FALSE | 0 | 1 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 2958465 | 2026-10-27 | 2026-10-29 | 2026-11-04 | 2026-11-06 | 0 | 12 | 900 | 12 | 900 | 0 | 2912134 |  |  |  | 100000 |  |  |  | 19 | 2026-11-06 | 2026-11-06 | 2026-11-04 | 0 | TRUE | 0 | 2026-10-27 | 2026-10-29 | 2026-11-04 | 2026-11-06 | 2026-10-27 | 2026-10-29 |  |  |  |  | 2026-10-27 | 0 | 0 | 0 | 2026-11-04 | 0 | 0 | 0 | 43 | 45 | 4 | 168 | 3 | 0 | 17FF+1d |  | 0 | 900 | 0 | 0 | 0 | 3 |  |  | 7 | 2026-11-04 | 2026-11-06 | 2026-11-04 | 0 |  | 3
19 | 19 | 3.3 | 2 | Yes | Build complete | Auto | 0 | 14 | FS |  | 18 | FS | [9 empty] | 2026-11-06 | 2026-10-30 | 2026-10-30 |  |  | 2026-11-09 | 2026-11-09 | 6 | 6 | 2026-11-06 | 2026-11-06 | -1 | -1 | Yes | Late by 1d |  |  | 0% | Not Started |  |  |  |  | 0 | 0 |  |  | Sprint 5 |  | 14,18 | Milestone with a deadline of 06-Nov (see Deadline Check). | 2026-11-09 | 2026-11-09 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 2 | 19 | 15 | 1 | FALSE | 0 | 1 | 14 | 18 | 0 | 0 | 0 | 0 | 0 | 2958465 | 2026-10-30 | 2026-10-30 | 2026-11-09 | 2026-11-09 | 0 | 0 | 0 | 0 | 0 | 0 | 2912133 | 2912133 |  |  | 100000 | 99999 |  |  | 21 | 2026-11-24 | 2026-11-06 | 2026-11-06 | -1 | TRUE | 0 | 2026-10-30 | 2026-10-30 | 2026-11-09 | 2026-11-09 | 2026-10-30 | 2026-10-30 |  |  |  |  | 2026-10-30 | 2026-10-29 | 0 | 0 | 2026-11-09 | 2026-11-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 14,18 | 2026-11-09 | 0 | 0 | 0 | 0 | 0 | 3 |  | 2026-10-30 | 7 |  |  | 2026-11-09 | 0 |  | 0
20 | 20 | 4 | 1 | Yes | Test & Release | Auto | [16 empty] | 2026-11-02 | 2027-01-04 |  |  | 2026-11-10 | 2027-01-04 | 6 | 0 | 2026-11-25 | 2027-01-04 | 0 |  | Yes |  |  |  | 0% | Not Started |  |  |  |  | 260 | 18860 | [6 empty] | 2026-11-10 | 2027-01-04 | 36 | 260 | 18860 | [8 empty] | 18860 | 0 | 0 | 0 | 1 | 20 | 0 | 2 | TRUE | 6 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 |  |  |  |  | 2026-11-02 | 2027-01-04 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 4 | 20 | [5 empty] | 0 |  | 0
21 | 21 | 4.1 | 2 | Yes | System integration testing | Auto | 8 | 19 | FS | [13 empty] | 2026-11-02 | 2026-11-11 |  |  | 2026-11-10 | 2026-11-19 | 6 | 6 | 2026-11-25 | 2026-12-04 | 11 | 0 |  |  |  |  | 0% | Not Started | Taylor Morgan |  | Taylor Morgan, Sam Rivera[50%] |  | 96 | 6720 |  |  | Sprint 5 | 8 | 19 |  | 2026-11-10 | 2026-11-19 | 8 | 96 | 6720 | [8 empty] | 6720 | 0 | 0 | 0 | 2 | 21 | 25 | 2 | FALSE | 0 | 1 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 2958465 | 2026-11-02 | 2026-11-11 | 2026-11-10 | 2026-11-19 | 0 | 64 | 4160 | 96 | 6720 | 0 | 2912115 |  |  |  | 100000 |  |  |  | 24 | 2026-12-04 | 2026-12-04 | 2026-11-25 | 11 | FALSE | 0 | 2026-11-02 | 2026-11-11 | 2026-11-10 | 2026-11-19 | 2026-11-02 | 2026-11-11 |  |  |  |  | 2026-11-02 | 0 | 0 | 0 | 2026-11-10 | 0 | 0 | 0 | 47 | 54 | 8 | 368 | 8 | 0 | 19 |  | 0 | 6720 | 0 | 0 | 0 | 4 |  |  | 7 |  |  |  | 0 |  | 8
22 | 22 | 4.2 | 2 | Yes | User acceptance testing | Auto | 6 | 21 | FS | [10 empty] | Start No Earlier Than | 2026-12-07 |  | 2026-12-07 | 2026-12-14 |  |  | 2026-12-07 | 2026-12-14 | 0 | 0 | 2026-12-07 | 2026-12-14 | 0 | 0 | Yes |  |  |  | 0% | Not Started | Morgan Patel |  | Morgan Patel, Taylor Morgan |  | 96 | 6480 |  |  | Sprint 7 | 5 | 21 | Constraint: Start No Earlier Than 07-Dec (client availability). | 2026-12-07 | 2026-12-14 | 6 | 96 | 6480 | [8 empty] | 6480 | 0 | 0 | 0 | 2 | 22 | 25 | 2 | FALSE | 0 | 1 | 21 | 0 | 0 | 0 | 4 | 2026-12-07 | 2026-12-07 | 2958465 | 2026-12-07 | 2026-12-14 | 2026-12-07 | 2026-12-14 | 0 | 48 | 3360 | 96 | 6480 | 0 | 2912105 |  |  |  | 99989 |  |  |  | 24 | 2026-12-14 | 2026-12-14 | 2026-12-07 | 0 | TRUE | 0 | 2026-12-07 | 2026-12-14 | 2026-12-07 | 2026-12-14 | 2026-12-07 | 2026-12-14 |  |  |  |  | 2026-11-12 | 0 | 0 | 0 | 2026-11-20 | 0 | 0 | 0 | 66 | 71 | 8 | 520 | 6 | 0 | 21 |  | 0 | 6480 | 0 | 0 | 0 | 4 | [5 empty] | 2026-12-07 | 0 |  | 5
23 | 23 | 4.3 | 2 | Yes | Training & user guides | Auto | 5 | 21 | SS | 2 | [12 empty] | 2026-11-04 | 2026-11-10 |  |  | 2026-11-12 | 2026-11-18 | 6 | 6 | 2026-12-08 | 2026-12-14 | 18 | 18 |  |  |  |  | 0% | Not Started | Casey Kim | 50% | Casey Kim[50%] | Yes | 20 | 1500 |  |  | Sprint 5 | 3 | 21SS+2d |  | 2026-11-12 | 2026-11-18 | 5 | 20 | 1500 | [8 empty] | 1500 | 0 | 0 | 0 | 2 | 23 | 25 | 2 | FALSE | 0 | 1 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 2958465 | 2026-11-04 | 2026-11-10 | 2026-11-12 | 2026-11-18 | 0 | 20 | 1500 | 20 | 1500 | 0 | 2912094 |  |  |  | 100000 |  |  |  | 24 | 2026-12-14 | 2026-12-14 | 2026-12-08 | 18 | FALSE | 0 | 2026-11-04 | 2026-11-10 | 2026-11-12 | 2026-11-18 | 2026-11-04 | 2026-11-10 |  |  |  |  | 2026-11-04 | 0 | 0 | 0 | 2026-11-12 | 0 | 0 | 0 | 49 | 53 | 4 | 192 | 5 | 0 | 21SS+2d |  | 0 | 1500 | 0 | 0 | 0 | 4 |  |  | 7 |  |  |  | 0 |  | 3
24 | 24 | 4.4 | 2 | Yes | Go-live readiness review | Auto | 1 | 22 | FS |  | 23 | FS |  | 21 | FS | [7 empty] | 2026-12-15 | 2026-12-15 |  |  | 2026-12-15 | 2026-12-15 | 0 | 0 | 2026-12-15 | 2026-12-15 | 0 | 0 | Yes |  |  |  | 0% | Not Started | Priya Sharma |  | Priya Sharma |  | 8 | 760 |  |  | Sprint 8 | 1 | 22,23,21 | Three predecessors. | 2026-12-15 | 2026-12-15 | 1 | 8 | 760 | [8 empty] | 760 | 0 | 0 | 0 | 2 | 24 | 25 | 2 | FALSE | 0 | 1 | 22 | 23 | 21 | 0 | 0 | 0 | 0 | 2958465 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 0 | 8 | 760 | 8 | 760 | 0 | 2912095 | 2912095 | 2912095 |  | 100000 | 99982 | 99983 |  | 25 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 0 | TRUE | 0 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 2026-12-15 |  |  |  |  | 2026-12-15 | 2026-11-11 | 2026-11-12 | 0 | 2026-12-15 | 2026-11-19 | 2026-11-20 | 0 | 72 | 72 | 8 | 568 | 1 | 0 | 22,23,21 |  | 0 | 760 | 0 | 0 | 0 | 4 | [5 empty] | 2026-12-15 | 0 |  | 1
25 | 25 | 4.5 | 2 | Yes | Go-live | Auto | 0 | 24 | FS | [12 empty] | 2026-12-18 | 2026-12-15 | 2026-12-15 |  |  | 2026-12-15 | 2026-12-15 | 0 | 0 | 2026-12-15 | 2026-12-15 | 0 | 0 | Yes | OK |  |  | 0% | Not Started |  |  |  |  | 0 | 0 |  |  | Sprint 8 |  | 24 | Milestone with a deadline of 18-Dec. | 2026-12-15 | 2026-12-15 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 2 | 25 | 25 | 2 | FALSE | 0 | 1 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 2958465 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 0 | 0 | 0 | 0 | 0 | 0 | 2912094 |  |  |  | 100000 |  |  |  | 26 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 0 | TRUE | 0 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 2026-12-15 |  |  |  |  | 2026-12-15 | 0 | 0 | 0 | 2026-12-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 24 | 2026-12-15 | 0 | 0 | 0 | 0 | 0 | 4 |  | 2026-12-15 |  |  |  | 2026-12-15 | 0 |  | 0
26 | 26 | 4.6 | 2 | Yes | Hypercare support | Auto | 10 | 25 | FS | [13 empty] | 2026-12-16 | 2027-01-04 |  |  | 2026-12-16 | 2027-01-04 | 0 | 0 | 2026-12-16 | 2027-01-04 | 0 | 0 | Yes |  |  |  | 0% | Not Started | Jordan Lee | 50% | Jordan Lee[50%] | Yes | 40 | 3400 |  |  | Sprint 8 | 5 | 25 |  | 2026-12-16 | 2027-01-04 | 10 | 40 | 3400 | [8 empty] | 3400 | 0 | 0 | 0 | 2 | 26 | 25 | 1 | FALSE | 0 | 1 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 2958465 | 2026-12-16 | 2027-01-04 | 2026-12-16 | 2027-01-04 | 0 | 40 | 3400 | 40 | 3400 | 0 | 2912094 |  |  |  | 100000 |  |  |  | 29 | 2027-01-04 | 2027-01-04 | 2026-12-16 | 0 | TRUE | 0 | 2026-12-16 | 2027-01-04 | 2026-12-16 | 2027-01-04 | 2026-12-16 | 2027-01-04 |  |  |  |  | 2026-12-16 | 0 | 0 | 0 | 2026-12-16 | 0 | 0 | 0 | 73 | 82 | 4 | 288 | 10 | 0 | 25 |  | 0 | 3400 | 0 | 0 | 0 | 4 | [5 empty] | 2026-12-16 | 0 |  | 5
27 | 27 | 5 | 1 | Yes | Project Close | Auto | [16 empty] | 2026-11-16 | 2027-01-06 |  |  | 2026-11-16 | 2027-01-06 | 0 | 0 | 2027-01-05 | 2027-01-06 | 0 |  | Yes |  |  |  | 0% | Not Started |  |  |  |  | 24 | 2280 | [6 empty] | 2026-11-16 | 2027-01-06 | 34 | 24 | 2280 | [8 empty] | 2280 | 0 | 0 | 0 | 1 | 27 | 0 | 2 | TRUE | 3 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 |  |  |  |  | 2026-11-16 | 2027-01-06 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 5 | 27 | [5 empty] | 0 |  | 0
28 | 28 | 5.1 | 2 | Yes | Steering committee update | Manual | 1 | [13 empty] | 2026-11-16 |  | 2026-11-16 | 2026-11-16 |  |  | 2026-11-16 | 2026-11-16 | 0 | 0 | 2027-01-06 | 2027-01-06 | 33 | 33 |  |  |  |  | 0% | Not Started | Priya Sharma |  | Priya Sharma |  | 8 | 760 |  |  | Sprint 6 | 1 |  | Manual mode example: fixed on its Constraint Date. | 2026-11-16 | 2026-11-16 | 1 | 8 | 760 | [8 empty] | 760 | 0 | 0 | 0 | 2 | 28 | 32 | 2 | FALSE | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 2026-11-16 | 2026-11-16 | 2958465 | 2026-11-16 | 2026-11-16 | 2026-11-16 | 2026-11-16 | 0 | 8 | 760 | 8 | 760 | 0 | [8 empty] | 0 | 2958465 | 2027-01-06 | 2027-01-06 | 33 | FALSE | 0 | 2026-11-16 | 2026-11-16 | 2026-11-16 | 2026-11-16 | 2026-11-16 | 2026-11-16 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 51 | 8 | 400 | 1 | 0 |  |  | 0 | 760 | 0 | 0 | 0 | 5 | [6 empty] | 0 |  | 1
29 | 29 | 5.2 | 2 | Yes | Lessons learned | Auto | 2 | 26 | FS | [13 empty] | 2027-01-05 | 2027-01-06 |  |  | 2027-01-05 | 2027-01-06 | 0 | 0 | 2027-01-05 | 2027-01-06 | 0 | 0 | Yes |  |  |  | 0% | Not Started | Priya Sharma |  | Priya Sharma |  | 16 | 1520 |  |  | Sprint 9 | 2 | 26 |  | 2027-01-05 | 2027-01-06 | 2 | 16 | 1520 | [8 empty] | 1520 | 0 | 0 | 0 | 2 | 29 | 32 | 2 | FALSE | 0 | 1 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 2958465 | 2027-01-05 | 2027-01-06 | 2027-01-05 | 2027-01-06 | 0 | 16 | 1520 | 16 | 1520 | 0 | 2912074 |  |  |  | 100000 |  |  |  | 30 | 2027-01-06 | 2027-01-06 | 2027-01-05 | 0 | TRUE | 0 | 2027-01-05 | 2027-01-06 | 2027-01-05 | 2027-01-06 | 2027-01-05 | 2027-01-06 |  |  |  |  | 2027-01-05 | 0 | 0 | 0 | 2027-01-05 | 0 | 0 | 0 | 83 | 84 | 8 | 656 | 2 | 0 | 26 |  | 0 | 1520 | 0 | 0 | 0 | 5 | [5 empty] | 2027-01-05 | 0 |  | 2
30 | 30 | 5.3 | 2 | Yes | Project closed | Auto | 0 | 29 | FS | [13 empty] | 2027-01-06 | 2027-01-06 |  |  | 2027-01-06 | 2027-01-06 | 0 | 0 | 2027-01-06 | 2027-01-06 | 0 | 0 | Yes |  |  |  | 0% | Not Started |  |  |  |  | 0 | 0 |  |  | Sprint 9 |  | 29 | Milestone | 2027-01-06 | 2027-01-06 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 2 | 30 | 32 | 0 | FALSE | 0 | 1 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 2958465 | 2027-01-06 | 2027-01-06 | 2027-01-06 | 2027-01-06 | 0 | 0 | 0 | 0 | 0 | 0 | 2912072 |  |  |  | 100000 |  |  |  | 0 | 2958465 | 2027-01-06 | 2027-01-06 | 0 | TRUE | 0 | 2027-01-06 | 2027-01-06 | 2027-01-06 | 2027-01-06 | 2027-01-06 | 2027-01-06 |  |  |  |  | 2027-01-06 | 0 | 0 | 0 | 2027-01-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 29 | 2027-01-06 | 0 | 0 | 0 | 0 | 0 | 5 |  | 2027-01-06 |  |  |  | 2027-01-06 | 0 |  | 0
| 31 | [69 empty] | 31 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 32 | [69 empty] | 32 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 33 | [69 empty] | 33 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 34 | [69 empty] | 34 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 35 | [69 empty] | 35 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 36 | [69 empty] | 36 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 37 | [69 empty] | 37 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 38 | [69 empty] | 38 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 39 | [69 empty] | 39 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 40 | [69 empty] | 40 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 41 | [69 empty] | 41 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 42 | [69 empty] | 42 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 43 | [69 empty] | 43 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 44 | [69 empty] | 44 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 45 | [69 empty] | 45 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 46 | [69 empty] | 46 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 47 | [69 empty] | 47 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 48 | [69 empty] | 48 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 49 | [69 empty] | 49 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 50 | [69 empty] | 50 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 51 | [69 empty] | 51 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 52 | [69 empty] | 52 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 53 | [69 empty] | 53 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 54 | [69 empty] | 54 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 55 | [69 empty] | 55 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 56 | [69 empty] | 56 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 57 | [69 empty] | 57 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 58 | [69 empty] | 58 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 59 | [69 empty] | 59 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 60 | [69 empty] | 60 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 61 | [69 empty] | 61 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 62 | [69 empty] | 62 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 63 | [69 empty] | 63 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 64 | [69 empty] | 64 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 65 | [69 empty] | 65 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 66 | [69 empty] | 66 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 67 | [69 empty] | 67 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 68 | [69 empty] | 68 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 69 | [69 empty] | 69 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 70 | [69 empty] | 70 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 71 | [69 empty] | 71 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 72 | [69 empty] | 72 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 73 | [69 empty] | 73 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 74 | [69 empty] | 74 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 75 | [69 empty] | 75 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 76 | [69 empty] | 76 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 77 | [69 empty] | 77 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 78 | [69 empty] | 78 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 79 | [69 empty] | 79 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 80 | [69 empty] | 80 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 81 | [69 empty] | 81 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 82 | [69 empty] | 82 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 83 | [69 empty] | 83 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 84 | [69 empty] | 84 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 85 | [69 empty] | 85 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 86 | [69 empty] | 86 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 87 | [69 empty] | 87 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 88 | [69 empty] | 88 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 89 | [69 empty] | 89 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 90 | [69 empty] | 90 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 91 | [69 empty] | 91 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 92 | [69 empty] | 92 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 93 | [69 empty] | 93 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 94 | [69 empty] | 94 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 95 | [69 empty] | 95 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 96 | [69 empty] | 96 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 97 | [69 empty] | 97 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 98 | [69 empty] | 98 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 99 | [69 empty] | 99 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 100 | [69 empty] | 100 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 101 | [69 empty] | 101 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 102 | [69 empty] | 102 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 103 | [69 empty] | 103 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 104 | [69 empty] | 104 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 105 | [69 empty] | 105 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 106 | [69 empty] | 106 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 107 | [69 empty] | 107 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 108 | [69 empty] | 108 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 109 | [69 empty] | 109 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 110 | [69 empty] | 110 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 111 | [69 empty] | 111 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 112 | [69 empty] | 112 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 113 | [69 empty] | 113 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 114 | [69 empty] | 114 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 115 | [69 empty] | 115 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 116 | [69 empty] | 116 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 117 | [69 empty] | 117 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 118 | [69 empty] | 118 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 119 | [69 empty] | 119 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 120 | [69 empty] | 120 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 121 | [69 empty] | 121 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 122 | [69 empty] | 122 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 123 | [69 empty] | 123 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 124 | [69 empty] | 124 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 125 | [69 empty] | 125 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 126 | [69 empty] | 126 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 127 | [69 empty] | 127 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 128 | [69 empty] | 128 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 129 | [69 empty] | 129 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 130 | [69 empty] | 130 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 131 | [69 empty] | 131 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 132 | [69 empty] | 132 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 133 | [69 empty] | 133 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 134 | [69 empty] | 134 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 135 | [69 empty] | 135 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 136 | [69 empty] | 136 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 137 | [69 empty] | 137 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 138 | [69 empty] | 138 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 139 | [69 empty] | 139 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 140 | [69 empty] | 140 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 141 | [69 empty] | 141 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 142 | [69 empty] | 142 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 143 | [69 empty] | 143 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 144 | [69 empty] | 144 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 145 | [69 empty] | 145 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 146 | [69 empty] | 146 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 147 | [69 empty] | 147 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 148 | [69 empty] | 148 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 149 | [69 empty] | 149 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 150 | [69 empty] | 150 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 151 | [69 empty] | 151 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 152 | [69 empty] | 152 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 153 | [69 empty] | 153 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 154 | [69 empty] | 154 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 155 | [69 empty] | 155 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 156 | [69 empty] | 156 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 157 | [69 empty] | 157 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 158 | [69 empty] | 158 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 159 | [69 empty] | 159 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 160 | [69 empty] | 160 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 161 | [69 empty] | 161 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 162 | [69 empty] | 162 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 163 | [69 empty] | 163 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 164 | [69 empty] | 164 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 165 | [69 empty] | 165 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 166 | [69 empty] | 166 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 167 | [69 empty] | 167 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 168 | [69 empty] | 168 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 169 | [69 empty] | 169 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 170 | [69 empty] | 170 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 171 | [69 empty] | 171 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 172 | [69 empty] | 172 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 173 | [69 empty] | 173 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 174 | [69 empty] | 174 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 175 | [69 empty] | 175 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 176 | [69 empty] | 176 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 177 | [69 empty] | 177 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 178 | [69 empty] | 178 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 179 | [69 empty] | 179 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 180 | [69 empty] | 180 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 181 | [69 empty] | 181 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 182 | [69 empty] | 182 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 183 | [69 empty] | 183 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 184 | [69 empty] | 184 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 185 | [69 empty] | 185 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 186 | [69 empty] | 186 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 187 | [69 empty] | 187 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 188 | [69 empty] | 188 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 189 | [69 empty] | 189 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 190 | [69 empty] | 190 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 191 | [69 empty] | 191 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 192 | [69 empty] | 192 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 193 | [69 empty] | 193 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 194 | [69 empty] | 194 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 195 | [69 empty] | 195 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 196 | [69 empty] | 196 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 197 | [69 empty] | 197 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 198 | [69 empty] | 198 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 199 | [69 empty] | 199 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
| 200 | [69 empty] | 200 | 0 | 0 | FALSE | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2958465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | FALSE | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0
Formulas:
PLAN / ACTUAL / FORECAST = IF(Tasks[[#This Row],[Task Name]]="","",IF(N(Tasks[[#This Row],[Baseline Start]])>0,Tasks[[#This Row],[Baseline Start]],Tasks[[#This Row],[_CalcStart]]))
Note on A5: Position in the list; renumbers when rows move (like MS Project).
Note on B5: Permanent number that predecessors refer to. Each task needs a different one.
Note on C5: Outline number, generated from Level.
Note on D5: Outline level: 1 = phase, 2 = task, 3 = sub-task ... (at most 1 more than the row above).
Note on E5: Yes when Level <= Settings > OutlineShowLevel: filter on Yes to collapse the outline to that level (or use the 1 2 3 outline buttons at the top left).
Note on G5: Auto = scheduled from predecessors and the constraint. Manual = starts on the Constraint Date (finish constraints: finishes on it).
Note on H5: Working days. 0 = milestone.
Note on I5: UID of a predecessor: a detail task above this one.
Note on J5: FS, SS, FF or SF (blank = FS).
Note on K5: Lag in working days (negative = lead).
Note on L5: UID of a predecessor: a detail task above this one.
Note on M5: FS, SS, FF or SF (blank = FS).
Note on N5: Lag in working days (negative = lead).
Note on O5: UID of a predecessor: a detail task above this one.
Note on P5: FS, SS, FF or SF (blank = FS).
Note on Q5: Lag in working days (negative = lead).
Note on R5: UID of a predecessor: a detail task above this one.
Note on S5: FS, SS, FF or SF (blank = FS).
Note on T5: Lag in working days (negative = lead).
Note on U5: MS Project constraint (dropdown). Blank = Start No Earlier Than when a Constraint Date is entered, otherwise As Soon As Possible. Constraint dates win over links.
Note on V5: Date for the Constraint. Manual tasks are pinned to it.
Note on W5: Optional deadline; Deadline Check flags a forecast finish after it.
Note on X5: Baseline Start if a baseline is set, otherwise calculated from durations and links.
Note on Y5: Baseline Finish if a baseline is set, otherwise calculated.
Note on AB5: Current schedule: actuals where entered, otherwise recalculated from predecessors.
Note on AC5: Current schedule finish.
Note on AD5: Forecast Start minus Planned Start, in working days.
Note on AE5: Forecast Finish minus Planned Finish, in working days.
Note on AF5: Latest start that doesn't delay the project finish or a deadline (critical path backward pass).
Note on AG5: Latest finish that doesn't delay the project finish or a deadline.
Note on AH5: Total slack: working days this task can slip before it delays the project or a deadline.
Note on AI5: Free slack: working days it can slip before it delays any successor.
Note on AJ5: Yes when Total Slack <= CriticalSlackDays (Settings) and the task isn't complete.
Note on AL5: Explains predecessor links and constraints that are ignored.
Note on AM5: Enter 0-100%. An Actual Finish counts as 100%.
Note on AN5: % Complete, rolled up to summaries (duration-weighted).
Note on AP5: The task's person (dropdown). More people on the task: Assignments sheet.
Note on AQ5: Share of the resource's time (blank = DefaultUnits).
Note on AR5: Everyone on the task: Resource plus the Assignments sheet's rows for its UID (MS Project's Resource Names).
Note on AS5: Yes when this task's resource is over 100% of capacity (after leave) in a week the task runs: see Resource Report. Only weeks shown there count.
Note on AT5: Hours = Duration x HoursPerDay x Units, for each person on the task.
Note on AV5: Cost to date of a detail task. Blank = Cost x Progress (as MS Project calculates it). Summaries roll up in the AC column.
Note on AW5: Optional: the sprint this task is planned in (dropdown). Blank = the sprint containing its forecast start.
Note on AX5: Planned Sprint if entered, otherwise the sprint containing the forecast start.
Note on AY5: Story points (optional estimate for agile reporting). Detail tasks only.
Note on AZ5: Predecessors in MS Project notation, by ID.
Note on BB5: Copy the 5 BL Source columns, then Paste Special > Values onto the 5 Baseline columns.
Note on BG5: Frozen plan. Filled by pasting values from the BL Source columns.
Note on BL5: Duration minus Baseline Duration (working days).
Note on BM5: Work minus Baseline Work (hours).
Note on BN5: Cost minus Baseline Cost.
Note on BO5: Budget at completion: Baseline Cost once a baseline is set, otherwise Cost.
Note on BP5: Planned value: the budget of the work planned before the status date.
Note on BQ5: Earned value: Budget x Progress.
Note on BR5: Actual cost to date: Actual Cost, or Cost x Progress when it is blank.

## Gantt
Customer Portal Implementation - Gantt Chart | [22 empty] | Planned (outline) | [11 empty] | Done (% complete) | [11 empty] | Remaining - on track | [11 empty] | Remaining - late vs plan | [11 empty] | Remaining - critical
Status date: Sun 25-Oct-2026 ¦ Forecast finish: 06-Jan-2027 ¦ Planned finish: 06-Jan-2027 | [22 empty] | Summary (forecast) | [11 empty] | Milestone (forecast) | [11 empty] | Deadline | [11 empty] | Status date | [11 empty] | Non-working day
Timeline: conditional formatting only (no formulas), so it costs no recalculation. | [21 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W
[22 empty] | Sep 26 | [23 empty] | Oct 26 | [30 empty] | Nov 26 | [29 empty] | Dec 26 | [30 empty] | Jan 27 | [30 empty] | Feb 27
ID | WBS | Task | Dur | Planned Start | Planned Finish | Forecast Start | Forecast Finish | % | Resource | Status | Show | _Row | _IsSummary | _IsMilestone | _DoneFrom | _DoneTo | _RemFrom | _RemTo | _Late | _Deadline | _Critical | time axis 2026-09-07 to 2027-02-03
1 | 1 | Initiation | 6 | 2026-09-07 | 2026-09-11 | 2026-09-07 | 2026-09-14 | 100% |  | Complete | Yes | 1 | TRUE | FALSE | 0 | 0 | 0 | 0 | TRUE | 0 | FALSE
2 | 1.1 | Project charter & scope statement | 3 | 2026-09-07 | 2026-09-09 | 2026-09-07 | 2026-09-10 | 100% | Priya Sharma | Complete | Yes | 2 | FALSE | FALSE | 2026-09-07 | 2026-09-10 | 0 | 0 | TRUE | 0 | FALSE
3 | 1.2 | Stakeholder kickoff workshop | 2 | 2026-09-10 | 2026-09-11 | 2026-09-11 | 2026-09-14 | 100% | Morgan Patel | Complete | Yes | 3 | FALSE | FALSE | 2026-09-11 | 2026-09-14 | 0 | 0 | TRUE | 0 | FALSE
4 | 1.3 | Kickoff complete | 0 | 2026-09-11 | 2026-09-11 | 2026-09-14 | 2026-09-14 | 100% |  | Complete | Yes | 4 | FALSE | TRUE | 0 | 0 | 0 | 0 | TRUE | 0 | FALSE
5 | 2 | Requirements & Design | 16 | 2026-09-14 | 2026-10-01 | 2026-09-15 | 2026-10-06 | 100% |  | Complete | Yes | 5 | TRUE | FALSE | 0 | 0 | 0 | 0 | TRUE | 0 | FALSE
6 | 2.1 | Requirements gathering | 8 | 2026-09-14 | 2026-09-23 | 2026-09-15 | 2026-09-25 | 100% | Morgan Patel | Complete | Yes | 6 | FALSE | FALSE | 2026-09-15 | 2026-09-25 | 0 | 0 | TRUE | 0 | FALSE
7 | 2.2 | Solution architecture | 5 | 2026-09-17 | 2026-09-23 | 2026-09-18 | 2026-09-25 | 100% | Alex Chen, Jordan Lee[50%] | Complete | Yes | 7 | FALSE | FALSE | 2026-09-18 | 2026-09-25 | 0 | 0 | TRUE | 0 | FALSE
8 | 2.3 | UX wireframes & prototype | 6 | 2026-09-24 | 2026-10-01 | 2026-09-28 | 2026-10-06 | 100% | Casey Kim | Complete | Yes | 8 | FALSE | FALSE | 2026-09-28 | 2026-10-06 | 0 | 0 | TRUE | 0 | FALSE
9 | 2.4 | Design sign-off | 0 | 2026-10-01 | 2026-10-01 | 2026-10-06 | 2026-10-06 | 100% |  | Complete | Yes | 9 | FALSE | TRUE | 0 | 0 | 0 | 0 | TRUE | 0 | FALSE
10 | 3 | Build | 24 | 2026-10-02 | 2026-10-30 | 2026-10-07 | 2026-11-09 | 45.13% |  | Behind | Yes | 10 | TRUE | FALSE | 0 | 0 | 0 | 0 | TRUE | 0 | TRUE
11 | 3.1 | Backend | 24 | 2026-10-02 | 2026-10-30 | 2026-10-07 | 2026-11-09 | 47.62% |  | Behind | Yes | 11 | TRUE | FALSE | 0 | 0 | 0 | 0 | TRUE | 0 | TRUE
12 | 3.1.1 | Data model & database setup | 5 | 2026-10-02 | 2026-10-08 | 2026-10-07 | 2026-10-14 | 100% | Jordan Lee | Complete | Yes | 12 | FALSE | FALSE | 2026-10-07 | 2026-10-14 | 0 | 0 | TRUE | 0 | FALSE
13 | 3.1.2 | Core API endpoints | 10 | 2026-10-09 | 2026-10-22 | 2026-10-15 | 2026-10-30 | 50% | Jordan Lee | Behind | Yes | 13 | FALSE | FALSE | 2026-10-15 | 2026-10-22 | 2026-10-23 | 2026-10-30 | TRUE | 0 | TRUE
14 | 3.1.3 | Payment gateway integration | 6 | 2026-10-23 | 2026-10-30 | 2026-11-02 | 2026-11-09 | 0% | Jordan Lee | Late Start | Yes | 14 | FALSE | FALSE | 0 | 0 | 2026-11-02 | 2026-11-09 | TRUE | 0 | TRUE
15 | 3.2 | Frontend | 23 | 2026-10-02 | 2026-10-29 | 2026-10-07 | 2026-11-06 | 42.86% |  | Behind | Yes | 15 | TRUE | FALSE | 0 | 0 | 0 | 0 | TRUE | 0 | TRUE
16 | 3.2.1 | UI component library | 6 | 2026-10-02 | 2026-10-09 | 2026-10-07 | 2026-10-16 | 100% | Sam Rivera | Complete | Yes | 16 | FALSE | FALSE | 2026-10-07 | 2026-10-16 | 0 | 0 | TRUE | 0 | FALSE
17 | 3.2.2 | Feature screens | 12 | 2026-10-13 | 2026-10-28 | 2026-10-19 | 2026-11-05 | 25% | Sam Rivera, Casey Kim[50%] | Behind | Yes | 17 | FALSE | FALSE | 2026-10-19 | 2026-10-23 | 2026-10-24 | 2026-11-05 | TRUE | 0 | TRUE
18 | 3.2.3 | Accessibility review | 3 | 2026-10-27 | 2026-10-29 | 2026-11-04 | 2026-11-06 | 0% | Casey Kim[50%] | Not Started | Yes | 18 | FALSE | FALSE | 0 | 0 | 2026-11-04 | 2026-11-06 | TRUE | 0 | TRUE
19 | 3.3 | Build complete | 0 | 2026-10-30 | 2026-10-30 | 2026-11-09 | 2026-11-09 | 0% |  | Not Started | Yes | 19 | FALSE | TRUE | 0 | 0 | 0 | 0 | TRUE | 2026-11-06 | TRUE
20 | 4 | Test & Release | 36 | 2026-11-02 | 2027-01-04 | 2026-11-10 | 2027-01-04 | 0% |  | Not Started | Yes | 20 | TRUE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | TRUE
21 | 4.1 | System integration testing | 8 | 2026-11-02 | 2026-11-11 | 2026-11-10 | 2026-11-19 | 0% | Taylor Morgan, Sam Rivera[50%] | Not Started | Yes | 21 | FALSE | FALSE | 0 | 0 | 2026-11-10 | 2026-11-19 | TRUE | 0 | FALSE
22 | 4.2 | User acceptance testing | 6 | 2026-12-07 | 2026-12-14 | 2026-12-07 | 2026-12-14 | 0% | Morgan Patel, Taylor Morgan | Not Started | Yes | 22 | FALSE | FALSE | 0 | 0 | 2026-12-07 | 2026-12-14 | FALSE | 0 | TRUE
23 | 4.3 | Training & user guides | 5 | 2026-11-04 | 2026-11-10 | 2026-11-12 | 2026-11-18 | 0% | Casey Kim[50%] | Not Started | Yes | 23 | FALSE | FALSE | 0 | 0 | 2026-11-12 | 2026-11-18 | TRUE | 0 | FALSE
24 | 4.4 | Go-live readiness review | 1 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 0% | Priya Sharma | Not Started | Yes | 24 | FALSE | FALSE | 0 | 0 | 2026-12-15 | 2026-12-15 | FALSE | 0 | TRUE
25 | 4.5 | Go-live | 0 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 0% |  | Not Started | Yes | 25 | FALSE | TRUE | 0 | 0 | 0 | 0 | FALSE | 2026-12-18 | TRUE
26 | 4.6 | Hypercare support | 10 | 2026-12-16 | 2027-01-04 | 2026-12-16 | 2027-01-04 | 0% | Jordan Lee[50%] | Not Started | Yes | 26 | FALSE | FALSE | 0 | 0 | 2026-12-16 | 2027-01-04 | FALSE | 0 | TRUE
27 | 5 | Project Close | 34 | 2026-11-16 | 2027-01-06 | 2026-11-16 | 2027-01-06 | 0% |  | Not Started | Yes | 27 | TRUE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | TRUE
28 | 5.1 | Steering committee update | 1 | 2026-11-16 | 2026-11-16 | 2026-11-16 | 2026-11-16 | 0% | Priya Sharma | Not Started | Yes | 28 | FALSE | FALSE | 0 | 0 | 2026-11-16 | 2026-11-16 | FALSE | 0 | FALSE
29 | 5.2 | Lessons learned | 2 | 2027-01-05 | 2027-01-06 | 2027-01-05 | 2027-01-06 | 0% | Priya Sharma | Not Started | Yes | 29 | FALSE | FALSE | 0 | 0 | 2027-01-05 | 2027-01-06 | FALSE | 0 | TRUE
30 | 5.3 | Project closed | 0 | 2027-01-06 | 2027-01-06 | 2027-01-06 | 2027-01-06 | 0% |  | Not Started | Yes | 30 | FALSE | TRUE | 0 | 0 | 0 | 0 | FALSE | 0 | TRUE
[12 empty] | 31 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 32 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 33 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 34 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 35 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 36 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 37 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 38 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 39 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 40 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 41 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 42 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 43 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 44 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 45 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 46 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 47 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 48 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 49 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 50 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 51 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 52 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 53 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 54 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 55 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 56 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 57 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 58 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 59 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 60 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 61 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 62 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 63 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 64 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 65 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 66 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 67 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 68 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 69 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 70 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 71 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 72 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 73 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 74 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 75 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 76 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 77 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 78 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 79 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 80 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 81 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 82 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 83 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 84 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 85 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 86 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 87 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 88 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 89 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 90 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 91 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 92 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 93 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 94 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 95 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 96 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 97 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 98 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 99 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 100 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 101 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 102 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 103 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 104 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 105 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 106 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 107 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 108 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 109 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 110 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 111 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 112 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 113 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 114 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 115 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 116 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 117 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 118 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 119 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 120 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 121 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 122 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 123 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 124 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 125 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 126 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 127 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 128 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 129 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 130 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 131 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 132 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 133 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 134 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 135 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 136 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 137 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 138 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 139 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 140 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 141 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 142 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 143 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 144 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 145 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 146 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 147 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 148 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 149 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 150 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 151 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 152 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 153 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 154 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 155 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 156 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 157 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 158 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 159 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 160 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 161 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 162 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 163 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 164 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 165 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 166 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 167 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 168 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 169 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 170 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 171 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 172 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 173 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 174 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 175 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 176 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 177 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 178 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 179 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 180 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 181 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 182 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 183 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 184 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 185 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 186 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 187 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 188 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 189 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 190 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 191 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 192 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 193 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 194 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 195 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 196 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 197 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 198 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 199 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
[12 empty] | 200 | FALSE | FALSE | 0 | 0 | 0 | 0 | FALSE | 0 | FALSE
Note on L5: Yes down to Settings > OutlineShowLevel: filter on Yes to collapse the outline.

## Resources
Resource Sheet
Like MS Project's Resource Sheet. Names here feed the Resource dropdown on Tasks. Add rows to the table for more people.
| Resource Name | Initials | Group | Type | Max Units | Std Rate | Email | Tasks | Work | Cost | Actual Cost | Notes
| Priya Sharma | PS | Project Manager | Work | 50% | 95 | priya@example.com | 4 | 56 | 5320 | 3040
| Morgan Patel | MP | Business Analyst | Work | 100% | 70 | morgan@example.com | 3 | 128 | 8960 | 6160
| Alex Chen | AC | Solution Architect | Work | 50% | 110 | alex@example.com | 1 | 40 | 4400 | 4400
| Casey Kim | CK | UX Designer | Work | 100% | 75 | casey@example.com | 4 | 128 | 9600 | 4500
| Jordan Lee | JL | Backend Developer | Work | 100% | 85 | jordan@example.com | 5 | 228 | 19380 | 9180
| Sam Rivera | SR | Frontend Developer | Work | 100% | 80 | sam@example.com | 3 | 176 | 14080 | 5760
| Taylor Morgan | TM | QA Engineer | Work | 100% | 65 | taylor@example.com | 2 | 112 | 7280 | 0
Note on E5: Work, Material or Cost (MS Project resource types).
Note on F5: Availability: 100% = full time.
Note on G5: Standard rate per hour.
Note on I5: Detail tasks assigned to this resource (Tasks > Resource, and the Assignments sheet).
Note on J5: Assigned work (hours).
Note on K5: Assigned cost.
Note on L5: Cost to date: Actual Cost entered on Tasks (shared by cost between the task's people), or Cost x Progress where blank.

## Assignments
Assignments
More than one person on a task: the first goes on Tasks (Resource, Units); add a row here for each other person. Work, cost, the Resource Report and Sprints include them. Add rows to the table for more.
| Task UID | Task | Resource | Units | Work | Cost | Check | _TaskPos | _Valid | _Key | _Text | _StartWD | _FinishWD | _WorkPerWD | _WorkBeforeStart | _WorkDone | _ActualCost | _Late | _Critical | _OverAllocated
| 7 | Solution architecture | Jordan Lee | 50% | 20 | 1700 |  | 7 | 1 | 7001 | Jordan Lee[50%] | 10 | 15 | 3.3333 | 30 | 20 | 1700 | 0 | 0
| 17 | Feature screens | Casey Kim | 50% | 48 | 3600 |  | 17 | 1 | 17001 | Casey Kim[50%] | 31 | 44 | 3.4286 | 102.8571 | 12 | 900 | 1 | 1
| 21 | System integration testing | Sam Rivera | 50% | 32 | 2560 |  | 21 | 1 | 21001 | Sam Rivera[50%] | 47 | 54 | 4 | 184 | 0 | 0 | 1 | 0
| 22 | User acceptance testing | Taylor Morgan |  | 48 | 3120 |  | 22 | 1 | 22001 | Taylor Morgan | 66 | 71 | 8 | 520 | 0 | 0 | 0 | 1
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on B5: UID of a detail task on Tasks.
Note on C5: The task's name (looked up).
Note on D5: Another person on the task (dropdown). The first person goes on Tasks > Resource.
Note on E5: Share of the person's time on this task (blank = DefaultUnits).
Note on F5: Hours = the task's Duration x HoursPerDay x Units.
Note on G5: Work x the resource's Std Rate.
Note on H5: Explains a row that is ignored.

## Sprints
Customer Portal Implementation - Sprint & Capacity Planning
Sprint calendar from Settings (Sprint1Start, SprintLength, SprintCount); add rows to the table for more sprints. Each task's work is spread evenly over its forecast working days, then summed per sprint.
No | Sprint | Start | End | Working Days | Goal | Tasks Starting | Planned Work | Capacity | Utilisation | Status | Points Capacity | Committed Points | Done Points | Velocity | Remaining Points | Forecast Remaining | Ideal Remaining | _ChartRemaining | _LeaveCol0 | _LeaveCol1 | _LeaveCol2
1 | Sprint 1 | 2026-09-07 | 2026-09-20 | 10 | Charter & kickoff | 5 | 78.4444 | 480 | 16.34% | Closed |  | 18 | 5 | 5 | 77 | 77 | 75.1667 | 77 | 10 | 11 | 12
2 | Sprint 2 | 2026-09-21 | 2026-10-04 | 10 | Requirements | 1 | 119.8413 | 480 | 24.97% | Closed |  | 5 | 13 | 9 | 64 | 64 | 68.3333 | 64 | 10 | 11 | 12
3 | Sprint 3 | 2026-10-05 | 2026-10-18 | 10 | Design & architecture | 4 | 115.0476 | 480 | 23.97% | Closed |  | 18 | 15 | 11 | 49 | 49 | 61.5 | 49 | 11 | 12 | 13
4 | Sprint 4 | 2026-10-19 | 2026-11-01 | 10 | Foundations: DB + components | 1 | 169.5238 | 472 | 35.92% | Active |  | 8 | 0 |  | 49 | 41 | 54.6667 | 49 | 11 | 12 | 13
5 | Sprint 5 | 2026-11-02 | 2026-11-15 | 10 | Core APIs + screens | 5 | 157.1429 | 476 | 33.01% | Future |  | 19 |  |  |  | 25 | 47.8333 | #N/A | 12 | 13 | 14
6 | Sprint 6 | 2026-11-16 | 2026-11-29 | 10 | Payments + screens | 1 | 68 | 404 | 16.83% | Future |  | 1 |  |  |  | 13 | 41 | #N/A | 12 | 13 | 14
7 | Sprint 7 | 2026-11-30 | 2026-12-13 | 10 | Feature complete | 1 | 80 | 480 | 16.67% | Future |  | 5 |  |  |  | 13 | 34.1667 | #N/A | 12 | 13 | 14
8 | Sprint 8 | 2026-12-14 | 2026-12-27 | 8 | System testing | 3 | 48 | 364 | 13.19% | Future |  | 6 |  |  |  | 7 | 27.3333 | #N/A | 13 | 14 | 15
9 | Sprint 9 | 2026-12-28 | 2027-01-10 | 8 | UAT | 2 | 32 | 360 | 8.889% | Future |  | 2 |  |  |  | 0 | 20.5 | #N/A | 13 | 14 | 15
10 | Sprint 10 | 2027-01-11 | 2027-01-24 | 10 | Release & hypercare | 0 | 0 | 480 | 0% | Future |  | 0 |  |  |  | 0 | 13.6667 | #N/A | 14 | 15 | 16
11 | Sprint 11 | 2027-01-25 | 2027-02-07 | 10 | Hypercare | 0 | 0 | 480 | 0% | Future |  | 0 |  |  |  | 0 | 6.8333 | #N/A | 14 | 15 | 16
12 | Sprint 12 | 2027-02-08 | 2027-02-21 | 10 | Close-out | 0 | 0 | 480 | 0% | Future |  | 0 |  |  |  | 0 | 0 | #N/A | 15 | 16 | 17
13 |  | 2027-02-22 | 2027-03-07 | 10 | [13 empty] | #N/A | 15 | 16 | 17
14 |  | 2027-03-08 | 2027-03-21 | 10 | [13 empty] | #N/A | 16 | 17 | 18
15 |  | 2027-03-22 | 2027-04-04 | 10 | [13 empty] | #N/A | 16 | 17 | 18
16 |  | 2027-04-05 | 2027-04-18 | 10 | [13 empty] | #N/A | 17 | 18 | 19
17 |  | 2027-04-19 | 2027-05-02 | 10 | [13 empty] | #N/A | 17 | 18 | 19
18 |  | 2027-05-03 | 2027-05-16 | 10 | [13 empty] | #N/A | 18 | 19 | 20
19 |  | 2027-05-17 | 2027-05-30 | 10 | [13 empty] | #N/A | 18 | 19 | 20
20 |  | 2027-05-31 | 2027-06-13 | 10 | [13 empty] | #N/A | 18 | 19 | 20
21 |  | 2027-06-14 | 2027-06-27 | 10 | [13 empty] | #N/A | 19 | 20 | 21
22 |  | 2027-06-28 | 2027-07-11 | 10 | [13 empty] | #N/A | 19 | 20 | 21
23 |  | 2027-07-12 | 2027-07-25 | 10 | [13 empty] | #N/A | 20 | 21 | 22
24 |  | 2027-07-26 | 2027-08-08 | 10 | [13 empty] | #N/A | 20 | 21 | 22
25 |  | 2027-08-09 | 2027-08-22 | 10 | [13 empty] | #N/A | 21 | 22 | 23
26 |  | 2027-08-23 | 2027-09-05 | 10 | [13 empty] | #N/A | 21 | 22 | 23
Resource load by sprint (hours) - red = over capacity (Max Units x HoursPerDay x working days, less leave)
| Resource | Max Units | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | Sprint 12
| Sprint start |  | 2026-09-07 | 2026-09-21 | 2026-10-05 | 2026-10-19 | 2026-11-02 | 2026-11-16 | 2026-11-30 | 2026-12-14 | 2026-12-28 | 2027-01-11 | 2027-01-25 | 2027-02-08
| Priya Sharma | 50% | 24 | 0 | 0 | 0 | 0 | 8 | 0 | 8 | 16 | 0 | 0 | 0
| Morgan Patel | 100% | 44.4444 | 35.5556 | 0 | 0 | 0 | 0 | 40 | 8 | 0 | 0 | 0 | 0
| Alex Chen | 50% | 6.6667 | 33.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Casey Kim | 100% | 0 | 34.2857 | 13.7143 | 34.2857 | 33.7143 | 12 | 0 | 0 | 0 | 0 | 0 | 0
| Jordan Lee | 100% | 3.3333 | 16.6667 | 53.3333 | 66.6667 | 48 | 0 | 0 | 24 | 16 | 0 | 0 | 0
| Sam Rivera | 100% | 0 | 0 | 48 | 68.5714 | 43.4286 | 16 | 0 | 0 | 0 | 0 | 0 | 0
| Taylor Morgan | 100% | 0 | 0 | 0 | 0 | 32 | 32 | 40 | 8 | 0 | 0 | 0 | 0
Resource utilisation by sprint (% of capacity after leave)
| Resource | Max Units | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | Sprint 12
| Sprint start |  | 2026-09-07 | 2026-09-21 | 2026-10-05 | 2026-10-19 | 2026-11-02 | 2026-11-16 | 2026-11-30 | 2026-12-14 | 2026-12-28 | 2027-01-11 | 2027-01-25 | 2027-02-08
| Priya Sharma | 50% | 60% | 0% | 0% | 0% | 0% | 20% | 0% | 25% | 50% | 0% | 0% | 0%
| Morgan Patel | 100% | 55.56% | 44.44% | 0% | 0% | 0% | 0% | 50% | 12.5% | 0% | 0% | 0% | 0%
| Alex Chen | 50% | 16.67% | 83.33% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Casey Kim | 100% | 0% | 42.86% | 17.14% | 42.86% | 42.14% | 300% | 0% | 0% | 0% | 0% | 0% | 0%
| Jordan Lee | 100% | 4.167% | 20.83% | 66.67% | 92.59% | 60% | 0% | 0% | 54.55% | 25% | 0% | 0% | 0%
| Sam Rivera | 100% | 0% | 0% | 60% | 85.71% | 57.14% | 20% | 0% | 0% | 0% | 0% | 0% | 0%
| Taylor Morgan | 100% | 0% | 0% | 0% | 0% | 40% | 40% | 50% | 12.5% | 0% | 0% | 0% | 0%
Leave days by sprint (helper for the utilisation grid)
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 | 0 | 0 | 0 | 0 | 0 | 9.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
Start = Sprint1Start+(SprintTable[[#This Row],[No]]-1)*SprintLength
End = SprintTable[[#This Row],[Start]]+SprintLength-1
Working Days = NETWORKDAYS.INTL(SprintTable[[#This Row],[Start]],SprintTable[[#This Row],[End]],WorkWeek,Holidays)
Note on H5: Hours of task work falling in the sprint.
Note on I5: Sum of Work resources' Max Units x HoursPerDay x working days, less the leave of the people in the grids below (Leave sheet).
Note on L5: Optional: story points the team can take on in the sprint. Committed Points turn red above it.
Note on M5: Story points of the tasks in this sprint (Tasks > Sprint).
Note on N5: Story points of tasks finished during the sprint (by Actual Finish).
Note on O5: Average Done Points of this and the two previous sprints (closed sprints only).
Note on P5: Release burndown: story points not yet done at the sprint end (or the status date).
Note on Q5: Points still open at the sprint end if tasks finish on their forecast dates.
Note on R5: Straight line from the total scope to zero at the last sprint.
Note on T5: LeaveTable column of a month the sprint touches (for the leave look-ups).
Note on U5: LeaveTable column of a month the sprint touches (for the leave look-ups).
Note on V5: LeaveTable column of a month the sprint touches (for the leave look-ups).

## Holidays
Holidays & Non-Working Days
Every date in this table is skipped by all scheduling formulas (named range: Holidays). Add rows to the table as needed.
| Date | Description
| 2026-12-24 | Christmas Eve (example - replace with your calendar)
| 2026-12-25 | Christmas Day (example)
| 2026-12-31 | New Year's Eve (example)
| 2027-01-01 | New Year's Day (example)

## Leave
Leave
One row per person, one column per month. Type the days off, e.g. "16, 17(0.5)" under Nov-26 = all of 16 November and half of the 17th. Leave lowers capacity (Resource Report, Sprints) but doesn't move tasks. Add a month by typing its name (e.g. "Jan-29") in the header cell after the last month.
| Resource | Jan-26 | Feb-26 | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27 | Apr-27 | May-27 | Jun-27 | Jul-27 | Aug-27 | Sep-27 | Oct-27 | Nov-27 | Dec-27 | Jan-28 | Feb-28 | Mar-28 | Apr-28 | May-28 | Jun-28 | Jul-28 | Aug-28 | Sep-28 | Oct-28 | Nov-28 | Dec-28
| Casey Kim | [10 empty] | 16, 17(0.5), 18, 19, 20, 23, 24, 25, 26, 27
| Jordan Lee | [9 empty] | 30 |  | 21, 22, 23(0.5)
| Sam Rivera | [10 empty] | 2(0.5)
| Morgan Patel | [11 empty] | 28, 29, 30
Note on B4: Name as on the Resources sheet.
Note on C4: Days off in Jan-26: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on D4: Days off in Feb-26: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on E4: Days off in Mar-26: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on F4: Days off in Apr-26: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on G4: Days off in May-26: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on H4: Days off in Jun-26: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on I4: Days off in Jul-26: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on J4: Days off in Aug-26: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on K4: Days off in Sep-26: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on L4: Days off in Oct-26: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on M4: Days off in Nov-26: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on N4: Days off in Dec-26: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on O4: Days off in Jan-27: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on P4: Days off in Feb-27: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on Q4: Days off in Mar-27: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on R4: Days off in Apr-27: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on S4: Days off in May-27: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on T4: Days off in Jun-27: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on U4: Days off in Jul-27: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on V4: Days off in Aug-27: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on W4: Days off in Sep-27: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on X4: Days off in Oct-27: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on Y4: Days off in Nov-27: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on Z4: Days off in Dec-27: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on AA4: Days off in Jan-28: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on AB4: Days off in Feb-28: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on AC4: Days off in Mar-28: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on AD4: Days off in Apr-28: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on AE4: Days off in May-28: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on AF4: Days off in Jun-28: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on AG4: Days off in Jul-28: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on AH4: Days off in Aug-28: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on AI4: Days off in Sep-28: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on AJ4: Days off in Oct-28: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on AK4: Days off in Nov-28: "16, 17(0.5)" = 16th all day, 17th half a day.
Note on AL4: Days off in Dec-28: "16, 17(0.5)" = 16th all day, 17th half a day.

## MSP_Tasks
ID | Unique ID | Name | Outline Level | Task Mode | Duration | Start | Finish | Predecessors | Unique ID Predecessors | Resource Names | % Complete | Actual Start | Actual Finish | Baseline Start | Baseline Finish | Baseline Duration | Baseline Work | Baseline Cost | Actual Cost | Constraint Type | Constraint Date | Deadline | Text1 | Number1 | Notes
1 | 1 | Initiation | 1 | Auto Scheduled |  | 2026-09-07 | 2026-09-14 | [6 empty] | 2026-09-07 | 2026-09-11 | [9 empty] | Phase 1 - summary rows roll up dates, work, cost and progress automatically.
2 | 2 | Project charter & scope statement | 2 | Auto Scheduled | 3d | 2026-09-07 | 2026-09-10 |  |  | Priya Sharma | 100 | 2026-09-07 | 2026-09-10 | 2026-09-07 | 2026-09-09 |  |  |  | 3040 | As Soon As Possible |  |  | Sprint 1 | 3 | Took 1 extra day for sponsor sign-off.
3 | 3 | Stakeholder kickoff workshop | 2 | Auto Scheduled | 2d | 2026-09-11 | 2026-09-14 | 2 | 2 | Morgan Patel | 100 | 2026-09-11 | 2026-09-14 | 2026-09-10 | 2026-09-11 |  |  |  |  | As Soon As Possible |  |  | Sprint 1 | 2
4 | 4 | Kickoff complete | 2 | Auto Scheduled | 0d | 2026-09-14 | 2026-09-14 | 3 | 3 |  | 100 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 |  |  |  |  | As Soon As Possible |  |  | Sprint 1 |  | Milestone (Duration 0).
5 | 5 | Requirements & Design | 1 | Auto Scheduled |  | 2026-09-15 | 2026-10-06 | [6 empty] | 2026-09-14 | 2026-10-01
6 | 6 | Requirements gathering | 2 | Auto Scheduled | 8d | 2026-09-15 | 2026-09-25 | 4 | 4 | Morgan Patel | 100 | 2026-09-15 | 2026-09-25 | 2026-09-14 | 2026-09-23 |  |  |  | 5040 | As Soon As Possible |  |  | Sprint 1 | 8
7 | 7 | Solution architecture | 2 | Auto Scheduled | 5d | 2026-09-18 | 2026-09-25 | 6SS+3d | 6SS+3d | Alex Chen, Jordan Lee[50%] | 100 | 2026-09-18 | 2026-09-25 | 2026-09-17 | 2026-09-23 |  |  |  |  | As Soon As Possible |  |  | Sprint 1 | 5 | Start-to-Start + 3 day lag example.
8 | 8 | UX wireframes & prototype | 2 | Auto Scheduled | 6d | 2026-09-28 | 2026-10-06 | 6 | 6 | Casey Kim | 100 | 2026-09-28 | 2026-10-06 | 2026-09-24 | 2026-10-01 |  |  |  |  | As Soon As Possible |  |  | Sprint 2 | 5
9 | 9 | Design sign-off | 2 | Auto Scheduled | 0d | 2026-10-06 | 2026-10-06 | 7,8 | 7,8 |  | 100 | 2026-10-06 | 2026-10-06 | 2026-10-01 | 2026-10-01 |  |  |  |  | As Soon As Possible |  |  | Sprint 3 |  | Two predecessors - waits for the later one.
10 | 10 | Build | 1 | Auto Scheduled |  | 2026-10-07 | 2026-11-09 | [6 empty] | 2026-10-02 | 2026-10-30
11 | 11 | Backend | 2 | Auto Scheduled |  | 2026-10-07 | 2026-11-09 | [6 empty] | 2026-10-02 | 2026-10-30 | [9 empty] | Level-2 summary with sub-tasks.
12 | 12 | Data model & database setup | 3 | Auto Scheduled | 5d | 2026-10-07 | 2026-10-14 | 9 | 9 | Jordan Lee | 100 | 2026-10-07 | 2026-10-14 | 2026-10-02 | 2026-10-08 |  |  |  |  | As Soon As Possible |  |  | Sprint 3 | 5
13 | 13 | Core API endpoints | 3 | Auto Scheduled | 10d | 2026-10-15 | 2026-10-30 | 12 | 12 | Jordan Lee | 50 | 2026-10-15 |  | 2026-10-09 | 2026-10-22 |  |  |  | 4080 | As Soon As Possible |  |  | Sprint 3 | 8 | In progress - enter % Complete; forecast finish adjusts.
14 | 14 | Payment gateway integration | 3 | Auto Scheduled | 6d | 2026-11-02 | 2026-11-09 | 13 | 13 | Jordan Lee | 0 |  |  | 2026-10-23 | 2026-10-30 |  |  |  |  | As Soon As Possible |  |  | Sprint 5 | 5
15 | 15 | Frontend | 2 | Auto Scheduled |  | 2026-10-07 | 2026-11-06 | [6 empty] | 2026-10-02 | 2026-10-29
16 | 16 | UI component library | 3 | Auto Scheduled | 6d | 2026-10-07 | 2026-10-16 | 9 | 9 | Sam Rivera | 100 | 2026-10-07 | 2026-10-16 | 2026-10-02 | 2026-10-09 |  |  |  |  | As Soon As Possible |  |  | Sprint 3 | 5
17 | 17 | Feature screens | 3 | Auto Scheduled | 12d | 2026-10-19 | 2026-11-05 | 16,13SS+2d | 16,13SS+2d | Sam Rivera, Casey Kim[50%] | 25 | 2026-10-19 |  | 2026-10-13 | 2026-10-28 |  |  |  |  | As Soon As Possible |  |  | Sprint 4 | 8
18 | 18 | Accessibility review | 3 | Auto Scheduled | 3d | 2026-11-04 | 2026-11-06 | 17FF+1d | 17FF+1d | Casey Kim[50%] | 0 |  |  | 2026-10-27 | 2026-10-29 |  |  |  |  | As Soon As Possible |  |  | Sprint 5 | 3 | Finish-to-Finish + 1 day; 50% units.
19 | 19 | Build complete | 2 | Auto Scheduled | 0d | 2026-11-09 | 2026-11-09 | 14,18 | 14,18 |  | 0 |  |  | 2026-10-30 | 2026-10-30 |  |  |  |  | As Soon As Possible |  | 2026-11-06 | Sprint 5 |  | Milestone with a deadline of 06-Nov (see Deadline Check).
20 | 20 | Test & Release | 1 | Auto Scheduled |  | 2026-11-10 | 2027-01-04 | [6 empty] | 2026-11-02 | 2027-01-04
21 | 21 | System integration testing | 2 | Auto Scheduled | 8d | 2026-11-10 | 2026-11-19 | 19 | 19 | Taylor Morgan, Sam Rivera[50%] | 0 |  |  | 2026-11-02 | 2026-11-11 |  |  |  |  | As Soon As Possible |  |  | Sprint 5 | 8
22 | 22 | User acceptance testing | 2 | Auto Scheduled | 6d | 2026-12-07 | 2026-12-14 | 21 | 21 | Morgan Patel, Taylor Morgan | 0 |  |  | 2026-12-07 | 2026-12-14 |  |  |  |  | Start No Earlier Than | 2026-12-07 |  | Sprint 7 | 5 | Constraint: Start No Earlier Than 07-Dec (client availability).
23 | 23 | Training & user guides | 2 | Auto Scheduled | 5d | 2026-11-12 | 2026-11-18 | 21SS+2d | 21SS+2d | Casey Kim[50%] | 0 |  |  | 2026-11-04 | 2026-11-10 |  |  |  |  | As Soon As Possible |  |  | Sprint 5 | 3
24 | 24 | Go-live readiness review | 2 | Auto Scheduled | 1d | 2026-12-15 | 2026-12-15 | 22,23,21 | 22,23,21 | Priya Sharma | 0 |  |  | 2026-12-15 | 2026-12-15 |  |  |  |  | As Soon As Possible |  |  | Sprint 8 | 1 | Three predecessors.
25 | 25 | Go-live | 2 | Auto Scheduled | 0d | 2026-12-15 | 2026-12-15 | 24 | 24 |  | 0 |  |  | 2026-12-15 | 2026-12-15 |  |  |  |  | As Soon As Possible |  | 2026-12-18 | Sprint 8 |  | Milestone with a deadline of 18-Dec.
26 | 26 | Hypercare support | 2 | Auto Scheduled | 10d | 2026-12-16 | 2027-01-04 | 25 | 25 | Jordan Lee[50%] | 0 |  |  | 2026-12-16 | 2027-01-04 |  |  |  |  | As Soon As Possible |  |  | Sprint 8 | 5
27 | 27 | Project Close | 1 | Auto Scheduled |  | 2026-11-16 | 2027-01-06 | [6 empty] | 2026-11-16 | 2027-01-06
28 | 28 | Steering committee update | 2 | Manually Scheduled | 1d | 2026-11-16 | 2026-11-16 |  |  | Priya Sharma | 0 |  |  | 2026-11-16 | 2026-11-16 |  |  |  |  | As Soon As Possible |  |  | Sprint 6 | 1 | Manual mode example: fixed on its Constraint Date.
29 | 29 | Lessons learned | 2 | Auto Scheduled | 2d | 2027-01-05 | 2027-01-06 | 26 | 26 | Priya Sharma | 0 |  |  | 2027-01-05 | 2027-01-06 |  |  |  |  | As Soon As Possible |  |  | Sprint 9 | 2
30 | 30 | Project closed | 2 | Auto Scheduled | 0d | 2027-01-06 | 2027-01-06 | 29 | 29 |  | 0 |  |  | 2027-01-06 | 2027-01-06 |  |  |  |  | As Soon As Possible |  |  | Sprint 9 |  | Milestone
Formulas:
Start = IF(IFERROR(INDEX(tsk_Name,(ROW()-ROW(MSPTasks[[#Headers],[ID]])))="",TRUE()),"",INDEX(tsk_FcStart,(ROW()-ROW(MSPTasks[[#Headers],[ID]]))))
Finish = IF(IFERROR(INDEX(tsk_Name,(ROW()-ROW(MSPTasks[[#Headers],[ID]])))="",TRUE()),"",INDEX(tsk_FcFinish,(ROW()-ROW(MSPTasks[[#Headers],[ID]]))))
Baseline Start = IF(IFERROR(INDEX(tsk_Name,(ROW()-ROW(MSPTasks[[#Headers],[ID]])))="",TRUE()),"",INDEX(tsk_PlanStart,(ROW()-ROW(MSPTasks[[#Headers],[ID]]))))
Baseline Finish = IF(IFERROR(INDEX(tsk_Name,(ROW()-ROW(MSPTasks[[#Headers],[ID]])))="",TRUE()),"",INDEX(tsk_PlanFinish,(ROW()-ROW(MSPTasks[[#Headers],[ID]]))))
Actual Start = IF(IFERROR(INDEX(tsk_Name,(ROW()-ROW(MSPTasks[[#Headers],[ID]])))="",TRUE()),"",IF(N(INDEX(tsk_ActStart,(ROW()-ROW(MSPTasks[[#Headers],[ID]]))))=0,"",INDEX(tsk_ActStart,(ROW()-ROW(MSPTasks[[#Headers],[ID]])))))
Actual Finish = IF(IFERROR(INDEX(tsk_Name,(ROW()-ROW(MSPTasks[[#Headers],[ID]])))="",TRUE()),"",IF(N(INDEX(tsk_ActFinish,(ROW()-ROW(MSPTasks[[#Headers],[ID]]))))=0,"",INDEX(tsk_ActFinish,(ROW()-ROW(MSPTasks[[#Headers],[ID]])))))
Deadline = IF(IFERROR(INDEX(tsk_Name,(ROW()-ROW(MSPTasks[[#Headers],[ID]])))="",TRUE()),"",IF(N(INDEX(tsk_Deadline,(ROW()-ROW(MSPTasks[[#Headers],[ID]]))))=0,"",INDEX(tsk_Deadline,(ROW()-ROW(MSPTasks[[#Headers],[ID]])))))
Note on X1: Sprint, in MS Project's custom field Text1 (rename it Sprint in MS Project).
Note on Y1: Story points, in MS Project's custom field Number1.

## MSP_Resources
Name | Initials | Group | Type | Max Units | Standard Rate | Email Address
Priya Sharma | PS | Project Manager | Work | 50% | 95/h | priya@example.com
Morgan Patel | MP | Business Analyst | Work | 100% | 70/h | morgan@example.com
Alex Chen | AC | Solution Architect | Work | 50% | 110/h | alex@example.com
Casey Kim | CK | UX Designer | Work | 100% | 75/h | casey@example.com
Jordan Lee | JL | Backend Developer | Work | 100% | 85/h | jordan@example.com
Sam Rivera | SR | Frontend Developer | Work | 100% | 80/h | sam@example.com
Taylor Morgan | TM | QA Engineer | Work | 100% | 65/h | taylor@example.com

## Lists
Link Type | Task Mode | Constraint | Yes / No | Resource Type | Gantt Days per Column | RAG | RAID Type | RAID Status | Decision Status | Change Status
FS | Auto | As Soon As Possible | Yes | Work | 1 | Green | Risk | Open | Proposed | Submitted
SS | Manual | As Late As Possible | No | Material | 7 | Amber | Assumption | In Progress | Approved | Under Review
FF |  | Must Start On |  | Cost | 30 | Red | Issue | Closed | Rejected | Approved
SF |  | Must Finish On |  |  | 91 |  | Dependency |  | Superseded | Rejected
|  | Start No Earlier Than | [7 empty] | Implemented
Start No Later Than
Finish No Earlier Than
Finish No Later Than
Dropdown sources. Add a value by typing it in the row under a list: the table and its named range grow.